## RS PhII (LCA)
Brazi: Low-Carbon Agriculture for Avoided Deforestation and Reduced Poverty Phase II: Cerrado & Caatinga / Rural Sustentavel (LCA Phase II) LOGFRAME
Last updated: | May 2020
Notes: | * LCA Phase II is carried out in two biomes in Brazil: Cerrado and Caatinga. * Delivery partner: Inter-American Development Bank; Executing agencies: IABS (Cerrado) and FBDS (Caatinga) * All baseline studies will be carried out before implemestation by August 2020. * Caatinga project is expected to complete by 2023. Cerrado project is expected to complete by February 2024. * The term "low carbon agriculture" will be used to refer to the farming and land management practices relating to crop-livestock-forest integration (ICLF). ICLF is a strategy aimed at maximizing positive environmental effects, combining productivity growth with natural resources conservation in the process of intensifying the use of deforested areas in Brazil. It is one of the six low-carbon technologies promoted under the Low-Carbon Agriculture Plan (Plano ABC) of Brazil. ICLF includes four different production systems (variations): (i) integrated crop-livestock or agro-pasture system, which integrates crop and livestock components in rotation, combination or succession in the same area and in a same crop year or for multiple years; (ii) integrated livestock-forest, forest-pasture, or silvopasture system, which integrates livestock and forest components in combination; (iii) integrated crop-forest or agroforestry system, which integrates crop and forest components through the combination of tree species and agricultural (annual or perennial) crops; and (iv) integrated crop-livestock-forest system, which integrates crop, livestock and forest components in rotation, combination or succession in the same area. *Multiplying Units (MUs) refers to rural properties that will adopt low-carbon agriculture technologies as a result of support through this programme. *Demonstration Units (DUs) refers to rural properties that have already adopted ICLF technology (see definition above) and will be used as a model to other producers to demonstrate the benefits of low-carbon agriculture through field days and training.
IMPACT | Impact Indicator 1 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
The programme will contribute to a transformational change in the agriculture and land use sector in key biomes of Brazil, contributing to climate mitigation and support on implementation of Brazilian policies, whilst providing sustainable livelihoods for small and medium farmers. | Extent to which LCA Phase II is likely to have a transformational impact (KPI 15) | Planned | TOTAL
|  |  | Cerrado | TBD - Dec 2020 | TBD | TBD | TBD | TBD | TBD | TBD
|  |  | Caatinga | TBD - Dec 2020 | TBD | TBD | TBD | TBD | 0 | TBD
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
LCA annual report and impact evaluation report
OUTCOME | Outcome Indicator 1 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project | Assumptions
Integrated systems improve sustainable managed land, mitigates emissions and avoids deforestation while increasing farmers’ income & quality of life and supporting replication of related policies. | % increase in income for farmers participating in LCA Phase II | Planned | TOTAL | 0 |  |  |  | 20% | 20% | 20% | Brazilian Ministry of Agriculture (beneficiary) remains committed to promoting LCA Brazilian Federal government policies do not contradict LCA programme Implementation of LCA is consolidated and extended in farms Areas under project intervention would be deforested without the programme
|  |  | Cerrado | 0 |  |  |  | 15% | 15% | 15%
|  |  | Caatinga | 0 |  |  |  | 25% | 25% | 25%
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
LCA annual report and impact evaluation report
| Outcome Indicator 2 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of people with livelihood benefits protected or improved | Planned | TOTAL | 0 | 7600 | 17100 | 23650 | 24250 | 24250 | 24250
|  |  | Cerrado | 0 | 6600 | 15100 | 20950 | 21550 | 21550 | 21550
|  |  | Caatinga | 0 | 1000 | 2000 | 2700 | 2700 | 2700 | 2700
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
LCA annual report and impact evaluation report
| Outcome Indicator 3a |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Greenhouse gas emissions reduced through avoided deforestation (KPI 6) | Planned | TOTAL | 0 |  | 4955000 | 7160000 | 7170000 | 9326000 | 28576000
|  |  | Cerrado | 0 |  | 4950000 | 7150000 | 7150000 | 9306000 | 28556000
|  |  | Caatinga | 0 |  | 5000 | 10000 | 20000 | 20000 | 20000
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
LCA annual report and final report
| Outcome Indicator 3b |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Greenhouse gas emissions reduced through the adoption of sustainable agricultural practices | Planned | TOTAL
|  |  | Cerrado | 0 | 672000 | 1344000 | 2016000 | 2016000 | 6048000 | 6048000
Caatinga
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
LCA annual report and final report
| Outcome Indicator 4 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of hectares where deforestation has been avoided (KPI 8) | Planned | TOTAL | 0
|  |  | Cerrado | 0 |  | 22500 | 32500 | 32500 | 42300 | 129800
|  |  | Caatinga | 0 | TBD - June 2020 | TBD - June 2020 | TBD - June 2020 | TBD - June 2020 | TBD - June 2020
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
Progress reports from executing agencies. Supervision missions will verify reported figures and quality of implementation.
| Outcome Indicator 5 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of farms adopting low carbon agricultural technologies as a result of increased capacities and/or awareness | Planned | TOTAL | 0 | 500 | 1100 | 1300 | 500 | 0 | 3400
|  |  | Cerrado | 0 | 500 | 1000 | 1000 | 500 | 0 | 3000
|  |  | Caatinga | 0 | 0 | 100 | 300 | 0 | 0 | 400
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
Progress reports from executing agencies
| Outcome Indicator 6 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Evidence of programmes / policies within and beyond Brazil that are either (i) using lessons learned from LCA Phase II or (ii) applying LCA Phase II mechanism | Planned |  | 0 | 0 | TBD - Dec 2020 | TBD - Dec 2020 | TBD - Dec 2020 | TBD - Dec 2020 | TBD - Dec 2020
Achieved
Source
Minutes from meetings with the Ministry of Agriculture, which will be part of IDB reports, quarterly progress reports and annual reports
| Outcome Indicator 7 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Participation % increase of farmers in rural organisations | Planned | TOTAL |  |  |  | 10% | 15% | 15% | 15%
|  |  | Cerrado |  |  |  | 10% | 20% | 20% | 20%
|  |  | Caatinga |  |  |  | 10% | 10% | 10% | 10%
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB final report and evaluation report.
OUTPUT 1 (performance weighting 25%) | Output Indicator 1.1 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project | Assumptions
Strengthened capacity of farmers, technical assistants and stakeholders in low carbon agriculture. | Number of farmers trained on low carbon agriculture | Planned | TOTAL | 0 | 3700 | 7500 | 10500 | 10500 | 10500 | 10500 | There are capable TA providers in the project areas interested in participating in the programme Awareness about low carbon agriculture is spread amongst the community, including students. Farmers associations are unable to assist farmers on LCA Farmers are not aware of LCA benefits Farmers believe they need to deforest to increase production
|  |  | Cerrado | 0 | 3000 | 6000 | 9000 | 9000 | 9000 | 9000
|  |  | Caatinga | 0 | 700 | 1500 | 1500 | 1500 | 1500 | 1500
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB progress reports
| Output Indicator 1.2 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of technical agents trained on low carbon agriculture | Planned | TOTAL | 0 | 775 | 1475 | 1626 | 1626 | 1626 | 1626
|  |  | Cerrado | 0 | 400 | 800 | 876 | 876 | 876 | 876
|  |  | Caatinga | 0 | 375 | 675 | 750 | 750 | 750 | 750
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB progress reports
| Output Indicator 1.3 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Field days and workshops delivered on low carbon agriculture | Planned | TOTAL | 0 | 140 | 430 | 170 | 60 | 0 | 800
|  |  | Cerrado | 0 | 140 | 430 | 170 | 60 | 0 | 800
|  |  | Caatinga | 0 | TBD - Aug 2020 | TBD - Aug 2020 | TBD - Aug 2020 | TBD - Aug 2020 |  | TBD - Aug 2020
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB progress reports
| Output Indicator 1.4 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of students trained on low carbon agriculture | Planned | TOTAL | 0 | 3000 | 3000 | 1500 | 300 | 0 | 7800
|  |  | Cerrado | 0 | 3000 | 3000 | 1500 | 300 | 0 | 7800
Caatinga
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB progress reports
OUTPUT 2 (performance weighting 60%) | Output Indicator 2.1 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project | Assumptions
Increased agricultural productivity and areas with sustainable land use, through LCA implementation, in already deforested and degraded areas | Hectares of land brought under sustainable management | Planned | TOTAL | 0 | 300 | 100600 | 200800 | 300800 | 300800 | 300800 | Farmers respond rapidily to LCA implementation and increase their production in already opened areas Farmers recover degraded lands to increase production and preserve native vegetation, mitigating emissions Farmers are able to acess low carbon agriculture credit lines Farmers acknowledge the economic viability of LCA, even without cash incentives
|  |  | Cerrado | 0 | 0 | 100000 | 200000 | 300000 | 300000 | 300000
|  |  | Caatinga | 0 | 300 | 600 | 800 | 800 | 800 | 800
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB progress reports
| Output Indicator 2.2 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of farmers with improved access to rural credit | Planned | TOTAL | 0 | 400 | #VALUE! | #VALUE! | #VALUE! | 1500 | 1500
|  |  | Cerrado | 0 | 400 | 800 | 1500 | 1500 | 1500 | 1500
|  |  | Caatinga | 0 | 0 | TBD - Oct 2021 | TBD - Oct 2021 | TBD - Oct 2021 |  | TBD - Oct 2021
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB progress reports
| Output Indicator 2.3 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of studies assessing the impact of low carbon technology in the restoration and conservation of the Caatinga | Planned | TOTAL | 0 | 4 | 0 | 0 | 0 |  | 4
Cerrado
|  |  | Caatinga | 0 | 4 | 0 | 0 | 0 |  | 4
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
Progress reports from executing agencies
OUTPUT 3 (performance weighting 10%) | Output Indicator 3.1 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project | Assumptions
Market barriers for farmers reduced, through the development of value chains and increased access to markets | Number of farmer's organisations supported with collected benefits | Planned | TOTAL | 0 | 7 | 15 | 28 | 35 | 35 | 35 | Organizations able to process/ sell increased production from farmers Farmers have more access to the market Farmers associations are interested in the LCA programme Market conditions remain favourable to LCA
|  |  | Cerrado | 0 | 0 | 0 | 13 | 20 | 20 | 20
|  |  | Caatinga | 0 | 7 | 15 | 15 | 15 | 15 | 15
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB progress reports
| Output Indicator 3.2 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of low-carbon based productive chains supported | Planned | TOTAL | 0 | 4 | 13 | 13 | 13 | 13 | 13
|  |  | Cerrado | 0 | 0 | 3 | 3 | 3 | 3 | 3
|  |  | Caatinga | 0 | 4 | 10 | 10 | 10 | 10 | 10
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB progress reports
| Output Indicator 3.3 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of new markets accessed | Planned | TOTAL | 0
|  |  | Cerrado | 0 | TBD - Sep 2020 | TBD - Sep 2020 | TBD - Sep 2020 | TBD - Sep 2020
|  |  | Caatinga | 0 | TBD - Sep 2020 | TBD - Sep 2020 | TBD - Sep 2020 | TBD - Sep 2020
|  | Achieved | TOTAL
Cerrado
Caatinga
Source
IDB progress reports
OUTPUT 4 (performance weighting 5%) | Output Indicator 4.1 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project | Assumptions
Improved partnerships between project stakeholders (eg executing agenciess, government) and strengthened dialogue on LCA | Number of workshops organised by LCA Phase II to promote policy dialogue | Planned |  | 0 | 2 | 2 | 2 | 2 | 0 | 8 | Executors are able to implement project on time and on budget Project delivers impressive results and it is disseminated widely amongst relevant stakeholders Policy conditions remain favourable to LCA
Achieved
Source
IDB progress reports
| Output Indicator 4.2 |  |  | Baseline (2020) | 2020 | 2021 | 2022 | 2023 | 2024 | End of Project
| Number of events organised about LCA Phase II | Planned |  | 0 | 0 | TBD - Dec 2020 | TBD - Dec 2020 | TBD - Dec 2020 | TBD - Dec 2020 | TBD - Dec 2020
|  | Achieved |  |  | 0 | TBD - Dec 2020 | TBD - Dec 2020 | TBD - Dec 2020 | TBD - Dec 2020 | TBD - Dec 2020
Source
IDB progress and final reports and evaluation report
Note on D135: Dell: This would be done through the creation of a Facility Fund. The number of people is still tbc

## Planilha1
tCO2/ano
[5 empty] | 220 | 22500 | 4950000
[6 empty] | 32500 | 7150000
[6 empty] | 32500 | 7150000
[6 empty] | 42300 | 9306000
[6 empty] | 129800 | 28556000
2001 | 2098155 | 468466023 | 223.2752
2002 | 2098155 | 468466023 | 223.2752
2003 | 2151777 | 478153156 | 222.2132
2004 | 2151777 | 478153156 | 222.2132
2005 | 1356658 | 306070255 | 225.6061
2006 | 1356658 | 306070255 | 225.6061
2007 | 1000721 | 222589427 | 222.4291
2008 | 1000721 | 222589427 | 222.4291
2009 | 759913 | 158083682 | 208.0287
2010 | 759913 | 158083682 | 208.0287 | 220.3104

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.