## Log-frame
PROJECT TITLE | Taskforce on Nature-related Financial Disclosures
IMPACT | Impact Indicator 1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  | Assumptions
Increased nature-related risk disclosures across financial markets, facilitating the redirection of global financial flows away from activities that contribute to nature loss and towards nature-positive outcomes - supporting sustainable development and poverty reduction. | KPI 15 - extent to which ICF intervention is likely to have a transformational change. | Planned |  |  | KPI15 score of 5 achieved in 2023 - substantial evidence that suggests transformative change is likely or already occurring among leading corporate and financial institutions globally with regard to nature-related risks and opportunities. |  |  | 5 - substantial evidence that suggests transformative change is likely or already occurring. |  | 2025-01-31 |  |  |  | Achievement of this impact will ultimately require much longer than the 1 year timeframe of our uptake funding and will depend on contributions from a wide range of other international and national-level actors.
Achieved
[5 empty] | Source | [7 empty] | RISK RATING
[5 empty] | TNFD Secretariat | [7 empty] | Medium
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline |  |  | Milestone 1 (2025) |  |  |  |  | Target date |  |  | Assumptions
The growth across geographies and sectors in awareness about - and participation in - the work of the TNFD, through a number of distinct stages of engagement. | Number of webinars organised by the TNFD | Planned | 0 |  |  |  |  | 10 webinars organised |  |  | 2025-01-31 |  | Webinars are an effective way of engaging with key stakeholders and raising awareness about the work of the TNFD.
Achieved
|  | Source | [10 empty] | RISK RATING
|  | TNFD Secretariat | [10 empty] | Medium
| Outcome Indicator 1.1 |  | Baseline |  |  | Milestone 1 (2025) |  |  |  |  | Target date |  |  | Assumptions
| Number of participants in webinars organised by the TNFD | Planned | 0 |  |  |  |  | 3500 participants |  |  | 2025-01-31 |  | High participation in webinars organised is essential for raising awareness about the TNFD across sectors and geographies.
Achieved
|  | Source | [10 empty] | RISK RATING
|  | TNFD Secretariat | [10 empty] | Medium
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline |  |  | Milestone 1 (2025) |  |  |  |  | Target date |  |  | Assumptions
Efforts by leading organisations, including the ISSB, to develop nature standards and draw on the TNFD recommendations. | Production of a correspondence mapping table that outlines the interoperability of the TNFD and leading standard setters. | Planned | 0 |  |  |  |  | Correspondence mapping table outlining the interoperability of the TNFD and leading standard setters produced |  |  | 2025-01-31 |  | An effective way of securing the longevity and sustainability of the TNFD over the long-term would be to ensure that the TNFD recommendations are mainstreamed and onboarded within the emerging global sustainability standards, including the ISSB.
Achieved
|  | Source | [10 empty] | RISK RATING
|  | TNFD Secretariat | [10 empty] | Medium
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline |  |  | Milestone 1 (2025) |  |  |  |  | Target date |  |  | Assumptions
The growth of interest and support from governments and financial regulators in the TNFD recommendations, specifically among G20 finance ministries and central government agencies. | # of countries (inclusive of policy-making entities, central banks, or other regulatory entities) engaged by the TNFD directly or through partner channels during the uptake phase (post-September 2023) | Planned | TNFD engaged with all G7 and G20 countries and 10 non-G20 countries during the 'design and development' phase |  |  |  |  | Engagement with 40 countries (including a majority of the megadiverse countries and G20 countries) |  |  | 2025-01-31 |  | G7 and G20 governments represent the overwhelming majority of jurisdictions through which global capital flows and is therefore regulated. The 17 megadiverse countries are key actors in the global effort to halt and reverse biodiversity loss owing to the high levels of biodiversity in their jurisdictions.
Achieved
|  | Source | [10 empty] | RISK RATING
|  | TNFD Secretariat | [10 empty] | Low
OUTCOME 4 | Outcome Indicator 4.1 |  | Baseline |  |  | Milestone 1 (2025) |  |  |  |  | Target date |  |  | Assumptions
Market demand for nature-related knowledge, skill development, and data solutions. | # of downloads of the 'Getting started with adoption of the TNFD recommendations' guidance document | Planned | 0 |  |  | TBD |  | 29000 |  |  | 2025-01-31 |  | Market demand for nature-related knowledge, skills development, and data solutions demonstrates the TNFD's level of success in raising awareness on the importance of tackling nature risk.
Achieved
|  | Source | [10 empty] | RISK RATING
|  | TNFD Secretariat | [10 empty] | Low
OUTPUT 1 | Output Indicator 1.1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date | Assumptions | Assumptions
Market adoption and Capacity Building | Number of downloads of the TNFD's LEAP framework (which provides guidance on the identification and assessment of nature-related issues) | Planned |  |  | 0 |  |  | 29000 |  | 2023-07-01 |  | 2025-01-31 |  | Downloads of the LEAP framework acts as a proxy for measuring the level of interest in identifying and assessing nature-related issues.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output indicator 1.2 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of organisations who have publicly committed to adopt the TNFD recommendations by FY2024 or FY2025. | Planned |  | 320 adopters announced at Davos 2024 |  |  |  | 520 |  |  |  | 2025-01-31 |  | Public commitments to adopt the TNFD corporate reporting recommendations represents the principal way for an organisation to signal its commitment to take action on tackling its nature-related risks, opportunities, impacts, and dependencies.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output indicator 1.3 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of countries and jurisdictions from which organisations have committed to adopt the TNFD recommendations. | Planned |  | 45 countries or territories announced at Davos 2024 |  |  |  | 55 |  |  |  | 2025-01-31 |  | Number of countries that have at least one TNFD adopter acts as a way of measuring the extent to which the TNFD delivering on the goal of achieving global voluntary uptake of the TNFD recommendations.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output indicator 1.4 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of developing countries from which organisations have committed to adopt the TNFD recommendations | Planned |  | 9 |  |  |  | 27 |  |  |  | 2025-01-31 |  | Developing countries predominantly contain the highest concentrations of biodiversity and a greater proportion of people in developing countries rely on the ecosystem services that nature provides for their incomes and livelihoods.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output indicator 1.5 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of SASB industries represented among the TNFD adopters | Planned |  | 58 |  |  |  | 65 |  |  |  | 2025-01-31 |  | SASB groups companies based on their sustainability-related risks and opportunities. SASB uses sustainability profiles to group similar companies within industries and sectors. Market uptake across sectors is important for ensuring economy-wide efforts to tackle nature risks.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output indicator 1.6 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of TNFD Consultation Groups | Planned |  | 15 |  |  |  | 20 |  |  |  | 2025-01-31 |  | TNFD Consultation Groups are formed on the basis of demonstrated in-country market demand. As such, they act as a strong proxy for market engagement with the TNFD recommendations.
Achieved
IMPACT WEIGHTING (%) |  | Source | [11 empty] | RISK RATING
30 |  | TNFD Secretariat | [11 empty] | Low
OUTPUT 2 | Output Indicator 2.1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  | Assumptions
Stakeholder Engagement and Guidance | # of guidance documents published | Planned |  |  | 0 |  |  | Publication of the following guidance documents: 1) Biome guidance 2) Guidance on the application of TNFD recommendations for small and medium-sized enterprises (SMEs) 3) Sector Guidance |  | 2025-01-31 |  |  | Guidance documents play a pivotal role in ensuring comprehensive market uptake and thorough application of the LEAP framework and TNFD recommendations.
Achieved
|  | Source | [10 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output indicator 2.2 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of dialogues with IPLCs | Planned |  | 0 |  |  |  | 10 |  |  |  | 2025-01-31 |  | IPLCs play a crucial role as the custodians of high biodiversity areas, and it is therefore important for the TNFD and private sector organisations to engage with IPLCs as part of the market adoption process.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output indicator 2.3 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of engagements with the Taskforce on Inequality & Social-related Financial Disclosures (TISFD) | Planned |  | 0 |  |  |  | 4 |  |  |  | 2025-01-31 |  | The nexus between nature loss and poverty and other social-related challenges is well-established. Collaboration is required to ensure alignment between the TNFD and TISFD.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output indicator 2.4 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of briefings delivered to non-governmental stakeholders (i.e. MDBs, PDBs, DFIs, industry associations, sustainable finance and investor associations, financial market regulators). | Planned |  | 0 |  |  |  | 9 |  |  |  | 2025-01-31 |  | Briefings are instrumental for raising awareness on the TNFD and nature risk to key stakeholders, and encouraging TNFD uptake.
Achieved
IMPACT WEIGHTING (%) |  | Source | [11 empty] | RISK RATING
20 |  | TNFD Secretariat | [11 empty] | Low
OUTPUT 3 | Output Indicator 3.1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date |  | Assumptions
Global Nature-related Public Data Finance Facility | Blueprint developed for a preferred governance, funding, and operating model for the Global Nature-related Public Data Facility | Planned |  | 0 |  |  | Blueprint published |  | A broad cross section with representation from every sector and continent |  |  | 2025-01-01 |  | Access to comparable, high-quality underlying nature-related data is essential for enabling accountability and accelerating action. The Data Facility will act as an open data repository to allow stakeholders to access key nature-related data and commitments and to assess the progress of businesses and financial institutions towards these commitments.
Achieved
IMPACT WEIGHTING (%) |  | Source | [11 empty] | RISK RATING
10 |  | TNFD Secretariat | [11 empty] | Low
OUTPUT 4 | Output Indicator 4.1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date |  | Assumptions
UK TNFD National Consultation Group (NCG) | Number of events (webinars, teach-ins, roundtables, sector discussions) that the UK TNFD NCG has hosted or spoken at | Planned | 0 |  | 0 |  |  | 40 |  | 2023-07-01 |  | 2025-01-01 |  | Participation in UK NCG-led events plays an invaluable role in supporting engagement with and uptake of the TNFD recommendations. Speaking at events also helps to publicise and advocate for the work of the UK NCG and the TNFD more broadly.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | Green Finance Institute | [11 empty] | Low
| Output indicator 4.2 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of UK institutions engaged in bilateral or sector peer group discussions | Planned |  | 0 |  |  | 100 |  | A broad cross section with representation from every sector and continent |  |  | 2025-01-01 |  | Bilateral engagements and sector peer group discussions play an invaluable role in enabling organisations to engage with the TNFD recommendations and implementation guidance. They also help to support uptake and heighten ambition.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | Green Finance Institute | [11 empty] | Low
| Output indicator 4.3 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target date |  |  |  | Assumptions
| Number of UK institutions who have committed to report in line with the TNFD recommendations by FY2024 or FY2025 | Planned |  | 0 |  |  |  | 65 |  |  |  | 2025-01-01 |  | Commitments to report in line with the TNFD recommendations by UK plc demonstrates the success of the UK TNFD NCG in driving voluntary market uptake.
Achieved
IMPACT WEIGHTING (%) |  | Source | [11 empty] | RISK RATING
10 |  | Green Finance Institute | [11 empty] | Low
OUTPUT 5 | Output Indicator 5.1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date |  | Assumptions
Nature Transition Plan | Publication of 'Draft Guidance on Nature Transition Plans' for consultation with the market and wider stakeholders | Planned |  |  | - |  |  | Draft Guidance on Nature Transition Plans published, serving as a workable prototype, and released for consultation to the market and wider stakeholders. |  | 2023-07-01 |  | 2025-01-01 |  | Guidance and consultation pertaining to the integration of nature into transition planning frameworks is crucial for ensuring that nature is embedded into organisations' decision-making and strategic planning for the short, medium, and long-term.
Achieved
IMPACT WEIGHTING (%) |  | Source | [11 empty] | RISK RATING
10 |  | TNFD Secretariat | [11 empty] | Low
OUTPUT 6 | Output Indicator 6.1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date |  | Assumptions
Education and Executive Training | # of downloads of 'TNFD in a Box' modules | Planned | 0 |  | 0 |  |  | 5000 |  | 2023-07-01 |  | 2025-01-01 |  | Market demand for 'TNFD in a Box's' nature-related knowledge materials demonstrates the TNFD's level of success in raising awareness on the importance of tackling nature risk.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output Indicator 6.1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date |  | Assumptions
| Number of participants in the 'TNFD in a Box' webinar on director duties | Planned | 0 |  | 0 |  |  | 300 |  | 2023-07-01 |  | 2025-01-01 |  | Board directors exercise a major influence over their company's priorities and direction, and it is therefore important for directors to be cognisant of the materiality of nature-related risks.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | TNFD Secretariat | [11 empty] | Low
| Output Indicator 6.2 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date |  | Assumptions
| Number of IPLC Business Engagement training sessions delivered | Planned |  |  | 0 |  |  | 3 |  | 2023-07-01 |  | 2025-01-01 |  | Training sessions will enhance the capabilities of business executives to engage constructively and productively with IPLCs.
Achieved
|  | Source | [11 empty] | RISK RATING
|  | Green Finance Institute | [11 empty] | Low
| Output Indicator 6.3 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date |  | Assumptions
| Publication of the TNFD's 'White Label' capacity building material | Planned |  |  | 0 |  |  | TNFD 'White Label' capacity building material published |  | 2023-07-01 |  | 2025-01-01 |  | The adaptation of the TNFD's existing publications into white-label training materials for market participants will help to scale market capacity.
Achieved
IMPACT WEIGHTING (%) |  | Source | [11 empty] | RISK RATING
10 |  | Green Finance Institute | [11 empty] | Low
OUTPUT 7 | Output Indicator 7.1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date |  | Assumptions
Developing a Nature Risks Evidence Base | Publication of additional case studies for the 'When the Bee Stings' report, in collaboration with Bloomberg | Planned |  |  | 0 |  |  | Additional case studies for 'When the Bee Stings' report published |  | 2023-07-01 |  | 2025-01-01 |  | Developing publicly sharable evidence on the materiality of nature-related risks, impacts, and dependencies is important for underscoring the need for action to tackle nature loss and degradation.
Achieved
IMPACT WEIGHTING (%) |  | Source | [11 empty] | RISK RATING
5 |  | TNFD Secretariat | [11 empty] | Low
OUTPUT 8 | Output Indicator 8.1 |  |  |  | Baseline |  |  | Milestone 1 (2025) |  | Target (date) |  | Target date |  | Assumptions
Evidencing nature's role in systemic risks/financial stability | Number of articles published, following TNFD interviews or engagement, that evidence systemic nature risk | Planned |  |  | 0 |  |  | 5 |  | 2023-07-01 |  | 2025-01-01 |  | Publications in the media are instrumental for raising awareness on systemic nature risk to core and wider audiences.
Achieved
IMPACT WEIGHTING (%) |  | Source | [11 empty] | RISK RATING
5 |  | TNFD Secretariat | [11 empty] | Low