## Logframe
Landscape NAME | FMH Madagascar
Lead Delivery Partner's NAME | Kew Gardens
Version: | 6.2 (January 2023)
Notes: | All targets are cumulative. Targets and results read automatically from "Aggregation" tab, except purple highlighted cells which need direct results input on this tab.
IMPACT | Impact Indicator 1.1 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027) | Assumptions and Risks
To reduce poverty and create sustainable economic development for communities living in, and dependent upon, environmentally-critical landscapes through delivering lasting landscape protection, sustainable management and restoration, safeguarding biodiversity, maintaining and improving ecosystem quality | Likelihood that the intervention will achieve transformational change (ICF KPI 15) | Planned | [5 empty] | -
Source
Independent Evaluation
INPUTS (£) | £ |  | Govt (£) | Other (£) |  | Total (£) | Defra %
| (total budget) |  |  | (10% match funding) |  |  | 90%
INPUTS (HR) | (FTEs)
OUTCOME 1 | Outcome Indicator 1.1 | No FMH interventions in this area. | [5 empty] | Assumptions and Risks
People: Economic opportunities that incentivise biodiversity positive outcomes whilst supporting local development, climate resilience and poverty reduction are developed. | Number of adults with secure tenure rights to land, with (a) legally recognised documentation; and (b) who perceive their rights as land secure. | [6 empty] | From outcome-level TOC: Improved participation improves NRM effectiveness Conserved ecosystems are viable habitats for species of concern Conserved ecosystems store more carbon than alternative land uses Sustainable land management reduces pressure on target ecosystems and species Improved natural resource-based household welfare leads to improved conservation attitudes and behaviours Improved household welfare reduces reliance on, an extraction of, natural resources Improved household welfare reduces reliance on, an extraction of, natural resources Sustainable land management (e.g., climate smart agriculture, agroforestry) strengthens household resilience to environmental change Natural resources are managed in a way that supports the livelihoods of poor / marginalised community members Increased resilience to environmental shocks improves household welfare Improved household welfare strengthens resilience (absorptive capacity) Improved conservation outcomes strengthen natural resource-based household livelihoods Evidence-based policy and sustainable financing models bolster the scale and sustainability of all outcomes
| Outcome Indicator 1.2 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of communities with improved participation and power in natural resource management. | Planned | 0 | 28 | 35.97 | 40.95 | 46.95
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Annual (household survey at baseline/endline, routine intervention monitoring in 2024, 2025, 2026)
| Outcome Indicator 1.3 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of households with improved welfare | Planned | MPI = 0.403 | 952.0766 | 2007.5259 | 2786.1157 | 3240.1299
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Annual (household survey at baseline/endline, routine intervention monitoring in 2024, 2025, 2026)
| Outcome Indicator 1.4 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of households with increasingly resilient and sustainable livelihoods | Planned | 0 | 952.0766 | 2007.5259 | 2786.1157 | 3240.1299
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Annual (household survey at baseline/endline, routine intervention monitoring in 2024, 2025, 2026)
| Outcome Indicator 1.5 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Progress by policy-makers in reforming, implementing, enforcing and protecting laws and policies that require improved, inclusive and equitable governance of protected areas and their connecting landscapes, and sustainable natural resource management (policy progress measured in rubrics). | Planned | 3/5 | 3/5 | 4/5 | 4/5 | 5/5
Achieved
Source
Annual (key informant interview / document review and policy rubrics)
| Outcome Indicator 1.6 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Volume of finance (public or private) leveraged by the BLF portfolio / landscape for improved biodiversity and ecosystem management and/or sustainable and resilient local development to which the intervention has contributed. | Planned |  | 10% match funding | 10% match funding | 10% match funding | 10% match funding
Achieved
Source
Project management data
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
Nature: Biodiversity loss is slowed, halted or reversed. | Population abundance or occupancy of key (indicator) species (number of individuals or probability of species occurrence). | Planned | See "Species" tab. | Not assessed | Improvement vs. baseline | Not assessed | Improvement vs. baseline
|  | Achieved |  |  | See "Species" tab. |  | See "Species" tab.
Source
Biennial field monitoring by project teams (baseline/midline/endline)
| Outcome Indicator 2.2 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| ICF KPI 8 Ecosystem Loss Avoided (hectares). | Planned | 9,609 ha/year forest loss in ZOI | Improvement vs. baseline | Improvement vs. baseline | Improvement vs. baseline | Improvement vs. baseline
|  | Achieved |  | - | - | - | -
Source
Annual remote sensing + ground truthing (baseline/midline/endline); Global Forest Watch (other milestones)
| Outcome Indicator 2.3 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| ICF KPI 17 Area under Sustainable Management Practices as a result of International Climate Finance (hectares). | Planned |  | 730.672 | 1458.76 | 2092.38 | 2732.06
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Ongoing intervention monitoring
| Outcome Indicator 2.4 - OPTIONAL | No FMH interventions in this area.
Change in ecosystem structural connectivity (change in connectivity measured in rubrics)
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
Climate: Greenhouse gas emissions are reduced. | ICF KPI 6 Tonnes of greenhouse gas emissions reduced or avoided (tCO2e). | Planned | 4.1 million tCO2e / year | Improvement vs. baseline | Improvement vs. baseline | Improvement vs. baseline | Improvement vs. baseline
Achieved
Source
Carbon assumptions applied to ecosystem loss avoidance (Outcome 2.2)
INPUTS (£) | £ |  | Govt (£) | Other (£) |  | Total (£) | Defra %
| (total budget) |  | 0 | (10% match funding) |  |  | 90%
INPUTS (HR) | (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027) | Assumptions & Risks
Improved sustainable landscape planning (WP1/WP2). | Number of sustainable resource use and development plans co-developed with communities. (WP1/WP2) | Planned |  | 7 | 7 | 7 | 7 | WP1/2: Plans are sufficient to address risks faced by communities Plans are sufficiently tailored to local conditions and positively perceived by communities Communities have capacity to implement plans
|  | Achieved |  | 7 | 7 | 7 | 7
Source
Management data.
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of new disaster risk reduction plans being implemented effectively. (WP1/WP2) | Planned |  | 8 | 8 | 8 | 8
Achieved
|  |  | Source |  |  |  |  | RISK RATING
|  |  | Management data. |  |  |  |  | Low
INPUTS (£) | £ |  | Govt (£) | Other (£) |  | Total (£) | Defra %
| (WP1/2 budget) |  | 0 | (10% match funding) |  |  | 90%
INPUTS (HR) | (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027) | Assumptions & Risks
Improved local natural resource governance (WP3), sustainable timber and fuelwood supply (WP4), fire management (WP5), and nature connectedness (WP6). | Number of local associations with improved capacity. (WP3.1 - Capacity building) | Planned |  | 28 | 35.97 | 40.95 | 46.95 | WP3: Better community natural resource management has a tangible impact on household wellbeing Local natural resource governance institutions have incentives to sustain improved practices without project support Marginalised community members are successfully empowered to participate in NRM Training leads to desired behaviour change Community Score Cards address binding constraints to dina implementation Community members have incentives to participate in patrols Patrol efforts are evidence-based, well-targeted, and effective in detecting & addressing non- compliant behaviour WP4: Plantation-based exotic species are seen as viable substitutes for natural forest wood products Farmers prefer agroforestry to alternative approaches Communities see value in conserving restored areas Woodlots are seen as preferable to alternative land uses Viable crops can be identified for agroforestry regimes Seedling demand is sustained beyond project support Nursery operators perceive nurseries as a viable enterprise High quality nursery practices lead to successful seedling production Appropriate selection of tree species for different applications Communities prefer efficient cookstoves to traditional cooking methods People successfully apply the training People consider cookstove construction a worthwhile use of time and resources WP5: Fire management personnel have effective authority or other influence over agricultural practices Fire management plan is upheld beyond project support Improved practices are successfully applied Best practice elsewhere is effectively tailored to the local context Carbon projects are viable for landscape fire management WP6: Increased nature connectedness is sufficient to drive changes in attitudes and behaviours
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Annual activity monitoring (training) & WP3 evaluation (adoption).
| Output Indicator 2.2 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of local associations with increased female membership. (WP3.1 - Capacity building) | Planned |  | 8.5 | 18.69 | 23.25 | 30.39
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Annual activity monitoring (training) & WP3 evaluation (adoption).
| Output Indicator 2.3 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Average distance covered by monthly patrols (km). (WP3.3 - Community patrols) | Planned | 1988 | 3733 | 4174 | 4487 | 4740
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Monthly activity monitoring (patrol data).
| Output Indicator 2.4 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Area of land planted for timber and fuelwood (hectares). (WP4.1 - Timber & fuelwood) | Planned |  | 112.8 | 204.4 | 326 | 458
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Ongoing activity monitoring.
| Output Indicator 2.5 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Area of land planted as agroforestry (hectares). (WP4.2 - Agroforestry) | Planned |  | 70.2 | 170 | 230.5 | 286.5
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Ongoing activity monitoring.
| Output Indicator 2.6 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Area of land under active restoration (hectares). (WP4.3 - Forest restoration) | Planned |  | 223 | 429 | 645 | 961
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Ongoing activity monitoring.
| Output Indicator 2.7 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of households using fuel-efficient cookstoves. (WP4.4 - Cookstoves) | Planned |  | 32.75 | 85 | 148.7 | 226
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Ongoing activity monitoring & WP4 evaluation.
| Output Indicator 2.8 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of new PA fire management plans being implemented. (WP5 - Fire) | Planned |  | 0 | 5 | 5 | 5
Achieved
Source
Ongoing activity monitoring & WP5 evaluation.
| Output Indicator 2.9 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of knowledge products developed to support the evidence base for fire, biodiversity, and land management. (WP5 - Fire) | Planned |  | 1 | 3 | 5 | 7
Achieved
Source
Ongoing activity monitoring & WP6 evaluation.
| Output Indicator 2.10 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of fire community engagement reports produced. (WP5 - Fire) | Planned |  | 0 | 1 | 2 | 6
Achieved
Source
Ongoing activity monitoring & WP6 evaluation.
IMPACT WEIGHTING (%) | Output Indicator 2.11 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of communities demonstrating improved attitudes to conservation. (WP6 - Nature connectedness) | Planned |  | 2.2 | 11.05 | 22.59 | 38.65
|  | Achieved |  | 0 | 0 | 0 | 0
|  |  | Source |  |  |  |  | RISK RATING
|  |  | Ongoing activity monitoring & WP6 evaluation. |  |  |  |  | Low
INPUTS (£) | £ |  | Govt (£) | Other (£) |  | Total (£) | Defra %
| (WP3/4/5/6 budget) |  | 0 | (10% match funding) |  |  | 90%
INPUTS (HR) | (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027) | Assumptions & Risks
Increased adoption of climate smart agriculture (WP7), household financial sustainability (WP8), and reproductive healthcare access (WP9). | Number of farm households practicing climate-smart agriculture. (WP7.1 - Climate smart agriculture) | Planned |  | 507.3 | 1024 | 1392 | 1604 | WP7: Increased agricultural productivity does not incentivise expansion of agriculture into areas of conservation interest CSA approaches are preferred to conventional methods Knowledge & inputs are the main barriers to CSA adoption Cost of upholding project-supported improvements are justified by the benefits Sufficient demand exists for supported products Farmers adopt recommended practices in post-harvest storage, processing, and marketing Provided equipment is appropriately used and well-maintained Priority value chain constraints are identified in analyses Farm produce is of sufficient quality to enter target markets WP8: VSLAs have high repayment rates VSLAs are well-governed High female membership of VSLAs Revenues from new livelihood strategies justify the costs Viable markets exist for promoted products or services Lack of skills and equipment are the main binding constraints to developing new income sources Viable alternative livelihoods opportunities are identified based on robust market evidence New income sources replace – rather than complement – natural resource dependent livelihood strategies WP9: Households would extract fewer natural resources if they were better able to provide for their families (vs. continuing to extract to generate wealth) Families are currently having more children than desired due to a lack of access to and/or understanding of contraception CHAs have incentives to provide services Community members have demand for, & see benefits of, reproductive health services
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Ongoing activity monitoring & WP7 evaluation.
| Output Indicator 3.2 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of farm households benefiting from improved integration in formal value chains. (WP7.2 - Value chain development) | Planned |  | 15.55 | 44.85 | 131.1 | 309.6
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Ongoing activity monitoring & WP7 evaluation.
| Output Indicator 3.3 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of people participating in VSLAs (gender disaggregated). (WP8.1 - VSLAs) | Planned |  | 814 | 1694 | 2299 | 2512
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Ongoing activity monitoring & WP8 evaluation.
| Output Indicator 3.4 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of households with new income sources from alternative livelihoods. (WP8.2 - Alternative livelihoods) | Planned |  | 0 | 56 | 90 | 124
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Ongoing activity monitoring & WP8 evaluation.
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Couple Years of Protection (CYP) delivered through support to contraception provision. (WP9 - Reproductive health) | Planned |  | 312 | 417 | 602 | 632
|  | Achieved |  | 0 | 0 | 0 | 0
|  |  | Source |  |  |  |  | RISK RATING
|  |  | Ongoing activity monitoring & WP9 evaluation. |  |  |  |  | Low
INPUTS (£) | £ |  | Govt (£) | Other (£) |  | Total (£) | Defra %
| (WP7/8/9 budget) |  | 0 | (10% match funding) |  |  | 90%
INPUTS (HR) | (FTEs)
Output 4 | Output Indicator 4.1 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027) | Assumptions & Risks
Strengthened conservation evidence base (WP11) and improved evidence-based policymaking (WP12). | Number of external knowledge products produced by the project. (WP11 - Sharing lessons) | Planned |  | 15 | 66 | 117 | 159 | WP12: Government has resources to apply the model FMH achieves its goals & communicates them to government stakeholders Government is seeking input on evidence- based PA management
|  | Achieved |  | 0 | 0 | 0 | 0
Source
Management data.
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline (2023) | Milestone 1 (March 2024) | Midline (March 2025) | Milestone 3 (March 2026) | Endline (March 2027)
| Number of project meetings with government representatives in attendance. (WP12 - Policy) | Planned |  | 4 | 8 | 12 | 16
Achieved
|  |  | Source |  |  |  |  | RISK RATING
|  |  | Management data. |  |  |  |  | Low
INPUTS (£) | £ |  | Govt (£) | Other (£) |  | Total (£) | Defra %
| (WP11/12 budget) |  | 0 | (10% match funding) |  |  | 90%
INPUTS (HR) | (FTEs)

## Aggregation
Results aggregation
This tab aggregates partner outputs from the output tabs, calculates outcomes, and feeds both outputs and outcomes into the the logframe. The tab is automated & locked.
|  |  | Target |  |  |  | Achieved
|  | Baseline (2023) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Outcomes
Outcome 1.1 | Number of adults with secure tenure rights to land, with (a) legally recognised documentation; and (b) who perceive their rights as land secure. | n/a
Outcome 1.2 | Number of communities with improved participation and power in natural resource management. |  | 28 | 35.97 | 40.95 | 46.95 | 0 | 0 | 0 | 0
Assumed to be equal to the number of communities benefiting from capacity building support under Output 1.1 and 1.2.
Outcome 1.3 | Number of households with improved welfare. |  | 952.0766 | 2007.5259 | 2786.1157 | 3240.1299 | 0 | 0 | 0 | 0
Sum of households benefiting from climate smart agriculture (Output 3.1), value chain development (Output 3.2), VSLAs (Output 3.3), or alternative livelihoods (Output 3.4):
Aggregate of all outputs (inc. duplicates): |  |  | 1336.85 | 2818.85 | 3912.1 | 4549.6
Timescaling: |  |  | 29.38% | 61.96% | 85.99% | 100%
Double counting between these interventions is removed using assumptions on the 'Double counting' tab.
Outcome 1.4 | Number of households with increasingly resilient and sustainable livelihoods. |  | 952.0766 | 2007.5259 | 2786.1157 | 3240.1299 | 0 | 0 | 0 | 0
The beneficaries in Outcome 1.4 are the same as those in Outcome 1.3.
Outcome 1.5 | Progress by policy-makers in reforming, implementing, enforcing and protecting laws and policies that require improved, inclusive and equitable governance of protected areas and their connecting landscapes, and sustainable natural resource management. | (Entered directly into logframe)
Outcome 1.6 | Volume of finance (public or private) leveraged by the BLF portfolio / landscape for improved biodiversity and ecosystem management and/or sustainable and resilient local development to which the intervention has contributed. | (Entered directly into logframe)
Outcome 2.1 | Population abundance or occupancy of key (indicator) species (number of individuals or probability of species occurrence). | See "Species" tab
Outcome 2.2 | ICF KPI 8 Ecosystem Loss Avoided (hectares). |  | Improvement vs. baseline | Improvement vs. baseline | Improvement vs. baseline | Improvement vs. baseline | - | - | - | -
Outcome 2.3 | ICF KPI 17 Area under Sustainable Management Practices as a result of International Climate Finance (hectares). |  | 730.672 | 1458.76 | 2092.38 | 2732.06 | 0 | 0 | 0 | 0
Sum of areas planted as woodlots (Output 2.4), agroforestry (Output 2.5), forest restoration (Output 2.6), and climate smart agriculture (Output 3.1).
Area under climate smart agriculture is estimated by multiplying the number of adopting farmers (Output 3.1) by the average farm size (from the baseline survey):
Average farm size: |  |  | 0.64 | hectares
Farmers practicing CSA: |  |  | 507.3 | 1024 | 1392 | 1604 | 0 | 0 | 0 | 0
CSA area (hectares): |  |  | 324.672 | 655.36 | 890.88 | 1026.56 | 0 | 0 | 0 | 0
Outcome 2.4 | Change in ecosystem structural connectivity. | n/a
Outcome 3.1 | ICF KPI 6 Tonnes of greenhouse gas emissions reduced or avoided (tCO2e). | (Calculated in separate EX-ACT workbooks & entered direcrtly into Logframe)
Outputs
Outputs are aggregated from each partner monitoring tab into the below table, which in turn is used to calculate outcomes (above), and to populate the logframe tab.
|  |  | Target |  |  |  | Achieved
|  | Baseline (2023) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Output 1.1 | Number of sustainable resource use and development plans co-developed with communities. (WP1/WP2) | (Entered directly into logframe)
Output 1.2 | Number of new disaster risk reduction plans being implemented effectively. (WP1/WP2) | (Entered directly into logframe)
Output 2.1 | Number of local associations with improved capacity. (WP3.1 - Capacity building) |  | 28 | 35.97 | 40.95 | 46.95 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 72 | 76 | 77 | 77 | 0 | 0 | 0 | 0
2.1.2 | Adoption rate |  | 38.89% | 47.33% | 53.18% | 60.97% | na | na | na | na
Output 2.2 | Number of local associations with increased female membership. (WP3.1 - Capacity building) |  | 8.5 | 18.69 | 23.25 | 30.39 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 72 | 76 | 77 | 77 | 0 | 0 | 0 | 0
2.1.2 | % with increased membership |  | 11.81% | 24.59% | 30.19% | 39.47% | na | na | na | na
Output 2.3 | Average distance covered by monthly patrols (km). (WP3.3 - Community patrols) |  | 3733 | 4174 | 4487 | 4740 | 0 | 0 | 0 | 0
Output 2.4 | Area of land planted for timber and fuelwood (hectares). (WP4.1 - Timber & fuelwood) |  | 112.8 | 204.4 | 326 | 458 | 0 | 0 | 0 | 0
Output 2.5 | Area of land planted as agroforestry (hectares). (WP4.2 - Agroforestry) |  | 70.2 | 170 | 230.5 | 286.5 | 0 | 0 | 0 | 0
Output 2.6 | Area of land under active restoration (hectares). (WP4.3 - Forest restoration) |  | 223 | 429 | 645 | 961 | 0 | 0 | 0 | 0
Output 2.7 | Number of households using fuel-efficient cookstoves. (WP4.4 - Cookstoves) |  | 32.75 | 85 | 148.7 | 226 | 0 | 0 | 0 | 0
2.7.1 | Number of cookstoves distributed |  | 95 | 220 | 310 | 400 | 0 | 0 | 0 | 0
2.1.2 | % adoption |  | 34.47% | 38.64% | 47.97% | 56.5% | na | na | na | na
Output 2.8 | Number of new PA fire management plans being implemented. (WP5 - Fire) | (Entered directly into logframe)
Output 2.9 | Number of knowledge products developed to support the evidence base for fire, biodiversity, and land management. (WP5 - Fire) |  | 1 | 3 | 5 | 7
2023/24 | Comprehensive vegetation map
2024/25 | Fire management website
Predicted land use change map
2025/26 | Interpolated soil map
Interpolated plant diversity map
2026/27 | Report on fire-vegetation-carbon trade-offs
Policy brief on carbon-biodiversity market engagement
Output 2.10 | Number of fire community engagement reports produced. (WP5 - Fire) |  | 0 | 1 | 2 | 6
2023/24 | -
2024/25 | Community engagement report on Itremo PA
2025/26 | Report on fuzzy cognitive mapping on stakeholder perceptions of fire drivers
2026/27 | Community engagement reports from 4 other Pas
Output 2.11 | Number of communities demonstrating improved attitudes to conservation. (WP6 - Nature connectedness) |  | 2.2 | 11.05 | 22.59 | 38.65 | 0 | 0 | 0 | 0
2.9.1 | Number of communities with WP6 activities taking place |  | 49 | 60 | 75 | 92 | 0 | 0 | 0 | 0
2.9.2 | % adoption |  | 4.49% | 18.42% | 30.12% | 42.01% | na | na | na | na
Output 3.1 | Number of farm households practicing climate-smart agriculture. (WP7.1 - Climate smart agriculture) |  | 507.3 | 1024 | 1392 | 1604 | 0 | 0 | 0 | 0
3.1.1 | Number of farmers trained |  | 1042 | 1920 | 2360 | 2510 | 0 | 0 | 0 | 0
3.1.2 | % adoption |  | 48.69% | 53.33% | 58.98% | 63.9% | na | na | na | na
Output 3.2 | Number of farm households benefiting from improved integration in formal value chains. (WP7.2 - Value chain development) |  | 15.55 | 44.85 | 131.1 | 309.6 | 0 | 0 | 0 | 0
3.2.1 | Number of households receiving VCD support |  | 61 | 117 | 307 | 557 | 0 | 0 | 0 | 0
3.2.2 | % adoption |  | 25.49% | 38.33% | 42.7% | 55.58% | na | na | na | na
Output 3.3 | Number of people participating in VSLAs (gender disaggregated). (WP8.1 - VSLAs) |  | 814 | 1694 | 2299 | 2512 | 0 | 0 | 0 | 0
3.3.1 | Number of VSLAs established |  | 45 | 94 | 129 | 141 | 0 | 0 | 0 | 0
3.3.2 | Average group size |  | 18.0889 | 18.0213 | 17.8217 | 17.8156 | na | na | na | na
3.3.3 | % female membership |  | 42.6% | 42.76% | 47.06% | 49.74% | 0 | 0 | 0 | 0
Output 3.4 | Number of households new income sources from alternative livelihoods. (WP8.2 - Alternative livelihoods) |  | 0 | 56 | 90 | 124 | 0 | 0 | 0 | 0
3.4.1 | Number of households receiving alternative livelihood support |  | 0 | 265 | 290 | 310 | 0 | 0 | 0 | 0
3.4.2 | % adoption |  | na | 21.13% | 31.03% | 40% | na | na | na | na
Output 3.5 | Couple Years of Protection (CYP) delivered through support to contraception provision. (WP9 - Reproductive health) |  | 312 | 417 | 602 | 632 | 0 | 0 | 0 | 0
3.5.1 | Number of communities receiving WP9 support |  | 78 | 85 | 91 | 93 | 0 | 0 | 0 | 0
3.5.2 | Number of service users per village |  | 32 | 32 | 37 | 37 | 0 | 0 | 0 | 0
3.5.3 | CYP per service user (assumption from MEL Framework) |  | 6.1 | 6.1 | 6.1 | 6.1 | na | na | na | na
Output 4.1 | Number of external knowledge products produced by the project. (WP11 - Sharing lessons) |  | 15 | 66 | 117 | 159 | 0 | 0 | 0 | 0
Output 4.2 | Number of project meetings with government representatives in attendance. (WP12 - Policy) | (Entered directly into logframe)

## Species
Outcome 2.1: Species monitoring
|  | Species |  | Baseline (2023) |  | Achieved
Partner | Site | Common name | Latin name | Value | Notes | 2025 | 2027 | Contact
DU-APCLFA | Ambondrobe | [Lemus, species tbc] | tbc | tbc | [baseline count in 2023/24 Q4] |  |  | Haja Andrianavalona (Durrell)
DU-AMPA | Menabe-Antimena | Malagasy Giant Jumping Rat | Hypogeomys antimena | 5016 | 2019 (95% CI = 2,746 – 9,404) |  |  | Haja Andrianavalona (Durrell)
|  | Flat-tailed Tortoise | Pyxis planicauda | 13011 | 2022 (95% CI = 6,907 – 24,510) |  |  | Haja Andrianavalona (Durrell)
Kew | Massif d'Itremo | - | Podocarpus capuronii | tbc | [baseline count in 2023/24 Q4] |  |  | Tiana Randriamboavonjy (Kew)
|  | - | Dypsis ambositrae | 40 | Palm species endemic to the high plateau, threatened. Site: Fragmented humid forests Ca. 40 individuals available in the forests. |  |  | Tiana Randriamboavonjy (Kew)
MBG | Makirovana-Tsihomanaomby | Sanford’s brown lemur | Eulemur sanfordi | 8 to 12 | Group of 4 to 6 individuals (2 group at Tsihomanaomby forest bloc) |  |  | Jeremie Razafitsalama (MBG)
|  | Crowned lemur | Eulemur coronatus | 9 to 12 | Group of 3 to 4 individual - 1 group at Antsolatra forest bloc - 1 group at Farahagnitry forest bloc - 1 group at Makirovana forest bloc |  |  | Jeremie Razafitsalama (MBG)
|  | Eastern lesser bamboo lemur | Hapalemur griseus | 6 to 12 | Group of 1 to 2 individual - 2 group at Antsolatra forest bloc - 2 group at Farahagnitry forest bloc - 2 group at Makirovana forest bloc |  |  | Jeremie Razafitsalama (MBG)
|  | Woolly Indri | Avahi laniger | 3 to 6 | Group of 1 to 2 individual - 1 group at Antsolatra forest bloc - 1 group at Farahagnitry forest bloc - 1 group at Makirovana forest bloc |  |  | Jeremie Razafitsalama (MBG)
MV | Analalava & Analabe-Betanantanana | Madagascan flying fox | Pteropus rufus | 100 |  |  |  | Ellarissa (Larissa) Andrianjafy (MV)
|  | Common brown lemur | Eulemur fulvus | 5 |  |  |  | Ellarissa (Larissa) Andrianjafy (MV)
TPF | Bemanevika-Mahimborondro | Madagascar marsh harrier | Circus macrosceles | 5 |  |  |  | Donatien Randrianjafiniasa (TPF)
|  | Magadagascar red owl | Tyto soumagnei | 0.22 individuals per km2 |  |  |  | Donatien Randrianjafiniasa (TPF)

## Ecosystems
Outcome 2.2: Ecosystem conservation
Each of the following are defined within the project's "zone of influence", a 10km buffer around project villages, covering areas both inside and outside of PAs.
Note that areas and effects "inside/outside" of PAs are defined according to the baseline 2023 PA boundaries.
Land area
Total hectares within the zone of influence at each site as of 2023.
Site | Inside PA | Outside PA | Total
DU-APCLFA | 7050.1011 | 224167.4958 | 231217.5969
DU-APMA | 133560.0609 | 110910.4326 | 244470.4935
Kew | 23324.1249 | 208253.4185 | 231577.5433
MBG | 3399.234 | 114044.5792 | 117443.8133
MV | 741.5514 | 101307.1276 | 102048.679
TPF | 104382.785 | 159797.8566 | 264180.6417
Total | 272457.8574 | 918480.9102 | 1190938.7676
Forest cover (hectares, 30% canopy cover)
(a) Inside PAs
[20 empty] | BASELINE |  |  |  |  | PROJECT
Site | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
DU-APCLFA | 6991.38 | 6990.66 | 6986.79 | 6982.65 | 6953.31 | 6874.29 | 6832.71 | 6628.95 | 6299.82 | 6222.51 | 6108.93 | 6058.62 | 6048.99 | 5892.66 | 5765.4 | 5682.15 | 5441.31 | 5367.15 | 4999.5 | 4917.96 | 4885.2 | 4806.81
DU-APMA | 78983.37 | 78416.19 | 77894.82 | 77791.05 | 77556.15 | 77083.47 | 76337.1 | 75737.43 | 75303.81 | 74042.01 | 72893.79 | 71151.57 | 68990.85 | 66358.53 | 64225.89 | 62930.79 | 56625.3 | 50412.87 | 46452.24 | 45913.32 | 44399.52 | 42889.68
Kew | 344.07 | 344.07 | 343.89 | 343.17 | 343.17 | 343.08 | 342.99 | 342.36 | 342.18 | 342.18 | 341.73 | 341.73 | 341.64 | 340.56 | 340.11 | 339.66 | 339.48 | 339.48 | 339.48 | 337.77 | 337.32 | 336.96
MBG | 3487.59 | 3469.5 | 3462.39 | 3417.75 | 3396.33 | 3391.92 | 3346.65 | 3319.47 | 3305.52 | 3287.7 | 3270.69 | 3255.84 | 3219.75 | 3183.84 | 3162.06 | 3120.84 | 3040.92 | 2962.44 | 2919.33 | 2842.02 | 2811.06 | 2774.79
MV | 287.19 | 287.19 | 287.19 | 282.6 | 282.51 | 282.51 | 274.14 | 274.05 | 274.05 | 273.51 | 271.08 | 270.54 | 270.45 | 270.45 | 270.27 | 270.27 | 269.55 | 269.55 | 269.55 | 269.55 | 267.75 | 262.35
TPF | 88688.52 | 88570.89 | 88417.26 | 88338.15 | 87966 | 87680.52 | 87548.94 | 87384.15 | 87279.75 | 87213.33 | 87108.03 | 87064.65 | 87010.83 | 86925.96 | 86773.86 | 86670.99 | 86478.3 | 86299.83 | 86176.71 | 86036.94 | 85909.68 | 85772.16
Total | 178782.12 | 178078.5 | 177392.34 | 177155.37 | 176497.47 | 175655.79 | 174682.53 | 173686.41 | 172805.13 | 171381.24 | 169994.25 | 168142.95 | 165882.51 | 162972 | 160537.59 | 159014.7 | 152194.86 | 145651.32 | 141156.81 | 140317.56 | 138610.53 | 136842.75 | 0 | 0 | 0 | 0 | 0
(b) Outside PAs
[20 empty] | BASELINE |  |  |  |  | PROJECT
Site | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
DU-APCLFA | 78475.86 | 78390.54 | 78160.59 | 77971.95 | 77581.71 | 76580.55 | 75760.92 | 74368.53 | 72799.02 | 71824.59 | 71125.65 | 70626.69 | 69970.95 | 68186.25 | 66983.76 | 65471.31 | 62958.96 | 60496.56 | 57885.03 | 56600.01 | 54061.47 | 51731.55
DU-APMA | 32422.23 | 32237.64 | 31914.09 | 31687.11 | 31419.63 | 30834.27 | 30091.05 | 29443.5 | 29029.05 | 28007.46 | 27538.92 | 26957.97 | 26309.7 | 24888.96 | 22935.87 | 22078.98 | 20068.83 | 18787.5 | 17218.8 | 16399.26 | 14080.05 | 13213.89
Kew | 690.21 | 689.67 | 688.59 | 684.81 | 684.18 | 683.19 | 680.22 | 678.06 | 677.16 | 675.27 | 673.2 | 671.31 | 670.95 | 670.5 | 670.41 | 669.51 | 666.36 | 666.36 | 666.36 | 665.55 | 663.75 | 663.21
MBG | 110944.17 | 109777.77 | 109398.6 | 107323.74 | 106606.98 | 106473.69 | 103990.32 | 102665.52 | 101465.01 | 100544.67 | 99583.83 | 99073.08 | 93876.48 | 91678.59 | 90364.14 | 87953.94 | 85634.1 | 83784.96 | 82344.06 | 79947.36 | 78294.78 | 76664.16
MV | 28648.8 | 28627.11 | 28605.96 | 28560.06 | 28541.25 | 28531.08 | 28320.48 | 28314.45 | 28235.34 | 28202.4 | 28153.44 | 28116.09 | 28010.79 | 27873.99 | 27825.57 | 27722.61 | 27483.84 | 27378.45 | 27214.11 | 27124.11 | 26966.07 | 26912.25
TPF | 78309 | 78155.1 | 77944.32 | 77741.91 | 77510.52 | 77155.65 | 76900.14 | 76397.31 | 76121.91 | 75937.59 | 75748.05 | 75548.25 | 75179.43 | 74649.15 | 74214.99 | 73652.31 | 73035.99 | 72783.27 | 72719.37 | 72596.16 | 72444.51 | 72197.91
Total | 329490.27 | 327877.83 | 326712.15 | 323969.58 | 322344.27 | 320258.43 | 315743.13 | 311867.37 | 308327.49 | 305191.98 | 302823.09 | 300993.39 | 294018.3 | 287947.44 | 282994.74 | 277548.66 | 269848.08 | 263897.1 | 258047.73 | 253332.45 | 246510.63 | 241382.97 | 0 | 0 | 0 | 0 | 0
(c) Total
[20 empty] | BASELINE |  |  |  |  | PROJECT
Site | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
DU-APCLFA | 85467.24 | 85381.2 | 85147.38 | 84954.6 | 84535.02 | 83454.84 | 82593.63 | 80997.48 | 79098.84 | 78047.1 | 77234.58 | 76685.31 | 76019.94 | 74078.91 | 72749.16 | 71153.46 | 68400.27 | 65863.71 | 62884.53 | 61517.97 | 58946.67 | 56538.36 | 0 | 0 | 0 | 0 | 0
DU-APMA | 111405.6 | 110653.83 | 109808.91 | 109478.16 | 108975.78 | 107917.74 | 106428.15 | 105180.93 | 104332.86 | 102049.47 | 100432.71 | 98109.54 | 95300.55 | 91247.49 | 87161.76 | 85009.77 | 76694.13 | 69200.37 | 63671.04 | 62312.58 | 58479.57 | 56103.57 | 0 | 0 | 0 | 0 | 0
Kew | 1034.28 | 1033.74 | 1032.48 | 1027.98 | 1027.35 | 1026.27 | 1023.21 | 1020.42 | 1019.34 | 1017.45 | 1014.93 | 1013.04 | 1012.59 | 1011.06 | 1010.52 | 1009.17 | 1005.84 | 1005.84 | 1005.84 | 1003.32 | 1001.07 | 1000.17 | 0 | 0 | 0 | 0 | 0
MBG | 114431.76 | 113247.27 | 112860.99 | 110741.49 | 110003.31 | 109865.61 | 107336.97 | 105984.99 | 104770.53 | 103832.37 | 102854.52 | 102328.92 | 97096.23 | 94862.43 | 93526.2 | 91074.78 | 88675.02 | 86747.4 | 85263.39 | 82789.38 | 81105.84 | 79438.95 | 0 | 0 | 0 | 0 | 0
MV | 28935.99 | 28914.3 | 28893.15 | 28842.66 | 28823.76 | 28813.59 | 28594.62 | 28588.5 | 28509.39 | 28475.91 | 28424.52 | 28386.63 | 28281.24 | 28144.44 | 28095.84 | 27992.88 | 27753.39 | 27648 | 27483.66 | 27393.66 | 27233.82 | 27174.6 | 0 | 0 | 0 | 0 | 0
TPF | 166997.52 | 166725.99 | 166361.58 | 166080.06 | 165476.52 | 164836.17 | 164449.08 | 163781.46 | 163401.66 | 163150.92 | 162856.08 | 162612.9 | 162190.26 | 161575.11 | 160988.85 | 160323.3 | 159514.29 | 159083.1 | 158896.08 | 158633.1 | 158354.19 | 157970.07 | 0 | 0 | 0 | 0 | 0
Total | 508272.39 | 505956.33 | 504104.49 | 501124.95 | 498841.74 | 495914.22 | 490425.66 | 485553.78 | 481132.62 | 476573.22 | 472817.34 | 469136.34 | 459900.81 | 450919.44 | 443532.33 | 436563.36 | 422042.94 | 409548.42 | 399204.54 | 393650.01 | 385121.16 | 378225.72 | 0 | 0 | 0 | 0 | 0
(d) Baseline summary
Baseline
Site | Inside PA | Outside PA | Total
Kew | 4995.324 | 56154.924 | 61150.248
MBG | 46013.526 | 15939.9 | 61953.426
TPF | 338.202 | 665.046 | 1003.248
MV | 2861.928 | 80207.064 | 83068.992
DU-APMA | 267.75 | 27118.998 | 27386.748
DU-APCLFA | 86039.064 | 72548.244 | 158587.308
Total | 140515.794 | 252634.176 | 393149.97
Forest loss (hectares)
(a) Inside PAs
[20 empty] | BASELINE |  |  |  |  | PROJECT
Site | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
DU-APCLFA | 2.43 | 0.72 | 3.87 | 4.32 | 29.88 | 79.11 | 41.67 | 204.12 | 329.22 | 77.31 | 113.58 | 50.76 | 10.44 | 156.87 | 128.34 | 83.25 | 241.11 | 74.16 | 368.64 | 82.35 | 35.55 | 78.57
DU-APMA | 252 | 601.83 | 559.8 | 135.72 | 254.97 | 487.98 | 797.49 | 632.16 | 448.02 | 1283.49 | 1176.03 | 1758.69 | 2200.86 | 2739.42 | 2201.67 | 1332.18 | 6407.37 | 6301.44 | 4146.57 | 614.07 | 1823.04 | 1598.31
Kew | 0.18 | 0 | 0.27 | 2.34 | 1.62 | 0.45 | 0.27 | 1.17 | 0.18 | 0 | 0.63 | 0.18 | 0.54 | 1.98 | 0.45 | 2.25 | 1.17 | 0.09 | 0 | 3.69 | 4.05 | 12.96
MBG | 8.91 | 18.09 | 7.11 | 44.64 | 21.42 | 4.41 | 45.27 | 27.18 | 13.95 | 17.82 | 17.01 | 14.85 | 36.54 | 36.18 | 21.78 | 41.22 | 80.01 | 78.48 | 43.11 | 77.31 | 30.96 | 36.27
MV | 0.27 | 0 | 0 | 4.59 | 0.09 | 0 | 8.37 | 0.09 | 0 | 0.54 | 2.43 | 0.54 | 0.09 | 0 | 0.18 | 0 | 0.72 | 0 | 0 | 0 | 1.8 | 5.4
TPF | 137.07 | 120.69 | 155.61 | 79.83 | 373.95 | 287.01 | 136.53 | 166.5 | 105.57 | 67.23 | 106.47 | 45.54 | 65.7 | 103.5 | 166.68 | 115.02 | 209.61 | 188.01 | 124.83 | 144.99 | 129.06 | 141.21
Total | 400.86 | 741.33 | 726.66 | 271.44 | 681.93 | 858.96 | 1029.6 | 1031.22 | 896.94 | 1446.39 | 1416.15 | 1870.56 | 2314.17 | 3037.95 | 2519.1 | 1573.92 | 6939.99 | 6642.18 | 4683.15 | 922.41 | 2024.46 | 1872.72 | 0 | 0 | 0 | 0 | 0
(b) Outside PAs
[20 empty] | BASELINE |  |  |  |  | PROJECT
Site | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
DU-APCLFA | 69.66 | 104.22 | 297.81 | 232.02 | 430.02 | 1027.35 | 870.48 | 1473.12 | 1622.61 | 995.13 | 741.06 | 527.85 | 846.99 | 1950.57 | 1326.96 | 1879.02 | 2818.35 | 2675.34 | 3323.7 | 1811.61 | 2881.53 | 2671.74
DU-APMA | 189.99 | 227.97 | 365.31 | 333.45 | 296.01 | 617.13 | 830.79 | 692.91 | 436.95 | 1048.14 | 497.07 | 613.98 | 700.38 | 1555.2 | 2130.12 | 997.02 | 2263.14 | 1355.13 | 1799.55 | 969.84 | 2715.84 | 1007.64
Kew | 12.42 | 3.24 | 5.31 | 18.27 | 9.54 | 3.42 | 7.11 | 4.59 | 4.32 | 3.6 | 7.92 | 6.12 | 11.34 | 7.02 | 5.94 | 2.79 | 10.71 | 1.89 | 0 | 2.07 | 4.5 | 1.89
MBG | 412.2 | 1167.48 | 380.07 | 2077.74 | 717.03 | 133.56 | 2484.45 | 1326.51 | 1201.05 | 920.97 | 965.43 | 514.35 | 5268.24 | 2214.63 | 1324.35 | 2433.24 | 2341.17 | 1883.52 | 1450.98 | 2421.27 | 1672.38 | 1644.93
MV | 50.4 | 21.96 | 22.14 | 46.98 | 19.71 | 11.88 | 217.62 | 6.93 | 83.34 | 35.19 | 50.76 | 41.67 | 118.35 | 152.1 | 57.24 | 148.32 | 289.17 | 158.13 | 188.64 | 104.49 | 218.88 | 58.95
TPF | 173.7 | 157.86 | 222.03 | 219.6 | 235.71 | 358.47 | 278.64 | 507.6 | 292.77 | 191.61 | 190.98 | 209.43 | 395.82 | 569.43 | 446.49 | 567.9 | 663.66 | 266.13 | 64.71 | 131.58 | 159.39 | 254.79
Total | 908.37 | 1682.73 | 1292.67 | 2928.06 | 1708.02 | 2151.81 | 4689.09 | 4011.66 | 3641.04 | 3194.64 | 2453.22 | 1913.4 | 7341.12 | 6448.95 | 5291.1 | 6028.29 | 8386.2 | 6340.14 | 6827.58 | 5440.86 | 7652.52 | 5639.94 | 0 | 0 | 0 | 0 | 0
(c) Total
[20 empty] | BASELINE |  |  |  |  | PROJECT
Site | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
DU-APCLFA | 72.09 | 104.94 | 301.68 | 236.34 | 459.9 | 1106.46 | 912.15 | 1677.24 | 1951.83 | 1072.44 | 854.64 | 578.61 | 857.43 | 2107.44 | 1455.3 | 1962.27 | 3059.46 | 2749.5 | 3692.34 | 1893.96 | 2917.08 | 2750.31 | 0 | 0 | 0 | 0 | 0
DU-APMA | 441.99 | 829.8 | 925.11 | 469.17 | 550.98 | 1105.11 | 1628.28 | 1325.07 | 884.97 | 2331.63 | 1673.1 | 2372.67 | 2901.24 | 4294.62 | 4331.79 | 2329.2 | 8670.51 | 7656.57 | 5946.12 | 1583.91 | 4538.88 | 2605.95 | 0 | 0 | 0 | 0 | 0
Kew | 12.6 | 3.24 | 5.58 | 20.61 | 11.16 | 3.87 | 7.38 | 5.76 | 4.5 | 3.6 | 8.55 | 6.3 | 11.88 | 9 | 6.39 | 5.04 | 11.88 | 1.98 | 0 | 5.76 | 8.55 | 14.85 | 0 | 0 | 0 | 0 | 0
MBG | 421.11 | 1185.57 | 387.18 | 2122.38 | 738.45 | 137.97 | 2529.72 | 1353.69 | 1215 | 938.79 | 982.44 | 529.2 | 5304.78 | 2250.81 | 1346.13 | 2474.46 | 2421.18 | 1962 | 1494.09 | 2498.58 | 1703.34 | 1681.2 | 0 | 0 | 0 | 0 | 0
MV | 50.67 | 21.96 | 22.14 | 51.57 | 19.8 | 11.88 | 225.99 | 7.02 | 83.34 | 35.73 | 53.19 | 42.21 | 118.44 | 152.1 | 57.42 | 148.32 | 289.89 | 158.13 | 188.64 | 104.49 | 220.68 | 64.35 | 0 | 0 | 0 | 0 | 0
TPF | 310.77 | 278.55 | 377.64 | 299.43 | 609.66 | 645.48 | 415.17 | 674.1 | 398.34 | 258.84 | 297.45 | 254.97 | 461.52 | 672.93 | 613.17 | 682.92 | 873.27 | 454.14 | 189.54 | 276.57 | 288.45 | 396 | 0 | 0 | 0 | 0 | 0
Total | 1309.23 | 2424.06 | 2019.33 | 3199.5 | 2389.95 | 3010.77 | 5718.69 | 5042.88 | 4537.98 | 4641.03 | 3869.37 | 3783.96 | 9655.29 | 9486.9 | 7810.2 | 7602.21 | 15326.19 | 12982.32 | 11510.73 | 6363.27 | 9676.98 | 7512.66 | 0 | 0 | 0 | 0 | 0
(d) Baseline summary
Baseline
Site | Inside PA | Outside PA | Total
Kew | 127.854 | 2672.784 | 2800.638
MBG | 2896.686 | 1569.6 | 4466.286
TPF | 4.158 | 2.07 | 6.228
MV | 53.226 | 1814.616 | 1867.842
DU-APMA | 1.44 | 145.818 | 147.258
DU-APCLFA | 145.62 | 175.32 | 320.94
Total | 3228.984 | 6380.208 | 9609.192

## Knowledge
Outcome 4.1: External knowledge products
Primary contact: Safidy Andriambao (Kew, s.andriambao@kew.org)
Aggregated cumulative targets
| Target |  |  |  | Achieved
| Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Number of external knowledge products produced by the project. (WP11 - Sharing lessons) | 15 | 66 | 117 | 159 | 0 | 0 | 0 | 0
Annual targets
| Target |  |  |  | Achieved
| Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Social media posts | 4 | 32 | 32 | 22
Newsletters | 1 | 4 | 4 | 4
Blog posts | 0 | 4 | 4 | 4
Project song | 0 | 1 | 0 | 0
Video report | 0 | 0 | 1 | 0
Newspaper articles | 0 | 0 | 0 | 2
Technical reports * | 10 | 10 | 10 | 10
Total | 15 | 51 | 51 | 42 | 0 | 0 | 0 | 0
* Technical reports include WP evaluation reports, learning notes resulting from learning cycles, or other public-facing reports.

## DU-APCLFA
Logframe output reporting
Site: | Amondrobe
Partner: | DU-APCLFA
Partners should enter targets in any cells with red text.
Targets in grey text are automatically calculated.
|  |  | Target |  |  |  | Achieved
|  | Baseline (2023) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Output Indicator 2.1 | Number of local associations with improved capacity. (WP3.1 - Capacity building) |  | 4 | 5 | 6 | 6 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0
2.1.2 | Adoption rate |  | 40% | 50% | 60% | 60% | 0% | 0% | 0% | 0%
Output Indicator 2.2 | Number of local associations with increased female membership. (WP3.1 - Capacity building) |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0
2.1.2 | % with increased membership |  | 0% | 10% | 10% | 10% | 0% | 0% | 0% | 0%
Output Indicator 2.3 | Average distance covered by monthly patrols (km). (WP3.3 - Community patrols) |  | 300 | 300 | 300 | 300 | 0 | 0 | 0 | 0
Output Indicator 2.4 | Area of land planted for timber and fuelwood (hectares). (WP4.1 - Timber & fuelwood) |  | 5 | 10 | 15 | 15 | 0 | 0 | 0 | 0
Output Indicator 2.5 | Area of land planted as agroforestry (hectares). (WP4.2 - Agroforestry) |  | 4 | 8 | 12 | 12 | 0 | 0 | 0 | 0
Output Indicator 2.6 | Area of land under active restoration (hectares). (WP4.3 - Forest restoration) |  | 95 | 145 | 195 | 245 | 0 | 0 | 0 | 0
Output Indicator 2.7 | Number of households using fuel-efficient cookstoves. (WP4.4 - Cookstoves) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7.1 | Number of households trained on cookstoves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2 | % adoption |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Output Indicator 2.8 | Number of new PA fire management plans being implemented. (WP5 - Fire) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 2.9 | Number of communities demonstrating improved attitudes to conservation. (WP6 - Nature connectedness) |  | 0 | 2.4 | 6 | 9 | 0 | 0 | 0 | 0
2.9.1 | Number of communities with WP6 activities taking place |  | 24 | 24 | 30 | 30 | 0 | 0 | 0 | 0
2.9.2 | % adoption |  | 0% | 10% | 20% | 30% | 0% | 0% | 0% | 0%
Output Indicator 3.1 | Number of farm households practicing climate-smart agriculture. (WP7.1 - Climate smart agriculture) |  | 108 | 216 | 288 | 288 | 0 | 0 | 0 | 0
3.1.1 | Number of farmers trained |  | 240 | 360 | 480 | 480 | 0 | 0 | 0 | 0
3.1.2 | % adoption |  | 45% | 60% | 60% | 60% | 0% | 0% | 0% | 0%
Output Indicator 3.2 | Number of farm households benefiting from improved integration in formal value chains. (WP7.2 - Value chain development) |  | 2.4 | 4.8 | 6.4 | 6.4 | 0 | 0 | 0 | 0
3.2.1 | Number of households receiving VCD support |  | 3 | 6 | 8 | 8 | 0 | 0 | 0 | 0
3.2.2 | % adoption |  | 80% | 80% | 80% | 80% | 0% | 0% | 0% | 0%
Output Indicator 3.3 | Number of people participating in VSLAs (gender disaggregated). (WP8.1 - VSLAs) |  | 90 | 198 | 306 | 324 | 0 | 0 | 0 | 0
3.3.1 | Number of VSLAs established |  | 5 | 11 | 17 | 18 | 0 | 0 | 0 | 0
3.3.2 | Average group size |  | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0
3.3.3 | % female membership |  | 60% | 60% | 50% | 50% | 0% | 0% | 0% | 0%
Output Indicator 3.4 | Number of households new income sources from alternative livelihoods. (WP8.2 - Alternative livelihoods) |  | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0
3.4.1 | Number of households receiving alternative livelihood support |  | 0 | 15 | 15 | 15 | 0 | 0 | 0 | 0
3.4.2 | % adoption |  | 0% | 40% | 40% | 40% | 0% | 0% | 0% | 0%
Output Indicator 3.5 | Couple Years of Protection (CYP) delivered through support to contraception provision. (WP9 - Reproductive health) |  | 132 | 132 | 132 | 132 | 0 | 0 | 0 | 0
3.5.1 | Number of communities receiving WP9 support |  | 66 | 66 | 66 | 66 | 0 | 0 | 0 | 0
3.5.2 | Number of service users per village |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
3.5.3 | CYP per service user (assumption from MEL Framework) |  | 6.1 | 6.1 | 6.1 | 6.1 | 0 | 0 | 0 | 0
Output Indicator 4.1 | Number of external knowledge products produced by the project. (WP11 - Sharing lessons) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 4.2 | Number of project meetings with government representatives in attendance. (WP12 - Policy) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)

## DU-APMA
Logframe output reporting
Site: | Menabe-Antimena
Partner: | DU-APMA
Partners should enter targets in any cells with red text.
Targets in grey text are automatically calculated.
|  |  | Target |  |  |  | Achieved
|  | Baseline (2023) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Output Indicator 2.1 | Number of local associations with improved capacity. (WP3.1 - Capacity building) |  | 10.35 | 11.5 | 11.5 | 13.8 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 23 | 23 | 23 | 23 | 0 | 0 | 0 | 0
2.1.2 | Adoption rate |  | 45% | 50% | 50% | 60% | 0% | 0% | 0% | 0%
Output Indicator 2.2 | Number of local associations with increased female membership. (WP3.1 - Capacity building) |  | 0 | 5.29 | 6.9 | 10.35 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 23 | 23 | 23 | 23 | 0 | 0 | 0 | 0
2.1.2 | % with increased membership |  | 0% | 23% | 30% | 45% | 0% | 0% | 0% | 0%
Output Indicator 2.3 | Average distance covered by monthly patrols (km). (WP3.3 - Community patrols) |  | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0
Output Indicator 2.4 | Area of land planted for timber and fuelwood (hectares). (WP4.1 - Timber & fuelwood) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output Indicator 2.5 | Area of land planted as agroforestry (hectares). (WP4.2 - Agroforestry) |  | 4 | 8 | 12 | 16 | 0 | 0 | 0 | 0
Output Indicator 2.6 | Area of land under active restoration (hectares). (WP4.3 - Forest restoration) |  | 64 | 104 | 144 | 184 | 0 | 0 | 0 | 0
Output Indicator 2.7 | Number of households using fuel-efficient cookstoves. (WP4.4 - Cookstoves) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7.1 | Number of households trained on cookstoves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2 | % adoption |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Output Indicator 2.8 | Number of new PA fire management plans being implemented. (WP5 - Fire) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 2.9 | Number of communities demonstrating improved attitudes to conservation. (WP6 - Nature connectedness) |  | 0 | 1.9 | 3.8 | 5.7 | 0 | 0 | 0 | 0
2.9.1 | Number of communities with WP6 activities taking place |  | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0
2.9.2 | % adoption |  | 0% | 10% | 20% | 30% | 0% | 0% | 0% | 0%
Output Indicator 3.1 | Number of farm households practicing climate-smart agriculture. (WP7.1 - Climate smart agriculture) |  | 120 | 216 | 288 | 288 | 0 | 0 | 0 | 0
3.1.1 | Number of farmers trained |  | 240 | 360 | 480 | 480 | 0 | 0 | 0 | 0
3.1.2 | % adoption |  | 50% | 60% | 60% | 60% | 0% | 0% | 0% | 0%
Output Indicator 3.2 | Number of farm households benefiting from improved integration in formal value chains. (WP7.2 - Value chain development) |  | 2.4 | 4.8 | 7.2 | 7.2 | 0 | 0 | 0 | 0
3.2.1 | Number of households receiving VCD support |  | 3 | 6 | 9 | 9 | 0 | 0 | 0 | 0
3.2.2 | % adoption |  | 80% | 80% | 80% | 80% | 0% | 0% | 0% | 0%
Output Indicator 3.3 | Number of people participating in VSLAs (gender disaggregated). (WP8.1 - VSLAs) |  | 144 | 288 | 432 | 432 | 0 | 0 | 0 | 0
3.3.1 | Number of VSLAs established |  | 8 | 16 | 24 | 24 | 0 | 0 | 0 | 0
3.3.2 | Average group size |  | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0
3.3.3 | % female membership |  | 70% | 60% | 60% | 60% | 0% | 0% | 0% | 0%
Output Indicator 3.4 | Number of households new income sources from alternative livelihoods. (WP8.2 - Alternative livelihoods) |  | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0
3.4.1 | Number of households receiving alternative livelihood support |  | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0
3.4.2 | % adoption |  | 0% | 0% | 40% | 40% | 0% | 0% | 0% | 0%
Output Indicator 3.5 | Couple Years of Protection (CYP) delivered through support to contraception provision. (WP9 - Reproductive health) |  | 150 | 225 | 380 | 380 | 0 | 0 | 0 | 0
3.5.1 | Number of communities receiving WP9 support |  | 10 | 15 | 19 | 19 | 0 | 0 | 0 | 0
3.5.2 | Number of service users per village |  | 15 | 15 | 20 | 20 | 0 | 0 | 0 | 0
3.5.3 | CYP per service user (assumption from MEL Framework) |  | 6.1 | 6.1 | 6.1 | 6.1 | 0 | 0 | 0 | 0
Output Indicator 4.1 | Number of external knowledge products produced by the project. (WP11 - Sharing lessons) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 4.2 | Number of project meetings with government representatives in attendance. (WP12 - Policy) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)

## Kew
Logframe output reporting
Site: | Massif d'Itremo
Partner: | Kew
Partners should enter targets in any cells with red text.
Targets in grey text are automatically calculated.
|  |  | Target |  |  |  | Achieved
|  | Baseline (2023) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Output Indicator 2.1 | Number of local associations with improved capacity. (WP3.1 - Capacity building) |  | 1.25 | 3.15 | 4.05 | 4.95 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 5 | 9 | 9 | 9 | 0 | 0 | 0 | 0
2.1.2 | Adoption rate |  | 25% | 35% | 45% | 55% | 0% | 0% | 0% | 0%
Output Indicator 2.2 | Number of local associations with increased female membership. (WP3.1 - Capacity building) |  | 0.5 | 2.7 | 3.6 | 5.4 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 5 | 9 | 9 | 9 | 0 | 0 | 0 | 0
2.1.2 | % with increased membership |  | 10% | 30% | 40% | 60% | 0% | 0% | 0% | 0%
Output Indicator 2.3 | Average distance covered by monthly patrols (km). (WP3.3 - Community patrols) |  | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0
Output Indicator 2.4 | Area of land planted for timber and fuelwood (hectares). (WP4.1 - Timber & fuelwood) |  | 4.8 | 14.4 | 24 | 24 | 0 | 0 | 0 | 0
Output Indicator 2.5 | Area of land planted as agroforestry (hectares). (WP4.2 - Agroforestry) |  | 48 | 96 | 96 | 96 | 0 | 0 | 0 | 0
Output Indicator 2.6 | Area of land under active restoration (hectares). (WP4.3 - Forest restoration) |  | 10 | 70 | 140 | 310 | 0 | 0 | 0 | 0
Output Indicator 2.7 | Number of households using fuel-efficient cookstoves. (WP4.4 - Cookstoves) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7.1 | Number of households trained on cookstoves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2 | % adoption |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Output Indicator 2.8 | Number of new PA fire management plans being implemented. (WP5 - Fire) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 2.9 | Number of communities demonstrating improved attitudes to conservation. (WP6 - Nature connectedness) |  | 0 | 0.45 | 0.99 | 4 | 0 | 0 | 0 | 0
2.9.1 | Number of communities with WP6 activities taking place |  | 0 | 3 | 3 | 8 | 0 | 0 | 0 | 0
2.9.2 | % adoption |  | 0% | 15% | 33% | 50% | 0% | 0% | 0% | 0%
Output Indicator 3.1 | Number of farm households practicing climate-smart agriculture. (WP7.1 - Climate smart agriculture) |  | 240 | 480 | 576 | 720 | 0 | 0 | 0 | 0
3.1.1 | Number of farmers trained |  | 480 | 960 | 960 | 960 | 0 | 0 | 0 | 0
3.1.2 | % adoption |  | 50% | 50% | 60% | 75% | 0% | 0% | 0% | 0%
Output Indicator 3.2 | Number of farm households benefiting from improved integration in formal value chains. (WP7.2 - Value chain development) |  | 4.5 | 9 | 30 | 39 | 0 | 0 | 0 | 0
3.2.1 | Number of households receiving VCD support |  | 30 | 30 | 60 | 60 | 0 | 0 | 0 | 0
3.2.2 | % adoption |  | 15% | 30% | 50% | 65% | 0% | 0% | 0% | 0%
Output Indicator 3.3 | Number of people participating in VSLAs (gender disaggregated). (WP8.1 - VSLAs) |  | 220 | 480 | 480 | 480 | 0 | 0 | 0 | 0
3.3.1 | Number of VSLAs established |  | 11 | 24 | 24 | 24 | 0 | 0 | 0 | 0
3.3.2 | Average group size |  | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0
3.3.3 | % female membership |  | 10% | 15% | 20% | 30% | 0% | 0% | 0% | 0%
Output Indicator 3.4 | Number of households new income sources from alternative livelihoods. (WP8.2 - Alternative livelihoods) |  | 0 | 50 | 78 | 112 | 0 | 0 | 0 | 0
3.4.1 | Number of households receiving alternative livelihood support |  | 0 | 250 | 260 | 280 | 0 | 0 | 0 | 0
3.4.2 | % adoption |  | 0% | 20% | 30% | 40% | 0% | 0% | 0% | 0%
Output Indicator 3.5 | Couple Years of Protection (CYP) delivered through support to contraception provision. (WP9 - Reproductive health) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.1 | Number of communities receiving WP9 support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.2 | Number of service users per village |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.3 | CYP per service user (assumption from MEL Framework) |  | 6.1 | 6.1 | 6.1 | 6.1 | 0 | 0 | 0 | 0
Output Indicator 4.1 | Number of external knowledge products produced by the project. (WP11 - Sharing lessons) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 4.2 | Number of project meetings with government representatives in attendance. (WP12 - Policy) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)

## MBG
Logframe output reporting
Site: | Makirovana-Tsihomanaomby
Partner: | MBG
Partners should enter targets in any cells with red text.
Targets in grey text are automatically calculated.
|  |  | Target |  |  |  | Achieved
|  | Baseline (2023) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Output Indicator 2.1 | Number of local associations with improved capacity. (WP3.1 - Capacity building) |  | 5.6 | 8.4 | 9.1 | 9.8 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0
2.1.2 | Adoption rate |  | 40% | 60% | 65% | 70% | 0% | 0% | 0% | 0%
Output Indicator 2.2 | Number of local associations with increased female membership. (WP3.1 - Capacity building) |  | 2.8 | 3.5 | 4.2 | 4.9 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0
2.1.2 | % with increased membership |  | 20% | 25% | 30% | 35% | 0% | 0% | 0% | 0%
Output Indicator 2.3 | Average distance covered by monthly patrols (km). (WP3.3 - Community patrols) |  | 125 | 250 | 375 | 500 | 0 | 0 | 0 | 0
Output Indicator 2.4 | Area of land planted for timber and fuelwood (hectares). (WP4.1 - Timber & fuelwood) |  | 10 | 50 | 90 | 130 | 0 | 0 | 0 | 0
Output Indicator 2.5 | Area of land planted as agroforestry (hectares). (WP4.2 - Agroforestry) |  | 10 | 50 | 100 | 150 | 0 | 0 | 0 | 0
Output Indicator 2.6 | Area of land under active restoration (hectares). (WP4.3 - Forest restoration) |  | 30 | 60 | 90 | 120 | 0 | 0 | 0 | 0
Output Indicator 2.7 | Number of households using fuel-efficient cookstoves. (WP4.4 - Cookstoves) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7.1 | Number of households trained on cookstoves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2 | % adoption |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Output Indicator 2.8 | Number of new PA fire management plans being implemented. (WP5 - Fire) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 2.9 | Number of communities demonstrating improved attitudes to conservation. (WP6 - Nature connectedness) |  | 0.5 | 2.4 | 5.2 | 8.4 | 0 | 0 | 0 | 0
2.9.1 | Number of communities with WP6 activities taking place |  | 1 | 4 | 8 | 12 | 0 | 0 | 0 | 0
2.9.2 | % adoption |  | 50% | 60% | 65% | 70% | 0% | 0% | 0% | 0%
Output Indicator 3.1 | Number of farm households practicing climate-smart agriculture. (WP7.1 - Climate smart agriculture) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 | Number of farmers trained |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.2 | % adoption |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Output Indicator 3.2 | Number of farm households benefiting from improved integration in formal value chains. (WP7.2 - Value chain development) |  | 6.25 | 26.25 | 67.5 | 210 | 0 | 0 | 0 | 0
3.2.1 | Number of households receiving VCD support |  | 25 | 75 | 150 | 350 | 0 | 0 | 0 | 0
3.2.2 | % adoption |  | 25% | 35% | 45% | 60% | 0% | 0% | 0% | 0%
Output Indicator 3.3 | Number of people participating in VSLAs (gender disaggregated). (WP8.1 - VSLAs) |  | 120 | 240 | 345 | 420 | 0 | 0 | 0 | 0
3.3.1 | Number of VSLAs established |  | 8 | 16 | 23 | 28 | 0 | 0 | 0 | 0
3.3.2 | Average group size |  | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0
3.3.3 | % female membership |  | 35% | 40% | 45% | 45% | 0% | 0% | 0% | 0%
Output Indicator 3.4 | Number of households new income sources from alternative livelihoods. (WP8.2 - Alternative livelihoods) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.1 | Number of households receiving alternative livelihood support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.2 | % adoption |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Output Indicator 3.5 | Couple Years of Protection (CYP) delivered through support to contraception provision. (WP9 - Reproductive health) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.1 | Number of communities receiving WP9 support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.2 | Number of service users per village |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.3 | CYP per service user (assumption from MEL Framework) |  | 6.1 | 6.1 | 6.1 | 6.1 | 0 | 0 | 0 | 0
Output Indicator 4.1 | Number of external knowledge products produced by the project. (WP11 - Sharing lessons) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 4.2 | Number of project meetings with government representatives in attendance. (WP12 - Policy) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)

## MV
Logframe output reporting
Site: | Analalava & Analabe-Betanantanana
Partner: | MV
Partners should enter targets in any cells with red text.
Targets in grey text are automatically calculated.
|  |  | Target |  |  |  | Achieved
|  | Baseline (2023) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Output Indicator 2.1 | Number of local associations with improved capacity. (WP3.1 - Capacity building) |  | 1.2 | 1.52 | 1.8 | 2.2 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
2.1.2 | Adoption rate |  | 30% | 38% | 45% | 55% | 0% | 0% | 0% | 0%
Output Indicator 2.2 | Number of local associations with increased female membership. (WP3.1 - Capacity building) |  | 1.2 | 1.4 | 1.6 | 1.6 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
2.1.2 | % with increased membership |  | 30% | 35% | 40% | 40% | 0% | 0% | 0% | 0%
Output Indicator 2.3 | Average distance covered by monthly patrols (km). (WP3.3 - Community patrols) |  | 600 | 660 | 720 | 720 | 0 | 0 | 0 | 0
Output Indicator 2.4 | Area of land planted for timber and fuelwood (hectares). (WP4.1 - Timber & fuelwood) |  | 80 | 100 | 150 | 225 | 0 | 0 | 0 | 0
Output Indicator 2.5 | Area of land planted as agroforestry (hectares). (WP4.2 - Agroforestry) |  | 1.2 | 2 | 3 | 4 | 0 | 0 | 0 | 0
Output Indicator 2.6 | Area of land under active restoration (hectares). (WP4.3 - Forest restoration) |  | 0 | 2 | 4 | 6 | 0 | 0 | 0 | 0
Output Indicator 2.7 | Number of households using fuel-efficient cookstoves. (WP4.4 - Cookstoves) |  | 24.75 | 55 | 97.5 | 150 | 0 | 0 | 0 | 0
2.7.1 | Number of households trained on cookstoves |  | 55 | 100 | 150 | 200 | 0 | 0 | 0 | 0
2.1.2 | % adoption |  | 45% | 55% | 65% | 75% | 0% | 0% | 0% | 0%
Output Indicator 2.8 | Number of new PA fire management plans being implemented. (WP5 - Fire) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 2.9 | Number of communities demonstrating improved attitudes to conservation. (WP6 - Nature connectedness) |  | 0.8 | 1.8 | 3 | 4.8 | 0 | 0 | 0 | 0
2.9.1 | Number of communities with WP6 activities taking place |  | 2 | 4 | 6 | 8 | 0 | 0 | 0 | 0
2.9.2 | % adoption |  | 40% | 45% | 50% | 60% | 0% | 0% | 0% | 0%
Output Indicator 3.1 | Number of farm households practicing climate-smart agriculture. (WP7.1 - Climate smart agriculture) |  | 27.3 | 56 | 128 | 144 | 0 | 0 | 0 | 0
3.1.1 | Number of farmers trained |  | 42 | 80 | 160 | 180 | 0 | 0 | 0 | 0
3.1.2 | % adoption |  | 65% | 70% | 80% | 80% | 0% | 0% | 0% | 0%
Output Indicator 3.2 | Number of farm households benefiting from improved integration in formal value chains. (WP7.2 - Value chain development) |  | 0 | 0 | 12 | 20 | 0 | 0 | 0 | 0
3.2.1 | Number of households receiving VCD support |  | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0
3.2.2 | % adoption |  | 0% | 0% | 30% | 50% | 0% | 0% | 0% | 0%
Output Indicator 3.3 | Number of people participating in VSLAs (gender disaggregated). (WP8.1 - VSLAs) |  | 80 | 208 | 336 | 336 | 0 | 0 | 0 | 0
3.3.1 | Number of VSLAs established |  | 5 | 13 | 21 | 21 | 0 | 0 | 0 | 0
3.3.2 | Average group size |  | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0
3.3.3 | % female membership |  | 60% | 60% | 65% | 70% | 0% | 0% | 0% | 0%
Output Indicator 3.4 | Number of households new income sources from alternative livelihoods. (WP8.2 - Alternative livelihoods) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.1 | Number of households receiving alternative livelihood support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.2 | % adoption |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Output Indicator 3.5 | Couple Years of Protection (CYP) delivered through support to contraception provision. (WP9 - Reproductive health) |  | 30 | 60 | 90 | 120 | 0 | 0 | 0 | 0
3.5.1 | Number of communities receiving WP9 support |  | 2 | 4 | 6 | 8 | 0 | 0 | 0 | 0
3.5.2 | Number of service users per village |  | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0
3.5.3 | CYP per service user (assumption from MEL Framework) |  | 6.1 | 6.1 | 6.1 | 6.1 | 0 | 0 | 0 | 0
Output Indicator 4.1 | Number of external knowledge products produced by the project. (WP11 - Sharing lessons) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 4.2 | Number of project meetings with government representatives in attendance. (WP12 - Policy) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)

## TPF
Logframe output reporting
Site: | Bemanevika-Mahimborondro
Partner: | TPF
Partners should enter targets in any cells with red text.
Targets in grey text are automatically calculated.
|  |  | Target |  |  |  | Achieved
|  | Baseline (2023) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027) | Milestone 1 (2024) | Midline (2025) | Milestone 3 (2026) | Endline (2027)
Output Indicator 2.1 | Number of local associations with improved capacity. (WP3.1 - Capacity building) |  | 5.6 | 6.4 | 8.5 | 10.2 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 16 | 16 | 17 | 17 | 0 | 0 | 0 | 0
2.1.2 | Adoption rate |  | 35% | 40% | 50% | 60% | 0% | 0% | 0% | 0%
Output Indicator 2.2 | Number of local associations with increased female membership. (WP3.1 - Capacity building) |  | 4 | 4.8 | 5.95 | 7.14 | 0 | 0 | 0 | 0
2.1.1 | Number of associations trained |  | 16 | 16 | 17 | 17 | 0 | 0 | 0 | 0
2.1.2 | % with increased membership |  | 25% | 30% | 35% | 42% | 0% | 0% | 0% | 0%
Output Indicator 2.3 | Average distance covered by monthly patrols (km). (WP3.3 - Community patrols) |  | 128 | 384 | 512 | 640 | 0 | 0 | 0 | 0
Output Indicator 2.4 | Area of land planted for timber and fuelwood (hectares). (WP4.1 - Timber & fuelwood) |  | 13 | 30 | 47 | 64 | 0 | 0 | 0 | 0
Output Indicator 2.5 | Area of land planted as agroforestry (hectares). (WP4.2 - Agroforestry) |  | 3 | 6 | 7.5 | 8.5 | 0 | 0 | 0 | 0
Output Indicator 2.6 | Area of land under active restoration (hectares). (WP4.3 - Forest restoration) |  | 24 | 48 | 72 | 96 | 0 | 0 | 0 | 0
Output Indicator 2.7 | Number of households using fuel-efficient cookstoves. (WP4.4 - Cookstoves) |  | 8 | 30 | 51.2 | 76 | 0 | 0 | 0 | 0
2.7.1 | Number of households trained on cookstoves |  | 40 | 120 | 160 | 200 | 0 | 0 | 0 | 0
2.1.2 | % adoption |  | 20% | 25% | 32% | 38% | 0% | 0% | 0% | 0%
Output Indicator 2.8 | Number of new PA fire management plans being implemented. (WP5 - Fire) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 2.9 | Number of communities demonstrating improved attitudes to conservation. (WP6 - Nature connectedness) |  | 0.9 | 2.1 | 3.6 | 6.75 | 0 | 0 | 0 | 0
2.9.1 | Number of communities with WP6 activities taking place |  | 3 | 6 | 9 | 15 | 0 | 0 | 0 | 0
2.9.2 | % adoption |  | 30% | 35% | 40% | 45% | 0% | 0% | 0% | 0%
Output Indicator 3.1 | Number of farm households practicing climate-smart agriculture. (WP7.1 - Climate smart agriculture) |  | 12 | 56 | 112 | 164 | 0 | 0 | 0 | 0
3.1.1 | Number of farmers trained |  | 40 | 160 | 280 | 410 | 0 | 0 | 0 | 0
3.1.2 | % adoption |  | 30% | 35% | 40% | 40% | 0% | 0% | 0% | 0%
Output Indicator 3.2 | Number of farm households benefiting from improved integration in formal value chains. (WP7.2 - Value chain development) |  | 0 | 0 | 8 | 27 | 0 | 0 | 0 | 0
3.2.1 | Number of households receiving VCD support |  | 0 | 0 | 40 | 90 | 0 | 0 | 0 | 0
3.2.2 | % adoption |  | 0% | 0% | 20% | 30% | 0% | 0% | 0% | 0%
Output Indicator 3.3 | Number of people participating in VSLAs (gender disaggregated). (WP8.1 - VSLAs) |  | 160 | 280 | 400 | 520 | 0 | 0 | 0 | 0
3.3.1 | Number of VSLAs established |  | 8 | 14 | 20 | 26 | 0 | 0 | 0 | 0
3.3.2 | Average group size |  | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0
3.3.3 | % female membership |  | 50% | 50% | 50% | 50% | 0% | 0% | 0% | 0%
Output Indicator 3.4 | Number of households new income sources from alternative livelihoods. (WP8.2 - Alternative livelihoods) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.1 | Number of households receiving alternative livelihood support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.2 | % adoption |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Output Indicator 3.5 | Couple Years of Protection (CYP) delivered through support to contraception provision. (WP9 - Reproductive health) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.1 | Number of communities receiving WP9 support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.2 | Number of service users per village |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.3 | CYP per service user (assumption from MEL Framework) |  | 6.1 | 6.1 | 6.1 | 6.1 | 0 | 0 | 0 | 0
Output Indicator 4.1 | Number of external knowledge products produced by the project. (WP11 - Sharing lessons) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)
Output Indicator 4.2 | Number of project meetings with government representatives in attendance. (WP12 - Policy) | (n/a - set centrally by FMH management) |  |  |  |  | (n/a - monitored centrally by FMH management)

## Double counting
Double counting assumptions
Assumptions
Crossover | 70% | i.e., In any village where multiple livelihood interventions (WP7/8) are carried out, 70% of beneficiaries participate in multiple interventions.
Calculations
Beneficiary count |  | 4549.6
Including duplicates
Total unique benefciaries: |  | 3240.1299
With double counting removed
| DU-APCLFA | [6 empty] | DU-APMA | [6 empty] | Kew
|  | Beneficiaries per intervention (inc. duplicates) | [6 empty] | Beneficiaries per intervention (inc. duplicates) | [6 empty] | Beneficiaries per intervention (inc. duplicates)
Intervention | Number of villages | CSA | VCD | VSLA | AL | Unique beneficiaries |  | Number of villages | CSA | VCD | VSLA | AL | Unique beneficiaries |  | Number of villages | CSA | VCD | VSLA | AL | Unique beneficiaries
CSA only | 3 | 22.7368 | - | - | - | 22.7368 |  | 3 | 57.6 | - | - | - | 57.6 |  | 4 | 120 | - | - | - | 120
VCD only | 0 | - | 0 | - | - | 0 |  | 0 | - | 0 | - | - | 0 |  | 0 | - | 0 | - | - | 0
VSLA only | 0 | - | - | 0 | - | 0 |  | 2 | - | - | 72 | - | 72 |  | 0 | - | - | 0 | - | 0
AL only | 0 | - | - | - | 0 | 0 |  | 0 | - | - | - | 0 | 0 |  | 0 | - | - | - | 0 | 0
CSA+VCD | 1 | 7.5789 | 0.91429 | - | - | 7.5789 |  | 0 | 0 | 0 | - | - | 0 |  | 0 | 0 | 0 | - | - | 0
CSA+VSLA | 24 | 181.8947 | - | 228.7059 | - | 241.5298 |  | 5 | 96 | - | 180 | - | 180 |  | 0 | 0 | - | 0 | - | 0
CSA+AL | 0 | 0 | - | - | 0 | 0 |  | 2 | 38.4 | - | - | 3 | 38.4 |  | 0 | 0 | - | - | 0 | 0
VCD+VSLA | 0 | - | 0 | 0 | - | 0 |  | 0 | - | 0 | 0 | - | 0 |  | 0 | - | 0 | 0 | - | 0
VCD+AL | 0 | - | 0 | - | 0 | 0 |  | 0 | - | 0 | - | 0 | 0 |  | 0 | - | 0 | - | 0 | 0
VSLA+AL | 0 | - | - | 0 | 0 | 0 |  | 0 | - | - | 0 | 0 | 0 |  | 0 | - | - | 0 | 0 | 0
CSA+VCD+VSLA | 0 | 0 | 0 | 0 | - | 0 |  | 3 | 57.6 | 5.4 | 108 | - | 108 |  | 0 | 0 | 0 | 0 | - | 0
CSA+VCD+AL | 0 | 0 | 0 | - | 0 | 0 |  | 0 | 0 | 0 | - | 0 | 0 |  | 1 | 30 | 6.5 | - | 5.6 | 30
CSA+VSLA+AL | 4 | 30.3158 | - | 38.1176 | 2.4 | 41.6667 |  | 1 | 19.2 | - | 36 | 1.5 | 36 |  | 14 | 420 | - | 353.6842 | 78.4 | 501.226
VCD+VSLA+AL | 0 | - | 0 | 0 | 0 | 0 |  | 0 | - | 0 | 0 | 0 | 0 |  | 0 | - | 0 | 0 | 0 | 0
CSA+VCD+VSLA+AL | 6 | 45.4737 | 5.4857 | 57.1765 | 3.6 | 65.727 |  | 1 | 19.2 | 1.8 | 36 | 1.5 | 36 |  | 5 | 150 | 32.5 | 126.3158 | 28 | 198.1269
Total | 38 | 288 | 6.4 | 324 | 6 | 379.2393 |  | 17 | 288 | 7.2 | 432 | 6 | 528 |  | 24 | 720 | 39 | 480 | 112 | 849.3529
| MBG | [6 empty] | MV | [6 empty] | TPF
|  | Beneficiaries per intervention (inc. duplicates) | [6 empty] | Beneficiaries per intervention (inc. duplicates) | [6 empty] | Beneficiaries per intervention (inc. duplicates)
Intervention | Number of villages | CSA | VCD | VSLA | AL | Unique beneficiaries |  | Number of villages | CSA | VCD | VSLA | AL | Unique beneficiaries |  | Number of villages | CSA | VCD | VSLA | AL | Unique beneficiaries
CSA only | 0 | 0 | - | - | - | 0 |  | 0 | 0 | - | - | - | 0 |  | 21 | 88.3077 | - | - | - | 88.3077
VCD only | 16 | - | 101.8182 | - | - | 101.8182 |  | 0 | - | 0 | - | - | 0 |  | 0 | - | 0 | - | - | 0
VSLA only | 9 | - | - | 145.3846 | - | 145.3846 |  | 6 | - | - | 144 | - | 144 |  | 1 | - | - | 27.3684 | - | 27.3684
AL only | 0 | - | - | - | 0 | 0 |  | 0 | - | - | - | 0 | 0 |  | 0 | - | - | - | 0 | 0
CSA+VCD | 0 | 0 | 0 | - | - | 0 |  | 0 | 0 | 0 | - | - | 0 |  | 0 | 0 | 0 | - | - | 0
CSA+VSLA | 0 | 0 | - | 0 | - | 0 |  | 0 | 0 | - | 0 | - | 0 |  | 14 | 58.8718 | - | 383.1579 | - | 383.1579
CSA+AL | 0 | 0 | - | - | 0 | 0 |  | 0 | 0 | - | - | 0 | 0 |  | 0 | 0 | - | - | 0 | 0
VCD+VSLA | 17 | - | 108.1818 | 274.6154 | - | 274.6154 |  | 0 | - | 0 | 0 | - | 0 |  | 0 | - | 0 | 0 | - | 0
VCD+AL | 0 | - | 0 | - | 0 | 0 |  | 0 | - | 0 | - | 0 | 0 |  | 0 | - | 0 | - | 0 | 0
VSLA+AL | 0 | - | - | 0 | 0 | 0 |  | 0 | - | - | 0 | 0 | 0 |  | 0 | - | - | 0 | 0 | 0
CSA+VCD+VSLA | 0 | 0 | 0 | 0 | - | 0 |  | 8 | 144 | 20 | 192 | - | 209.4118 |  | 4 | 16.8205 | 27 | 109.4737 | - | 109.4737
CSA+VCD+AL | 0 | 0 | 0 | - | 0 | 0 |  | 0 | 0 | 0 | - | 0 | 0 |  | 0 | 0 | 0 | - | 0 | 0
CSA+VSLA+AL | 0 | 0 | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
VCD+VSLA+AL | 0 | - | 0 | 0 | 0 | 0 |  | 0 | - | 0 | 0 | 0 | 0 |  | 0 | - | 0 | 0 | 0 | 0
CSA+VCD+VSLA+AL | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total | 42 | 0 | 210 | 420 | 0 | 521.8182 |  | 14 | 144 | 20 | 336 | 0 | 353.4118 |  | 40 | 164 | 27 | 520 | 0 | 608.3077
Locations
The table below reads from the separate Intervention Locations sheet.
| DU-APCLFA |  |  |  | DU-APMA |  |  |  | Kew |  |  |  | MBG |  |  |  | MV |  |  |  | TPF
| WP7: Agriculture |  | WP8: Alternative livelihoods |  | WP7: Agriculture |  | WP8: Alternative livelihoods |  | WP7: Agriculture |  | WP8: Alternative livelihoods |  | WP7: Agriculture |  | WP8: Alternative livelihoods |  | WP7: Agriculture |  | WP8: Alternative livelihoods |  | WP7: Agriculture |  | WP8: Alternative livelihoods
| 7.1 Climate-smart agriculture | 7.2 Value chain development | 8.1 VSLAs | 8.2 Alternative income generation | 7.1 Climate-smart agriculture | 7.2 Value chain development | 8.1 VSLAs | 8.2 Alternative income generation | 7.1 Climate-smart agriculture | 7.2 Value chain development | 8.1 VSLAs | 8.2 Alternative income generation | 7.1 Climate-smart agriculture | 7.2 Value chain development | 8.1 VSLAs | 8.2 Alternative income generation | 7.1 Climate-smart agriculture | 7.2 Value chain development | 8.1 VSLAs | 8.2 Alternative income generation | 7.1 Climate-smart agriculture | 7.2 Value chain development | 8.1 VSLAs | 8.2 Alternative income generation
# of villages | 38 | 7 | 34 | 10 | 15 | 4 | 12 | 4 | 24 | 6 | 19 | 20 | 0 | 33 | 26 | 0 | 8 | 8 | 14 | 0 | 39 | 4 | 19 | 0
# of beneficiaries | 288 | 6.4 | 324 | 6 | 288 | 7.2 | 432 | 6 | 720 | 39 | 480 | 112 | 0 | 210 | 420 | 0 | 144 | 20 | 336 | 0 | 164 | 27 | 520 | 0
1 | no | no | no | no | no | no | no | no | yes | no | yes | yes | no | no | no | no | yes | yes | yes | no | yes | no | yes | no
2 | yes | yes | yes | yes | no | no | no | no | yes | no | yes | yes | no | yes | no | no | no | no | no | no | no | no | no | no
3 | yes | yes | yes | yes | no | no | no | no | yes | no | yes | yes | no | yes | yes | no | no | no | no | no | yes | no | no | no
4 | no | no | no | no | yes | no | yes | no | yes | no | yes | yes | no | no | no | no | yes | yes | yes | no | yes | no | no | no
5 | no | no | no | no | no | no | yes | no | yes | no | yes | yes | no | yes | yes | no | no | no | no | no | no | no | no | no
6 | no | no | no | no | no | no | no | no | yes | no | yes | yes | no | yes | yes | no | no | no | yes | no | yes | no | no | no
7 | yes | no | yes | no | no | no | no | no | yes | yes | yes | yes | no | yes | yes | no | no | no | no | no | yes | yes | yes | no
8 | yes | no | yes | no | no | no | no | no | no | no | no | no | no | yes | no | no | no | no | no | no | no | no | no | no
9 | no | no | no | no | yes | no | no | no | yes | no | yes | yes | no | yes | no | no | yes | yes | yes | no | yes | no | yes | no
10 | yes | yes | yes | yes | no | no | no | no | yes | no | no | no | no | yes | no | no | yes | yes | yes | no | yes | no | no | no
11 | yes | no | yes | no | no | no | no | no | yes | no | yes | yes | no | no | no | no | no | no | no | no | yes | no | yes | no
12 | yes | no | yes | no | no | no | no | no | yes | yes | yes | yes | no | no | no | no | yes | yes | yes | no | yes | yes | yes | no
13 | no | no | no | no | no | no | no | no | yes | yes | no | yes | no | no | yes | no | no | no | no | no | yes | yes | yes | no
14 | yes | no | yes | no | yes | no | no | no | yes | no | no | no | no | no | yes | no | no | no | no | no | yes | no | no | no
15 | yes | no | yes | no | no | no | no | no | yes | no | yes | yes | no | no | no | no | no | no | yes | no | no | no | no | no
16 | yes | no | yes | no | no | no | no | no | yes | no | yes | yes | no | yes | yes | no | no | no | no | no | yes | no | yes | no
17 | no | no | no | no | no | no | no | no | yes | yes | yes | yes | no | yes | no | no | no | no | yes | no | yes | no | yes | no
18 | yes | no | yes | no | no | no | no | no | yes | no | yes | yes | no | yes | yes | no | yes | yes | yes | no | yes | no | yes | no
19 | no | no | no | no | no | no | no | no | yes | yes | yes | yes | no | yes | yes | no | no | no | no | no | no | no | no | no
20 | yes | no | yes | no | no | no | no | no | yes | no | no | no | no | yes | no | no | yes | yes | yes | no | no | no | no | no
21 | yes | yes | yes | yes | no | no | no | no | yes | no | yes | yes | no | no | yes | no | no | no | no | no | no | no | no | no
22 | no | no | no | no | no | no | no | no | yes | yes | yes | yes | no | no | no | no | no | no | no | no | yes | no | no | no
23 | yes | no | yes | no | no | no | no | no | yes | no | yes | yes | no | no | no | no | no | no | no | no | no | no | no | no
24 | no | no | no | no | yes | no | no | no | yes | no | no | no | no | no | no | no | no | no | yes | no | yes | no | no | no
25 | yes | no | yes | no | no | no | no | no | yes | no | yes | yes | no | yes | yes | no | no | no | no | no | yes | no | no | no
26 | no | no | no | no | yes | no | no | yes | 0 | 0 | 0 | 0 | no | yes | no | no | yes | yes | yes | no | yes | no | no | no
27 | yes | no | yes | no | yes | no | yes | yes | 0 | 0 | 0 | 0 | no | no | no | no | no | no | yes | no | yes | no | no | no
28 | no | no | no | no | yes | no | yes | no | 0 | 0 | 0 | 0 | no | yes | no | no | no | no | no | no | yes | no | yes | no
29 | no | no | no | no | yes | yes | yes | yes | 0 | 0 | 0 | 0 | no | no | yes | no | no | no | yes | no | yes | no | no | no
30 | yes | no | yes | yes | yes | yes | yes | no | 0 | 0 | 0 | 0 | no | no | yes | no | no | no | no | no | no | no | no | no
31 | no | no | no | no | no | no | no | no | 0 | 0 | 0 | 0 | no | no | no | no | no | no | no | no | yes | no | no | no
32 | no | no | no | no | no | no | no | no | 0 | 0 | 0 | 0 | no | no | no | no | no | no | no | no | no | no | yes | no
33 | yes | yes | no | no | yes | no | no | yes | 0 | 0 | 0 | 0 | no | no | no | no | no | no | no | no | no | no | no | no
34 | no | no | no | no | yes | yes | yes | no | 0 | 0 | 0 | 0 | no | yes | no | no | no | no | no | no | yes | no | yes | no
35 | no | no | no | no | no | no | yes | no | 0 | 0 | 0 | 0 | no | no | no | no | no | no | no | no | yes | no | no | no
36 | no | no | no | no | yes | no | yes | no | 0 | 0 | 0 | 0 | no | no | yes | no | no | no | no | no | no | no | no | no
37 | yes | no | yes | yes | yes | no | yes | no | 0 | 0 | 0 | 0 | no | yes | yes | no | 0 | 0 | 0 | 0 | yes | no | no | no
38 | yes | no | yes | no | no | no | no | no | 0 | 0 | 0 | 0 | no | yes | no | no | 0 | 0 | 0 | 0 | yes | no | no | no
39 | yes | no | no | no | yes | yes | yes | no | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | yes | no | yes | no
40 | no | no | no | no | yes | no | yes | no | 0 | 0 | 0 | 0 | no | yes | yes | no | 0 | 0 | 0 | 0 | no | no | no | no
41 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | yes | no | 0 | 0 | 0 | 0 | no | no | no | no
42 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | yes | no | 0 | 0 | 0 | 0 | yes | no | no | no
43 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | no | no | 0 | 0 | 0 | 0 | yes | no | yes | no
44 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | yes | no | 0 | 0 | 0 | 0 | yes | no | yes | no
45 | yes | yes | yes | yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | no | no | 0 | 0 | 0 | 0 | yes | no | no | no
46 | yes | yes | yes | yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | yes | no | no | no
47 | yes | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | yes | no | 0 | 0 | 0 | 0 | no | no | no | no
48 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | no | no | no | no
49 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | no | no | no | no
50 | yes | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | yes | no | yes | no
51 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | yes | no | yes | no
52 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | yes | no | 0 | 0 | 0 | 0 | yes | no | yes | no
53 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | yes | yes | yes | no
54 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | yes | no | no | no
55 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | no | no | 0 | 0 | 0 | 0 | no | no | no | no
56 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | no | no | 0 | 0 | 0 | 0 | no | no | no | no
57 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | no | no | 0 | 0 | 0 | 0 | yes | no | no | no
58 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | yes | no | 0 | 0 | 0 | 0 | yes | no | no | no
59 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | yes | no | yes | yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | yes | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | yes | no | yes | yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | yes | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | yes | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | no | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0