## Updated_2019
PROJECT TITLE | Defra ICF Blue Forests Project | [11 empty] | Source of information
IMPACT | Impact Indicator 1 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2037 (Year 20)
|  | Original | 0 | Total: 52,620; of which is verified: 0 | Total: 111,493; of which is verified: 0 | Total: 794,734; of which is verified: 0 | Total: 1,473,100; of which is verified: 0 | Total: 2,153,807; of which is verified: 63,594 | Total: 3,709,450; of which is verified: 129,371 | Total: 5,262,036; of which is verified: 197,303 | Total: 24,420,335; of which is verified: 13,934,696
Mangrove forests and ecosystem services (fisheries etc) protected and restored, preventing carbon emissions and supporting security of livelihoods in coastal communities. | Tonnes of CO2 emissions prevented (KPI 6) | Planned | 0 | Total: 54,620 | Total: 111,493 | Total: 149,974 | Total: 432,021 | Total: 721,927 | Total: 1,197,499 | Total: 1,682,211 | Total: 7,768,115 |  | Business case, sheet Deforestation & carbon, Columns BX-BY
|  | Achieved | 0 | Total estimated: 24,378; of which verified: 0 | Total estimated 50,475; of which verified: 0 | Total: 149,974; of which is verified: 0 | 0 | 0 | 0 | 0 | 0
Source
Forest change analysis will only be done every 5 years (starting in 2015). So until 2020, the unverified figures will be extrapolations based on estimates of effectiveness on the ground.
| Impact Indicator 2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2037 (Year 20)
|  | Original | 28300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | 28300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | Improved understanding of livelihood benefits in TH (4542) and measurement criteria/methods for other sites | Improved understanding of livelihoods benefits in AB and TH (29893). Census and baselines in Maha established. | Improved understanding of livelihoods benefits at 3 sites. Census and baselines in Indo established. Number of people estimated: 35,000 | Census and baselines in Indo established. Census and baselines in SE Asia. Number of people estimated: 63,000 | Census and baselines in SE Asia. Number of people estimated: 82,000 | 91659 | 119649
| Number of forest dependent people (ASSUMPTION: all people we work with are forest dependent) with livelihoods benefits (INCOME GENERATION AND FOOD SECURITY) protected or improved (KPI 3) | Planned | 28300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | 28300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | Improved understanding of livelihood benefits in TH (4542) and measurement criteria/methods for other sites | Improved understanding of livelihoods benefits in AB and TH (29893). Census and baselines in Maha established. | Improved understanding of livelihoods benefits at 3 sites. Census and baselines in Indo established. Number of people estimated: 33,000 | Census and baselines in Indo established. Census and baselines in SE Asia. Number of people estimated: 58,000 | Census and baselines in SE Asia. Number of people estimated: 59,000 | 61000 | 86000
|  | Achieved | 0 | Baseline intake assessments for alternative livelihood projects developed, and population baselines established across the Vel LMMA (TH) against which project level benefits may be compared. | Baseline intake assessments for alternative livelihood project participants underway. Baseline for Velondriake; HH weekly income MGA/Week or $90.48 PPP; $2.72 (PPP) per person, per day | 29893 - Census and baseline established in Site 3. | 0 | 0 | 0 | 0 | 0
Source
Activity beneficiary data, local census data where available and reliable, or BV census data where necessary. Integrated social surveys will be carried out at each site every 5 years.
| Site 1 - AAB |  | 0 | 0 | 0 | 25351 | 25351 | 26779 | 26779 | 28287 | 41508
| Site 2 - TH |  | 0 | 0 | 4542 | 4542 | 4542 | 4798 | 4798 | 5068 | 7437
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 2962 | 3044 | 3129 | 3216 | 8647
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 4101 | 4151 | 4201 | 4915
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 19707 | 19946 | 20188 | 23617
| Impact Indicator 3 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2023 (Year 7)
|  | Original | 6 | 10 | 12 | 16 | 20 | 23 | 26 | 29 | 29
| Extent to which ICF intervention is likely to have a transformational impact (KPI 15): Number of additional sites adopting models tested and proved within this project (outside of 6 sites) | Planned | 27 | 35 | 40 | 57 | 72 | 78 | 89 | 99 | 99
|  | Achieved | 0 | 38 | 44 | 60 | 0 | 0 | 0 | 0 | 0
Source
BV partner support database and tracking system
| PHE model |  | 6 | 10 | 11 | 14 | 16 | 18 | 20 | 22 | 22
| Octopus model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FIP |  | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 4
| Closure |  | 21 | 28 | 32 | 43 | 51 | 55 | 62 | 70 | 78
| Mangrove crab model |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sea cucumber model |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| VCS model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan Vivo model |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Bee keeping model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Homestay model |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Impact Indicator 4 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2037 (Year 20)
|  | Original | 0 | Total: 193; of which is verified: 0 | Total: 380; of which is verified: 0 | Total: 858; of which is verified: 0 | Total: 1323; of which is verified: 0 | Total: 1774; of which is verified: 174 | Total: 2644; of which is verified: 343 | Total: 3492; of which is verified: 508 | N/A
| Total number of hectares where deforestation have been avoided (KPI 8) [Note: we have removed degradation from this KPI as it is not possible to measure simply] | Planned | 0 | Total: 193; of which is verified: 0 | Total: 380; of which is verified: 0 | Total: 251 | Total: 464 | Total: 677 | Total: 936 | Total: 1194 | Total: 4413
|  | Achieved | 0 | Esimated Total: 43 (Site 1 & Site 2); of which is verified: 0. Can not include Site 3 yet as work not yet started. | Esimated Total: 84 (Site 1 & Site 2); of which is verified: 0. Can not include Site 3 yet as work still in its infancy. | 251 | 0 | 0 | 0 | 0 | 0
Source
GIS datsets showing baseline mangrove cover at the start of the intervention and GIS datasets showing current mangrove coverage
| Site 1 - AAB |  | 0 | 43 | 84 | 126 | 0 | 39.74 | 78.8 | 117.17 | 117.17 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 2 - TH |  | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 134.04 | 264.31 | 390.89 | 390.89 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Impact Indicator 5 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2023 (Year 7)
|  | Original | 0 | 65340 | 147361 | 268088 | 386398 | 556503 | 811598 | 1061901 | 1061901
| Ecosystem services (KPI 10): Difference in mangrove forest ecosystem services income (shoreline protection; pollution abatement; protection from sedimentation) provided by standing mangroves compared to without project scenario. ($/yr) | Planned | 0 | 65340 | 147361 | 124112 | 207307 | 308616 | 416671 | 524259 | 524259
|  | Achieved | 0 | We can only estimate 65,340 at present. | Estimate still at 147,361 updating figures following final site selection and regional/national figures validated | Estimate still at 124,112 updating figures following final site selection and regional/national figures validated | 0 | 0 | 0 | 0 | 0
Source
Hectares (Impact Indicator 4) will be used to calculate ES via the model developed in the business plan.
| Site 1 - AAB |  | 0 | 14452 | 46985 | 79274 | 111558 | 144074 | 177296 | 210286 | 210286
| Site 2 - TH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 3 - Maha |  | 0 | 50888 | 100376 | 44838 | 89472 | 133904 | 178133 | 222161 | 222161
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 2309 | 20018 | 40025 | 60021 | 60021
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 3968 | 10620 | 21217 | 31791 | 31791
OUTCOME | Outcome Indicator 1 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2023 (Year 7) | Assumptions
|  | Original | 250 | 5700 | 5700 | 8700 | 8700 | 39100 | 39100 | 89100 | 89100
Sustainable mangrove forestry and fisheries management activities implemented at six sites where coastal communities are supported by alternative livelihoods and improved access to health care, and therefore models for replication are validated. | Ha of mangrove forest area protected or under sustainable local management | Planned | 250 | 5700 | 5700 | 8700 | 9299 | 27500 | 117179 | 179678 | 181678 | Assumption: project would not have happened without Blue Ventures.
|  | Achieved | 0 | 5700 ha are now protected. 4600 of which are under draft management plans and 1100 of which are secured under Marine Protected Area control. | 6229 ha are now protected. 5199 of which are under ratified management plans and 1100 of which are secured under Marine Protected Area control. | 6229 ha are now protected. 5199 of which are under ratified management plans and 1100 of which are secured under Marine Protected Area control. | 0 | 0 | 0 | 0 | 0
Source
BV GIS datasets containing management plans/areas covered by dina and BV GIS datasets showing current (within 5 years) mangrove coverage
| Site 1 - AAB |  | 0 | 4600 ha secured under draft management plans | 5199 secured under management plans signed by the regional forestry services | 5199 secured under management plans signed by the regional forestry services | 5199 | 6000 | 6000 | 6000 | 6000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 2 - TH |  | 250 | 1100 ha secured under MPA protection | 1100 secured under both MPA protection and forestry management legislation | 1100 secured under both MPA protection and forestry management legislation | 1100 | 1100 | 1100 | 1100 | 1100 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 3 - Maha |  | 0 | Protection/sustainable management options assessed for Site 3 | Protection/sustainable management options assessed for Site 3 | Management unit defined. Discussions underway with communities around management options | 3000 | 5000 | 5000 | 5000 | 7000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 4 - Sembilang National Park |  | 0 | Current management/protection status assessed for potential Site 4 | Current management/protection status assessed for Site 4 | 0 | 0 | 400 | 90079 | 90079 | 90079 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 5 - Kubu Raya |  | 0 | Current management/protection status assessed for potential Site 5 | Current management/protection status assessed for potential Site 5 | 0 | 0 | 15000 | 15000 | 77499 | 77499 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Outcome Indicator 2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 0 | 0 | 1 | 2 | 2 | 5 | 5 | 5 | 5
| Number of sites implicated in Fisheries management including but not limited to Fisheries Improvement Projects (registered or actions plans being implemented) | Planned | 0 | 0 | 1 | 2 | 2 | 5 | 5 | 5 | 5
|  | Achieved | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Source
Blue Ventures village activity log and FIP action documents
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Outcome Indicator 3 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 10% in Site 2 | 10% in Site 2 | 6.6667 | 16.6667 | 30 | 46.6667 | 46.6667 | 60 | 60
| % of people making agreed model profit from alternative activity | Planned | 10% in Site 2 | 10% in Site 2 | 6.6667 | 16.6667 | 30 | 46.6667 | 46.6667 | 60 | 60
|  | Achieved | 0 | 10% in Site 2 | First sales due in October 2018 all figures to be updated with final sales data | 20.175 | 0 | 0 | 0 | 0 | 0
Source
Blue Ventures farmers log and sales data
| Site 1 - AAB |  | 0 | 0 | 0.0027612 | 0 | 40 | 60 | 60 | 60 | 60
| Site 2 - TH |  | 10.67% | 10 | 10.2 | 40.35 | 60 | 60 | 60 | 60 | 60
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 10 | 40 | 60 | 60 | 60
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 10 | 10 | 60 | 60 | 60
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 10 | 10 | 20 | 60 | 60
| Outcome Indicator 4 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 258 unintended pregnancies averted in 2016 / 4 = 64 unintended pregnancies averted for the 8 communities with CHWs in 2016 at Site 2. | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site
| Unitended pregnancies averted NOTE: we can't provide a target for this output as it depends on the number of voluntary family planning users and their free choice of contraceptive methods | Planned | 258 unintended pregnancies averted in 2016 / 4 = 64 unintended pregnancies averted for the 8 communities with CHWs in 2016 at Site 2. | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value calculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site
|  | Achieved | 0 | The data for this outcome will be collected every two years – first milestone is therefore in 2018. | 1270 - these figures are as of end Sept 2018, final year figures | 1270 | 0 | 0 | 0 | 0 | 0
Source
Blue Ventures data: Number and types of contracptives provided and calculated using Marie Stopes Impact 2 Calculations for number of unintended pregnancies averted
| Site 1 - AAB |  | 0 | 75 | 110 | 320 | 0 | 0 | 0 | 0 | 0
| Site 2 - TH |  | 258 unintended pregnancies averted in 2016 / 4 = 64 unintended pregnancies averted for the 8 communities with CHWs in 2016 at Site 2. | 625 | 1160 | 929 | 0 | 0 | 0 | 0 | 0
| Site 3 - Maha |  | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Outcome Indicator 5 |  | Baseline | 2017 | Milestone 1 (2018, Y2) | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2023 (Year 7)
|  | Original | 0 | 2 | 2 | 2 | 5 | 4 | 5 | 5 | 5
| Number of new pieces of evidence (per year) for individual conservation models (eg. crab fishery closure model, Plan Vivo model) | Planned | 0 | 2 | 2 | 2 | 5 | 4 | 5 | 5 | 5
|  | Achieved | 0 | Results from the models have been analysed and we have additional understanding (“new pieces of evidence”) from which to replicate work. [Crab and Health] | PDD for TH, manuscript on sea cucumber model, 3 theses dissertations on sea cucumber model from UoE, draft crab manuscript on effectiveness of periodic crab closures, ISS paper = Number completed, vs number pending | 7 FIP pre-assessment report published by MSC, PDD for TH, Crab good pratice guide (Kasprzyk and Levrel 2019), peer-reviewed paper on participatory mangrove management (Rakotomahazo et al 2019), MMM5 poster on Ambanja soil carbon, Evaluation of health integration (Singleton et al 2019) Others - Accepted 2019: The role of PHE in the response to cyclone Haruna in Madagascar In review 2019: AAB soil carbon paper | 0 | 0 | 0 | 0 | 0
Source
Blue Ventures' publications log
| Octopus FIP model |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Mangrove crab model |  | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1
| Sea cucumber model |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| VCS model |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Plan Vivo model |  | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| HE integration |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2023 (Year 7) | Assumptions
|  | Original | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 5 | 5
SUSTAINABLE COMMUNITY OWNED MANGROVE FORESTRY MANAGEMENT PLANS IN PLACE | Number of sites with community-led mangrove management plans | Planned | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 5 | 5 | Community benefit from carbon payments or other ecosystem services and uphold management plans which include protection of mangroves, reducing deforestation/degradation - If management plans are in place and followed communities will be clear on the activities that need to be undertaken to acheive improved management
|  | Achieved | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Output Indicator 1.2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2023 (Year 7)
|  | Original | 1 | 1 | 1 | 3 | 3 | 4 | 4 | 5 | 5
| Number of sites with an estimated carbon baseline scenario | Planned | 1 | 1 | 1 | 3 | 3 | 4 | 4 | 5 | 5
|  | Achieved | 0 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Output Indicator 1.3 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2037 (Year 20)
|  | Original | 0 | 0 | 0 | 0 | 0 | 63591 | 129371 | 197303 | 13934696
| Number of carbon credits produced (with a minimum of 50% revenue shared with community) | Planned | 0 | 0 | 0 | 0 | 0 | 31188.6667 | 64056.6667 | 98589 | 5726859
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
IMPACT WEIGHTING % | Site 1 - AAB |  | 0 | 0 | 0 | 0 | 0 | 31188.6667 | 64056.6667 | 98589.3333 | 668605.6667
30 | Site 2 - TH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81833 | 1106811
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2146584
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1804858
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target 2023 (Year 7) | Assumptions
|  | Original | 5 | 5 | 6 | 7 | 8 | 8 | 9 | 9 | 9
MANGROVE FISHERIES IMPROVEMENT PROJECTS IN PLACE | Number of fisheries being monitored | Planned | 5 | 5 | 6 | 7 | 9 | 10 | 11 | 11 | 11 | - Fisheries Improvement Project accrues benefits to fishers (through increased catch rates, price or improved access to market) ensuring buy-in to managment/ improvement project. - FIP includes advisory on habitat management specific to mangroves. - FIP also reinforces local governance structures that may manage both mangroves and fisheries in one management plan.
|  | Achieved | 0 | 5; plus Fisheries Diagnostic started at Site 2 | 8; diagnostic to be completed once sites selected in 2018 | 9 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber)
| Site 2 - TH |  | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish)
| Site 3 - Maha |  | 0 | Fisheries diagnostic started | 3 (Fish, Crab and Shrimp) | 3 (Fish, Crab and Shrimp) | 3 | 3 | 3 | 3 | 3
| Site 4 - Sembilang National Park |  | 0 | 0 | Fisheries diagnostics started | Fisheries diagnostic underway | 1 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 1 (Crab) | 1 | 1 | 1 | 1 | 1
| Output Indicator 2.2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 1 | 1 | 2 | 2 | 3 | 5 | 5 | 6 | 6
| Number of sites trialling/pilot locally relevant fisheries management (eg. periodic closures, gear restrictions) | Planned | 1 | 1 | 2 | 2 | 3 | 5 | 5 | 6 | 6
|  | Achieved | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1
| Output Indicator 2.3 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 0 | 0 | 0 | 2 | 2 | 3 | 4 | 6 | 6
IMPACT WEIGHTING % | Number of local fisheries management plans developed (eg. Agreed harvest rules concerning a fishery or wider management contracts) | Planned | 0 | 0 | 0 | 2 | 2 | 3 | 4 | 6 | 6
25 |  | Achieved | 0 | 2 in development | 1 developed in Site 1 validated by all 36 communities | 2 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7) | Assumptions
|  | Original | 336 | 336; Sea cucumber farming developed in Site 1 | 798.95 | 982.6 | 1762.85 | 2543.1 | 3888.8 | 5234.5 | 5234.5
Implementation of viable new livelihood mechanisms | Number of people engaged in alternative livelihoods | Planned | 336 | 336; Sea cucumber farming developed in Site 1 | 798.95 | 982.6 | 1762.85 | 2543.1 | 3888.8 | 5234.5 | 5234.5 | - New livelihoods provide income to communities - New livelihoods provide sufficient income to reduce reliance on fishing
|  | Achieved | 0 | 292 (8 beekeepers; 78 sea cucumber farmers; 212 seaweed farmers) | 506 | 691 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 8 | 8 | 70 | 80
| Site 2 - TH |  | 328 | 328 | 436 | 611
| Site 3 - Maha |  | 0 | 0 | 0 | 0
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0
| Output Indicator 3.2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023)
|  | Original | 0 | 13776 | 53631.9 | 122690.4 | 281425.2 | 530670 | 783774.6 | 1319094 | 1319094
| Total income generated (Number of people doing the activity [output 3.1] * USD 35 [aim of monthly income generated by alternative livelihoods] * 12 months) * (% of people making agreed profit level from this activity [outcome 3]) | Planned | 0 | 13776 | 53631.9 | 122694.4 | 281425.2 | 530670 | 783774.6 | 1319094 | 1319094
|  | Achieved | 0 | $ 250 (beekeepers); $ 23,853 (seaweed). | 25782 | 116929.6093 | 0 | 0 | 0 | 0 | 0
Source
Aquaculture farmers have a logbook of records of sales. Data are collected at each point of sale and BV digitise it.
| Site 1 - AAB |  | 0 | 0 | 500 | 475.6093
| Site 2 - TH |  | 0 | 13776 | 25282 | 116454
| Site 3 - Maha |  | 0 | 0 | 0 | 0
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0
| Output Indicator 3.3 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 6 | 8 | 9 | 9 | 9 | 9
IMPACT WEIGHTING % | Number of new alternative livelihoods developed by site | Planned | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 6 | 8 | 9 | 9 | 9 | 9
25 |  | Achieved | 0 | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 4 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 1 in development (bee keeping) | 1 in development (bee keeping) | 1 in progress (Bees), 1 in development (SC) | 1 in progress (Bees), 1 in development (SC) | 2 | 2 | 2 | 2 | 2
| Site 2 - TH |  | 2 (SC, SW) | 2 (SC, SW) | 2 in progress (SC, SW), 1 in development (Bees) | 3 (SC, SW, Bees) | 3 | 3 | 3 | 3 | 3
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7) | Assumptions
|  | Original | 1 completed in total | 2 completed 1 started/underway | 3 completed in total | 4 completed in total | 5 completed in total | 6 completed in total | 6 completed in total | 6 completed in total | 6 completed in total
Increased access to family planning services | Needs assessments completed at each site | Planned | 1 completed in total | 2 completed 1 started/underway | 3 completed in total | 4 completed in total | 5 completed in total | 5 completed in total | 5 completed in total | 5 completed in total | 5 completed in total | - By meeting the need for family planning women are more able to manage their own fertility and use additional time/energy etc to engage in projects, livelihoods, income generation etc - By providing alternative livelihoods in conjunction with access to FP women are able to engage in livelihood projects and not enter fishery
|  | Achieved | 0 | 3 completed by end 2017 | 3 completed in total, 1 underway | 4 completed in total | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
| Site 2 - TH |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
| Site 3 - Maha |  | 0 | Started | Started | Completed | Completed | Completed | Completed | Completed | Completed
| Site 4 - Sembilang National Park |  | 0 | 0 | Started | Completed | Completed | Completed | Completed | Completed | Completed
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | Completed | Completed | Completed | Completed | Completed
| Output Indicator 4.2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 8 at Site 2 | 8 at Site 2; Service delivery designed for Site 1 | 19 | 19 | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia
| Number of villages served by community-based health services | Planned | 8 at Site 2 | 8 at Site 2; Service delivery designed for Site 1 | 19 | 19 | 19 to 33 plus Indo | 19 to 33 plus Indo | 19 to 33 plus Indo | 19 to 33 plus Indo | 19 to 33 plus Indo
|  | Achieved | 0 | 8 at Site 2; Service delivery designed for Site 1 | 19 | 25 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | Scoping and partner mapping completed. Programme for delivery designed | 11 | 12 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019
| Site 2 - TH |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Site 3 - Maha |  | 0 | 0 | Needs assessment completed | 5 | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker
| Site 4 - Sembilang National Park |  | 0 | 0 | Needs assessment started | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment
| Output Indicator 4.3 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 2 mobile outreach missions per year (based on Site 2 in 2016); future milestones will be impacted by number of partners and funding available to them. | 2 mobile outreach missions per year; Site 2 outreach missions designed with partners and dependent on partner resources | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations.
IMPACT WEIGHTING % | Number of outreach missions completed by reproductive health partner | Planned | 2 mobile outreach missions per year (based on Site 2 in 2016); future milestones will be impacted by number of partners and funding available to them. | 2 mobile outreach missions per year; Site 2 outreach missions designed with partners and dependent on partner resources | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations.
10 |  | Achieved | 0 | 2 mobile outreach missions per year; Site 2 outreach missions designed with partners and dependent on partner resources | 3 1 in site 1 and 2 in site 2 | 10 total - 4 in site 1, 3 in site 2, 3 in site 3 - site 2 had to cancel the final mission due to a cyclone passing in the area | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 4 | 2 | 2 | 2 | 2 | 2
| Site 2 - TH |  | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2
| Site 3 - Maha |  | 0 | 0 | Partner mapping completed | 3 | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
| Site 4 - Sembilang National Park |  | 0 | 0 | Partner mapping completed | 0 | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7) | Assumptions
|  | Original | 2 | 2 | 3 | 3 | 5 | 5 | 5 | 6 | 6
Organisational and financial structures in place to support 20 year project vision | Organisational capacity - number of relevant community structures (organisational/financial/administrative) in place to support local mangrove and fisheries management | Planned | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | By having clear community led organisational and financial strutures both mangrove and fisheries management plans are supported, and more likely to be sustained in the long term beyond the scope of this funding.
|  | Achieved | 0 | 2 Site 1 Madagascar - 1 Federation officialised to coordinate the mangrove and fisheries management activities of the 11 associations. Site 2 Madagascar - 1 management association in place to manage mangrove and marine conservation in the project area. | 2 Site 1 Madagascar - 1 Federation officialised to coordinate the mangrove and fisheries management activities of the 11 associations. Site 2 Madagascar - 1 management association in place to manage mangrove and marine conservation in the project area. | 2 but discussions underway for establishment in site 3 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 5.2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 0 | 1 | 2 | 2 | 5 | 5 | 5 | 6 | 6
| Monitoring capacity - number of sites where community resource monitoring protocol is in place | Planned | 0 | 1 | 2 | 2 | 4 | 4 | 5 | 5 | 5
|  | Achieved | 0 | Site 2 Madagascar - Protocol and key indicators to be monitored have been defined. Recruitment ongoing and training starting by end of Q4 2017. | 2 CSE being trialled in TH, forest guards officalised in AAB | 3 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Output Indicator 5.3 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 6 | 6
| Enforcement capacity - number of sites where a community-led coastal management law enforcement protocol is in place | Planned | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 5 | 5
|  | Achieved | 0 | Site 2 Madagascar - Enforcement committee and enforcement procedure in place. | 2 Site 2 Madagascar - Enforcement committee and enforcement procedure in place. Forest guards in place in Site 1 Madagascar | 2 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Output Indicator 5.4 |  | Baseline | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Target (2023 Y7)
|  | Original | 0 | 0 | 2 | 2 | 5 | 5 | 5 | 6 | 6
IMPACT WEIGHTING % | Conservation agreements - number of sites with functioning, transparent community conservation agreements | Planned | 0 | 0 | 2 | 2 | 4 | 4 | 5 | 5 | 5
10 |  | Achieved | 0 | No agreements in place yet, although a pilot, based around mangrove reforestation, is being designed at Site 1. | 2 1 signed on mangrove carbon project, a second in development for aquaculture leasing agreements | 3 (Site1 restoration, Site 2 Aquaculture and Carbon project) | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Sembilang National Park |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Site 5 - Kubu Raya |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
Note on B154: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The indicator was updated in 2018, prior to this recent update.

## Simpler template_UPDATED (hidden)
Please refer to the Smart Guide for advice on completing the various fields in the logframe. |  | Need to be standard in way we treat baseline
Smart Guide
PROJECT TITLE | [12 empty] | Source of information
IMPACT | Impact Indicator 1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | 2021 | 2022 | Milestone 2023 (Year 7) | Target 2037 (Year 20)
Mangrove forests and ecosystem services (fisheries etc) protected and restored, preventing carbon emissions and supporting security of livelihoods in coastal communities. | Tonnes of CO2 emissions prevented (KPI 6) | Planned | 0 | Total: 54,620; of which is verified: 0 | Total: 111,493; of which is verified: 0 | Total: 794,734; of which is verified: 0 | Total: 1,473,100; of which is verified: 0 | Total: 2,153,807; of which is verified: 63,594 | Total: 3,709,450; of which is verified: 129,371 | Total: 5,262,036; of which is verified: 197,303 | Total: 5,262,036; of which is verified: 197,303 |  | Business case, sheet Deforestation & carbon, Columns BX-BY
|  | Achieved |  | Total estimated: 24,378; of which verified: 0 | Total estimated 50,475; of which verified: 0
|  | CUMULATIVE!! | Source
Forest change analysis will only be done every 5 years (starting in 2015). So until 2020, the unverified figures will be extrapolations based on estimates of effectiveness on the ground.
| Impact Indicator 2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | 2021 | 2022 | Milestone 2023 (Year 7) | Target 2037 (Year 20)
| Number of forest dependent people (ASSUMPTION: all people we work with are forest dependent) with livelihoods benefits (INCOME GENERATION AND FOOD SECURITY) protected or improved (KPI 3) | Planned | 28300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | 28300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | Improved understanding of livelihood benefits in TH (4542) and measurement criteria/methods for other sites | Improved understanding of livelihoods benefits in AB and TH (29893). Census and baselines in Maha established. | Improved understanding of livelihoods benefits at 3 sites. Census and baselines in Indo established. Number of people estimated: 35,000 | Census and baselines in Indo established. Census and baselines in SE Asia. Number of people estimated: 63,000 | Census and baselines in SE Asia. Number of people estimated: 82,000 | 91659 | 119649
|  | Achieved |  | Baseline intake assessments for alternative livelihood projects developed, and population baselines established across the Vel LMMA (TH) against which project level benefits may be compared. | Baseline intake assessments for alternative livelihood project participants underway. Baseline for Velondriake; HH weekly income MGA/Week or $90.48 PPP; $2.72 (PPP) per person, per day
Source
Activity beneficiary data, local census data where available and reliable, or BV census data where necessary. Integrated social surveys will be carried out at each site every 5 years.
| Site 1 - AAB |  | 0 | 0 | 0 | 25351 | 25351 | 26779 | 26779 | 28287 | 41508
| Site 2 - TH |  | 0 | 0 | 4542 | 4542 | 4542 | 4798 | 4798 | 5068 | 7437
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 5282 | 5579 | 5579 | 5893 | 8647
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 18365 | 18365 | 18814 | 22277
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 7765 | 7765 | 13439 | 15912
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 19677 | 20158 | 23868
| Impact Indicator 3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | Milestone 2023 (Year 7) | Target 2023 (Year 7)
| Extent to which ICF intervention is likely to have a transformational impact (KPI 15): Number of additional sites adopting models tested and proven within this project (outside of 6 sites) | Planned | 27 | 35 | 40 | 57 | 68 | 78 | 89 | 99 | 107
|  | Achieved |  | 38 | 44
Source
BV partner support database and tracking system (figures are cumulative)
| Integrating health model |  | 6 | 10 | 11 | 14 | 16 | 18 | 20 | 22 | 22
Octopus model
| FIP |  | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 4
| Closure |  | 21 | 28 | 32 | 40 | 48 | 55 | 62 | 70 | 78
| Mangrove crab model |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sea cucumber model |  | 0 |  | 0
| VCS model |  | 0 |  | 0
| Plan Vivo model |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Bee keeping model |  | 0 |  | 0
| Homestay model |  | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Impact Indicator 4 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | Milestone 2023 (Year 7) | Target 2023 (Year 7)
| Total number of hectares where deforestation have been avoided (KPI 8) [Note: we have removed degradation from this KPI as it is not possible to measure simply] | Planned | 0 | Total: 193; of which is verified: 0 | Total: 888; of which is verified: 0 | Total: 1366; of which is verified: 0 | Total: 1831; of which is verified: 0 | Total: 2282; of which is verified: 174 | Total: 3152; of which is verified: 343 | Total: 4000; of which is verified: 508 | Total: 4000; of which is verified: 508
|  | Corrected Planned |  | Total: 193; of which is verified: 0 | Total: 380; of which is verified: 0 | Total: 858; of which is verified: 0 | Total: 1323; of which is verified: 0 | Total: 1774; of which is verified: 174 | Total: 2644; of which is verified: 343 | Total: 3492; of which is verified: 508 | Total: 3492; of which is verified: 508
|  | Achieved |  | Esimated Total: 43 (Site 1 & Site 2); of which is verified: 0. Can not include Site 3 yet as work not yet started. | Esimated Total: 84 (Site 1 & Site 2); of which is verified: 0. Can not include Site 3 yet as work still in its infancy.
Source
GIS datsets showing baseline mangrove cover at the start of the intervention and GIS datasets showing current mangrove coverage
| Site 1 - AAB |  | 0 | 43 | 84 | 0 | 0 | 39.74 | 78.8 | 117.17 | 117.17 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 2 - TH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 134.04 | 264.31 | 390.89 | 390.89 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Impact Indicator 5 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | Milestone 2023 (Year 7) | Target 2023 (Year 7)
| Ecosystem services (KPI 10): Difference in mangrove forest ecosystem services income (shoreline protection; pollution abatement; protection from sedimentation) provided by standing mangroves compared to without project scenario. ($/yr) | Planned | 0 | 65340 | 147361 | 268088 | 386398 | 556503 | 811598 | 1061901 | 1061901
|  | Achieved |  | We can only estimate 65,340 at present. | Estimate still at 147,361 updating figures following final site selection and regional/national figures validated
Source
Hectares (Impact Indicator 4) will be used to calculate ES via the model developed in the business plan.
| Site 1 - AAB |  | 0 | 14452 | 46985 | 79274 | 111558 | 144074 | 177296 | 210286 | 210286
| Site 2 - TH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 3 - Maha |  | 0 | 50888 | 100376 | 150896 | 200078 | 247951 | 294544 | 339886 | 339886
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 30334 | 59810 | 133380 | 235464 | 336272 | 336272
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 7584 | 14952 | 31098 | 54373 | 77328 | 77328
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 49921 | 98129 | 98129
OUTCOME | Outcome Indicator 1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | Milestone 2023 (Year 7) | Target 2023 (Year 7) | Assumptions
Sustainable mangrove forestry and fisheries management activities implemented at six sites where coastal communities are supported by alternative livelihoods and improved access to health care, and therefore models for replication are validated. | Ha of mangrove forest area protected or under sustainable local management | Planned | 250 | 5700 | 5700 | 8700 | 8700 | 39100 | 39100 | 89100 | 89100 | Assumption: project would not have happened without Blue Ventures.
|  | Achieved |  | 5700 ha are now protected. 4600 of which are under draft management plans and 1100 of which are secured under Marine Protected Area control. | 6229 ha are now protected. 5199 of which are under ratified management plans and 1100 of which are secured under Marine Protected Area control.
Source
BV GIS datasets containing management plans/areas covered by dina and BV GIS datasets showing current (within 5 years) mangrove coverage
| Site 1 - AAB |  | 0 | 4600 ha secured under draft management plans | 5199 secured under management plans signed by the regional forestry services | 4600 | 4600 | 6000 | 6000 | 6000 | 6000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 2 - TH |  | 250 | 1100 ha secured under MPA protection | 1100 secured under both MPA protection and forestry management legislation | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 3 - Maha |  | 0 | Protection/sustainable management options assessed for Site 3 | Protection/sustainable management options assessed for Site 3 | 3000 | 3000 | 12000 | 12000 | 12000 | 12000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 4 - Indo carbon |  | 0 | Current management/protection status assessed for potential Site 4 | Current management/protection status assessed for Site 4 | 0 | 0 | 10000 | 10000 | 40000 | 40000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 5 - Indo non carbon |  | 0 | Current management/protection status assessed for potential Site 5 | Current management/protection status assessed for potential Site 5 | 0 | 0 | 5000 | 5000 | 10000 | 10000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 6 - SE Asia carbon |  | 0 | 0 | Current management/protection status assessed for potential Site 6 | 0 | 0 | 5000 | 5000 | 20000 | 20000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Outcome Indicator 2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019 Y3) | 2020 | Milestone 2 (2021 Y5) | 2022 | 2023 | Target (2023 Y7)
| Number of sites implicated in Fisheries management including but not limited to Fisheries Improvement Projects (registered or actions plans being implemented) | Planned | 0 | 0 | 1 | 2 | 2 | 5 | 5 | 6 | 6
|  | Achieved |  | 0 | 2
Source
Blue Ventures village activity log and FIP action documents
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Outcome Indicator 3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019 Y3) | 2020 | Milestone 2 (2021) | 2022 | 2023 | Target (2023 Y7)
| % of people making agreed model profit from alternative activity | Planned | 10% in Site 2 | 10% in Site 2 | 6.6667 | 16.6667 | 30 | 46.6667 | 46.6667 | 60 | 60
|  | Achieved |  | 10% in Site 2 | First sales due in October 2018 all figures to be updated with final sales data
Source
Blue Ventures farmers log and sales data
| Site 1 - AAB |  | 0 | 0 | 0.0027612 | 20 | 40 | 60 | 60 | 60 | 60
| Site 2 - TH |  | 10.67% | 10 | 10.2 | 40 | 60 | 60 | 60 | 60 | 60
| Site 3 - Maha |  | 0 | 0 | 0 | 20 | 40 | 60 | 60 | 60 | 60
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 20 | 20 | 60 | 60 | 60 | 60
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 10 | 20 | 20 | 60 | 60
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 10 | 20 | 20 | 60 | 60
| Outcome Indicator 4 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
| Unitended pregnancies averted NOTE: we can't provide a target for this output as it depends on the number of voluntary family planning users and their free choice of contraceptive methods | Planned | 258 unintended pregnancies averted in 2016 / 4 = 64 unintended pregnancies averted for the 8 communities with CHWs in 2016 at Site 2. | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site
|  | Achieved |  | The data for this outcome will be collected every two years – first milestone is therefore in 2018. | 1270 - these figures are as of end Sept 2018, final year figures
Source
Blue Ventures data: Number and types of contracptives provided and calculated using Marie Stopes Impact 2 Calculations for number of unintended pregnancies averted
| Site 1 - AAB |  | 0 | 75 | 110
| Site 2 - TH |  | 258 unintended pregnancies averted in 2016 / 4 = 64 unintended pregnancies averted for the 8 communities with CHWs in 2016 at Site 2. | 625 | 1160
| Site 3 - Maha |  | 0 | 0 | 0
| Site 4 - Indo carbon |  | 0 | 0 | 0
| Site 5 - Indo non carbon |  | 0 | 0 | 0
| Site 6 - SE Asia carbon |  | 0 | 0 | 0
| Outcome Indicator 5 |  | Baseline | 2017 | Milestone 1 (2018, Y2) | 2019 | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target 2023 (Year 7)
| Number of new pieces of evidence (per year) for individual conservation models (eg. crab fishery closure model, Plan Vivo model) | Planned | 0 | 2 | 2 | 2 | 5 | 4 | 5 | 5 | 5
|  | Achieved |  | Results from the models have been analysed and we have additional understanding (“new pieces of evidence”) from which to replicate work. [Crab and Health] | PDD for TH, manuscript on sea cucumber model, 3 theses dissertations on sea cucumber model from UoE, draft crab manuscript on effectiveness of periodic crab closures, ISS paper = Number completed, vs number pending
Source
Blue Ventures' publications log
| Octopus FIP model |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Mangrove crab model |  | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1
| Sea cucumber model |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| VCS model |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Plan Vivo model |  | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
0
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target 2023 (Year 7) | Assumptions
SUSTAINABLE COMMUNITY OWNED MANGROVE FORESTRY MANAGEMENT PLANS IN PLACE | Number of sites with community-led mangrove management plans | Planned | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 6 | 6 | Community benefit from carbon payments or other ecosystem services and uphold management plans which include protection of mangroves, reducing deforestation/degradation - If management plans are in place and followed communities will be clear on the activities that need to be undertaken to acheive improved management
|  | Achieved |  | 2 | 2
Source
| Site 1 - AAB |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 1.2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target 2023 (Year 7)
| Number of sites with an estimated carbon baseline scenario | Planned | 1 | 1 | 1 | 3 | 3 | 4 | 4 | 5 | 5
|  | Achieved |  | 1 | 1
Source
| Site 1 - AAB |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 1.3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | 2021 | 2022 | Milestone 2023 (Year 7) | Target 2037 (Year 20)
| Number of carbon credits produced (with a minimum of 50% revenue shared with community) | Planned | 0 | 0 | 0 | 0 | 0 | 63591 | 129371 | 197303.3333 | 13934695.6667
|  | Achieved |  | 0 | 0
Source
IMPACT WEIGHTING % | Site 1 - AAB |  | 0 | 0 | 0 | 0 | 0 | 31188.6667 | 64056.6667 | 98589.3333 | 668605.6667
30 | Site 2 - TH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 32402.3333 | 65314.3333 | 98714 | 543248
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9749890.3333
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2972951.6667
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target 2023 (Year 7) | Assumptions
MANGROVE FISHERIES IMPROVEMENT PROJECTS IN PLACE | Number of fisheries being monitored | Planned | 5 | 5 | 6 | 7 | 9 | 10 | 11 | 11 | 11 | - Fisheries Improvement Project accrues benefits to fishers (through increased catch rates, price or improved access to market) ensuring buy-in to managment/ improvement project. - FIP includes advisory on habitat management specific to mangroves. - FIP also reinforces local governance structures that may manage both mangroves and fisheries in one management plan.
|  | Achieved |  | 5; plus Fisheries Diagnostic started at Site 2 | 8; diagnostic to be completed once sites selected in 2018
Source
| Site 1 - AAB |  | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber)
| Site 2 - TH |  | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish)
| Site 3 - Maha |  | 0 | Fisheries diagnostic started | 3 (Octopus, Crab and Shrimp) | 3 | 3 | 3 | 3 | 3 | 3
| Site 4 - Indo carbon |  | 0 | 0 | Fisheries diagnostics started | 1 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | Fisheries diagnostics started | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | Fisheries diagnostic started | 1 | 1 | 1
| Output Indicator 2.2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target (2023 Y7)
| Number of sites trialling/pilot locally relevant fisheries management (eg. periodic closures, gear restrictions) | Planned | 1 | 1 | 2 | 2 | 3 | 5 | 5 | 6 | 6
|  | Achieved |  | 1 | 2
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 2.3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target (2023 Y7)
IMPACT WEIGHTING % | Number of local fisheries management plans developed (eg. Agreed harvest rules concerning a fishery or wider management contracts) | Planned | 0 | 0 | 0 | 2 | 2 | 3 | 4 | 6 | 6
25 |  | Achieved |  | 2 in development | 1 developed in Site 1 validated by all 36 communities
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2017 | Milestone 1 (2018 Y2) | 2019 | 2020 | Milestone 2 (2021 Y5) | 2022 | 2023 | Target (2023 Y7) | Assumptions
Implementation of viable new livelihood mechanisms | Number of people engaged in alternative livelihoods | Planned | 336 | 336; Sea cucumber farming developed in Site 1 | 799 | 983 | 1763 | 2543 | 3889 | 5235 | 5235 | - New livelihoods provide income to communities - New livelihoods provide sufficient income to reduce reliance on fishing
|  | Achieved |  | 292 (8 beekeepers; 78 sea cucumber farmers; 212 seaweed farmers) | 506
Source
| Site 1 - AAB |  | 8 | 8 | 70 | 64 | 160 | 256 | 512 | 768 | 768
| Site 2 - TH |  | 328 | 328 | 436 | 478 | 592 | 706 | 834 | 962 | 962
| Site 3 - Maha |  | 0 | 0 | 0 | 256.95 | 407.425 | 557.9 | 720.925 | 883.95 | 883.95
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 183.65 | 275.475 | 367.3 | 654 | 940.7 | 940.7
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 131.18 | 262.36 | 467.155 | 671.95 | 671.95
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 196.77 | 393.54 | 700.72 | 1007.9 | 1007.9
| Output Indicator 3.2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | Milestone 2 (2021 Y5) | 2022 | 2023 | Target (date)
| Total income generated (Number of people doing the activity [output 3.1] * USD 35 [aim of monthly income generated by alternative livelihoods] * 12 months) * (% of people making agreed profit level from this activity [outcome 3]) | Planned | 0 | 13776 | 53631.9 | 122694.6 | 281429.4 | 530670 | 783774.6 | 1319094 | 1319094
|  | Achieved |  | $ 250 (beekeepers); $ 23,853 (seaweed). | 25782
Source
Aquaculture farmers have a logbook of records of sales. Data are collected at each point of sale and BV digitise it.
| Site 1 - AAB |  | 0 | 0 | 500 | 5376 | 26880 | 64512 | 129024 | 193536 | 193536
| Site 2 - TH |  | 0 | 13776 | 25282 | 80304 | 149184 | 177912 | 210168 | 242424 | 242424
| Site 3 - Maha |  | 0 | 0 | 0 | 21583.8 | 68447.4 | 140590.8 | 181673.1 | 222755.4 | 222755.4
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 15426.6 | 23139.9 | 92559.6 | 164808 | 237056.4 | 237056.4
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 5509.56 | 22038.24 | 39241.02 | 169331.4 | 169331.4
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 8264.34 | 33057.36 | 58860.48 | 253990.8 | 253990.8
| Output Indicator 3.3 |  | Baseline | 2017 | 2018 | Milestone 1 (Y3 2019) | 2020 | Milestone 2 (Y5 2021) | 2022 | 2023 | Target (2023 Y7)
IMPACT WEIGHTING % | Number of new alternative livelihoods developed by site | Planned | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 6 | 8 | 9 | 9 | 9 | 9
25 |  | Achieved |  | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2
Source
| Site 1 - AAB |  | 1 in development (bee keeping) | 1 in development (bee keeping) | 1 in progress (Bees), 1 in development (SC) | 2 (Bees, SC) | 2 | 2 | 2 | 2 | 2
| Site 2 - TH |  | 2 (SC, SW) | 2 (SC, SW) | 2 in progress (SC, SW), 1 in development (Bees) | 3 (SC, SW, Bees) | 3 | 3 | 3 | 3 | 3
| Site 3 - Maha |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7) | Assumptions
Increased access to family planning services | Needs assessments completed at each site | Planned | 1 completed in total | 2 completed 1 started/underway | 3 completed in total | 4 completed in total | 5 completed in total | 6 completed in total | 6 completed in total | 6 completed in total | 6 completed in total | - By meeting the need for family planning women are more able to manage their own fertility and use additional time/energy etc to engage in projects, livelihoods, income generation etc - By providing alternative livelihoods in conjunction with access to FP women are able to engage in livelihood projects and not enter fishery
|  | Achieved |  | 3 completed by end 2017 | 3 completed in total, 1 underway
Source
| Site 1 - AAB |  | 0 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
| Site 2 - TH |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
| Site 3 - Maha |  | 0 | Started | Completed | Completed | Completed | Completed | Completed | Completed | Completed
| Site 4 - Indo carbon |  | 0 | 0 | Started | Completed | Completed | Completed | Completed | Completed | Completed
| Site 5 - Indo non carbon |  | 0 | 0 | 0 |  | Completed | Completed | Completed | Completed | Completed
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 |  | 0 | Completed | Completed | Completed | Completed
| Output Indicator 4.2 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
| Number of villages served by community-based health services | Planned | 8 at Site 2 | 8 at Site 2; Service delivery designed for Site 1 | 19 | 19 | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia
|  | Achieved |  | 8 at Site 2; Service delivery designed for Site 1 | 19
Source
| Site 1 - AAB |  | 0 | Scoping and partner mapping completed. Programme for delivery designed | 11 | 2 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019
| Site 2 - TH |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Site 3 - Maha |  | 0 | 0 | Needs assessment completed | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker
| Site 4 - Indo carbon |  | 0 | 0 | Needs assessment started | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | Needs assessment completed | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment
| Output Indicator 4.3 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
IMPACT WEIGHTING % | Number of outreach missions completed by reproductive health partner | Planned | 2 mobile outreach missions per year (based on Site 2 in 2016); future milestones will be impacted by number of partners and funding available to them. | 2 mobile outreach missions per year; Site 2 outreach missions designed with partners and dependent on partner resources | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations.
10 |  | Achieved |  | 2 mobile outreach missions per year; Site 2 outreach missions designed with partners and dependent on partner resources | 3 1 in site 1 and 2 in site 2
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2
| Site 2 - TH |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Site 3 - Maha |  | 0 | 0 | Partner mapping completed | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
| Site 4 - Indo carbon |  | 0 | 0 | Partner mapping completed | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
| Site 5 - Indo non carbon |  | 0 | 0 |  | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
| Site 6 - SE Asia carbon |  | 0 | 0 |  | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7) | Assumptions
Organisational and financial structures in place to support 20 year project vision | Organisational capacity - number of relevant community structures (organisational/financial/administrative) in place to support local mangrove and fisheries management | Planned | 2 | 2 | 3 | 3 | 5 | 5 | 5 | 6 | 6 | By having clear community led organisational and financial strutures both mangrove and fisheries management plans are supported, and more likely to be sustained in the long term beyond the scope of this funding.
|  | Achieved |  | 2 Site 1 Madagascar - 1 Federation officialised to coordinate the mangrove and fisheries management activities of the 11 associations. Site 2 Madagascar - 1 management association in place to manage mangrove and marine conservation in the project area. | 2 Site 1 Madagascar - 1 Federation officialised to coordinate the mangrove and fisheries management activities of the 11 associations. Site 2 Madagascar - 1 management association in place to manage mangrove and marine conservation in the project area.
Source
| Site 1 - AAB |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 5.2 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
| Monitoring capacity - number of sites where community resource monitoring protocol is in place | Planned | 0 | 1 | 2 | 2 | 5 | 5 | 5 | 6 | 6
|  | Achieved |  | Site 2 Madagascar - Protocol and key indicators to be monitored have been defined. Recruitment ongoing and training starting by end of Q4 2017. | 2 CSE being trialled in TH, forest guards officalised in AAB
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 5.3 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
| Enforcement capacity - number of sites where a community-led coastal management law enforcement protocol is in place | Planned | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 6 | 6
|  | Achieved |  | Site 2 Madagascar - Enforcement committee and enforcement procedure in place. | 2 Site 2 Madagascar - Enforcement committee and enforcement procedure in place. Forest guards in place in Site 1 Madagascar
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 5.4 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
IMPACT WEIGHTING % | Conservation agreements - number of sites with functioning, transparent community conservation agreements | Planned | 0 | 0 | 2 | 2 | 5 | 5 | 5 | 6 | 6
10 |  | Achieved |  | No agreements in place yet, although a pilot, based around mangrove reforestation, is being designed at Site 1. | 2 1 signed on mangrove carbon project, a second in development for aquaculture leasing agreements
Source
| Site 1 - AAB |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1

## Clean version UPDATED (hidden)
PROJECT TITLE | Defra ICF Blue Forests Project | [11 empty] | Source of information
IMPACT | Impact Indicator 1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | 2021 | 2022 | Milestone 2023 (Year 7) | Target 2037 (Year 20)
Mangrove forests and ecosystem services (fisheries etc) protected and restored, preventing carbon emissions and supporting security of livelihoods in coastal communities. | Tonnes of CO2 emissions prevented (KPI 6) | Planned | 0 | Total: 54,620; of which is verified: 0 | Total: 111,493; of which is verified: 0 | Total: 794,734; of which is verified: 0 | Total: 1,473,100; of which is verified: 0 | Total: 2,153,807; of which is verified: 63,594 | Total: 3,709,450; of which is verified: 129,371 | Total: 5,262,036; of which is verified: 197,303 | Total: 5,262,036; of which is verified: 197,303 |  | Business case, sheet Deforestation & carbon, Columns BX-BY
|  | Achieved | 0 | Total estimated: 24,378; of which verified: 0 | Total estimated 50,475; of which verified: 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
Forest change analysis will only be done every 5 years (starting in 2015). So until 2020, the unverified figures will be extrapolations based on estimates of effectiveness on the ground.
| Impact Indicator 2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | 2021 | 2022 | Milestone 2023 (Year 7) | Target 2037 (Year 20)
| Number of forest dependent people (ASSUMPTION: all people we work with are forest dependent) with livelihoods benefits (INCOME GENERATION AND FOOD SECURITY) protected or improved (KPI 3) | Planned | 28300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | 28300 people currently directly & indirectly involved in project at sites 1 & 2. Work ongoing to understand livelihoods benefits baseline. | Improved understanding of livelihood benefits in TH (4542) and measurement criteria/methods for other sites | Improved understanding of livelihoods benefits in AB and TH (29893). Census and baselines in Maha established. | Improved understanding of livelihoods benefits at 3 sites. Census and baselines in Indo established. Number of people estimated: 35,000 | Census and baselines in Indo established. Census and baselines in SE Asia. Number of people estimated: 63,000 | Census and baselines in SE Asia. Number of people estimated: 82,000 | 91659 | 119649
|  | Achieved | 0 | Baseline intake assessments for alternative livelihood projects developed, and population baselines established across the Vel LMMA (TH) against which project level benefits may be compared. | Baseline intake assessments for alternative livelihood project participants underway. Baseline for Velondriake; HH weekly income MGA/Week or $90.48 PPP; $2.72 (PPP) per person, per day | 0 | 0 | 0 | 0 | 0 | 0
Source
Activity beneficiary data, local census data where available and reliable, or BV census data where necessary. Integrated social surveys will be carried out at each site every 5 years.
| Site 1 - AAB |  | 0 | 0 | 0 | 25351 | 25351 | 26779 | 26779 | 28287 | 41508
| Site 2 - TH |  | 0 | 0 | 4542 | 4542 | 4542 | 4798 | 4798 | 5068 | 7437
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 5282 | 5579 | 5579 | 5893 | 8647
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 18365 | 18365 | 18814 | 22277
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 7765 | 7765 | 13439 | 15912
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 19677 | 20158 | 23868
| Impact Indicator 3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | Milestone 2023 (Year 7) | Target 2023 (Year 7)
| Extent to which ICF intervention is likely to have a transformational impact (KPI 15): Number of additional sites adopting models tested and proved within this project (outside of 6 sites) | Planned | 27 | 35 | 40 | 57 | 68 | 78 | 89 | 99 | 107
|  | Achieved | 0 | 38 | 44 | 0 | 0 | 0 | 0 | 0 | 0
Source
BV partner support database and tracking system
| PHE model |  | 6 | 10 | 11 | 14 | 16 | 18 | 20 | 22 | 22
| Octopus model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FIP |  | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 4
| Closure |  | 21 | 28 | 32 | 40 | 48 | 55 | 62 | 70 | 78
| Mangrove crab model |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sea cucumber model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| VCS model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan Vivo model |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Bee keeping model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Homestay model |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Impact Indicator 4 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | Milestone 2023 (Year 7) | Target 2023 (Year 7)
| Total number of hectares where deforestation have been avoided (KPI 8) [Note: we have removed degradation from this KPI as it is not possible to measure simply] | Planned | 0 | Total: 193; of which is verified: 0 | Total: 888; of which is verified: 0 | Total: 1366; of which is verified: 0 | Total: 1831; of which is verified: 0 | Total: 2282; of which is verified: 174 | Total: 3152; of which is verified: 343 | Total: 4000; of which is verified: 508 | Total: 4000; of which is verified: 508
|  | Corrected Planned | 0 | Total: 193; of which is verified: 0 | Total: 380; of which is verified: 0 | Total: 858; of which is verified: 0 | Total: 1323; of which is verified: 0 | Total: 1774; of which is verified: 174 | Total: 2644; of which is verified: 343 | Total: 3492; of which is verified: 508 | Total: 3492; of which is verified: 508
|  | Achieved | 0 | Esimated Total: 43 (Site 1 & Site 2); of which is verified: 0. Can not include Site 3 yet as work not yet started. | Esimated Total: 84 (Site 1 & Site 2); of which is verified: 0. Can not include Site 3 yet as work still in its infancy. | 0 | 0 | 0 | 0 | 0 | 0
Source
GIS datsets showing baseline mangrove cover at the start of the intervention and GIS datasets showing current mangrove coverage
| Site 1 - AAB |  | 0 | 43 | 84 | 0 | 0 | 39.74 | 78.8 | 117.17 | 117.17 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 2 - TH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 134.04 | 264.31 | 390.89 | 390.89 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Business case, sheet Deforestation & carbon, line 12 Columns U-AD
| Impact Indicator 5 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | Milestone 2023 (Year 7) | Target 2023 (Year 7)
| Ecosystem services (KPI 10): Difference in mangrove forest ecosystem services income (shoreline protection; pollution abatement; protection from sedimentation) provided by standing mangroves compared to without project scenario. ($/yr) | Planned | 0 | 65340 | 147361 | 268088 | 386398 | 556503 | 811598 | 1061901 | 1061901
|  | Achieved | 0 | We can only estimate 65,340 at present. | Estimate still at 147,361 updating figures following final site selection and regional/national figures validated | 0 | 0 | 0 | 0 | 0 | 0
Source
Hectares (Impact Indicator 4) will be used to calculate ES via the model developed in the business plan.
| Site 1 - AAB |  | 0 | 14452 | 46985 | 79274 | 111558 | 144074 | 177296 | 210286 | 210286
| Site 2 - TH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 3 - Maha |  | 0 | 50888 | 100376 | 150896 | 200078 | 247951 | 294544 | 339886 | 339886
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 30334 | 59810 | 133380 | 235464 | 336272 | 336272
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 7584 | 14952 | 31098 | 54373 | 77328 | 77328
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 49921 | 98129 | 98129
OUTCOME | Outcome Indicator 1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | Milestone 2023 (Year 7) | Target 2023 (Year 7) | Assumptions
Sustainable mangrove forestry and fisheries management activities implemented at six sites where coastal communities are supported by alternative livelihoods and improved access to health care, and therefore models for replication are validated. | Ha of mangrove forest area protected or under sustainable local management | Planned | 250 | 5700 | 5700 | 8700 | 8700 | 39100 | 39100 | 89100 | 89100 | Assumption: project would not have happened without Blue Ventures.
|  | Achieved | 0 | 5700 ha are now protected. 4600 of which are under draft management plans and 1100 of which are secured under Marine Protected Area control. | 6229 ha are now protected. 5199 of which are under ratified management plans and 1100 of which are secured under Marine Protected Area control. | 0 | 0 | 0 | 0 | 0 | 0
Source
BV GIS datasets containing management plans/areas covered by dina and BV GIS datasets showing current (within 5 years) mangrove coverage
| Site 1 - AAB |  | 0 | 4600 ha secured under draft management plans | 5199 secured under management plans signed by the regional forestry services | 4600 | 4600 | 6000 | 6000 | 6000 | 6000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 2 - TH |  | 250 | 1100 ha secured under MPA protection | 1100 secured under both MPA protection and forestry management legislation | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 3 - Maha |  | 0 | Protection/sustainable management options assessed for Site 3 | Protection/sustainable management options assessed for Site 3 | 3000 | 3000 | 12000 | 12000 | 12000 | 12000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 4 - Indo carbon |  | 0 | Current management/protection status assessed for potential Site 4 | Current management/protection status assessed for Site 4 | 0 | 0 | 10000 | 10000 | 40000 | 40000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 5 - Indo non carbon |  | 0 | Current management/protection status assessed for potential Site 5 | Current management/protection status assessed for potential Site 5 | 0 | 0 | 5000 | 5000 | 10000 | 10000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Site 6 - SE Asia carbon |  | 0 | 0 | Current management/protection status assessed for potential Site 6 | 0 | 0 | 5000 | 5000 | 20000 | 20000 |  | Business case, sheet Deforestation & carbon, line 12 Columns K-S
| Outcome Indicator 2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019 Y3) | 2020 | Milestone 2 (2021 Y5) | 2022 | 2023 | Target (2023 Y7)
| Number of sites implicated in Fisheries management including but not limited to Fisheries Improvement Projects (registered or actions plans being implemented) | Planned | 0 | 0 | 1 | 2 | 2 | 5 | 5 | 6 | 6
|  | Achieved | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Source
Blue Ventures village activity log and FIP action documents
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Outcome Indicator 3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019 Y3) | 2020 | Milestone 2 (2021) | 2022 | 2023 | Target (2023 Y7)
| % of people making agreed model profit from alternative activity | Planned | 10% in Site 2 | 10% in Site 2 | 6.6667 | 16.6667 | 30 | 46.6667 | 46.6667 | 60 | 60
|  | Achieved | 0 | 10% in Site 2 | First sales due in October 2018 all figures to be updated with final sales data | 0 | 0 | 0 | 0 | 0 | 0
Source
Blue Ventures farmers log and sales data
| Site 1 - AAB |  | 0 | 0 | 0.0027612 | 20 | 40 | 60 | 60 | 60 | 60
| Site 2 - TH |  | 10.67% | 10 | 10.2 | 40 | 60 | 60 | 60 | 60 | 60
| Site 3 - Maha |  | 0 | 0 | 0 | 20 | 40 | 60 | 60 | 60 | 60
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 20 | 20 | 60 | 60 | 60 | 60
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 10 | 20 | 20 | 60 | 60
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 10 | 20 | 20 | 60 | 60
| Outcome Indicator 4 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
| Unitended pregnancies averted NOTE: we can't provide a target for this output as it depends on the number of voluntary family planning users and their free choice of contraceptive methods | Planned | 258 unintended pregnancies averted in 2016 / 4 = 64 unintended pregnancies averted for the 8 communities with CHWs in 2016 at Site 2. | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site | No target set. Value caculated each year for each site
|  | Achieved | 0 | The data for this outcome will be collected every two years – first milestone is therefore in 2018. | 1270 - these figures are as of end Sept 2018, final year figures | 0 | 0 | 0 | 0 | 0 | 0
Source
Blue Ventures data: Number and types of contracptives provided and calculated using Marie Stopes Impact 2 Calculations for number of unintended pregnancies averted
| Site 1 - AAB |  | 0 | 75 | 110 |  | 0 | 0 | 0 | 0 | 0
| Site 2 - TH |  | 258 unintended pregnancies averted in 2016 / 4 = 64 unintended pregnancies averted for the 8 communities with CHWs in 2016 at Site 2. | 625 | 1160 | 0 | 0 | 0 | 0 | 0 | 0
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Outcome Indicator 5 |  | Baseline | 2017 | Milestone 1 (2018, Y2) | 2019 | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target 2023 (Year 7)
| Number of new pieces of evidence (per year) for individual conservation models (eg. crab fishery closure model, Plan Vivo model) | Planned | 0 | 2 | 2 | 2 | 5 | 4 | 5 | 5 | 5
|  | Achieved | 0 | Results from the models have been analysed and we have additional understanding (“new pieces of evidence”) from which to replicate work. [Crab and Health] | PDD for TH, manuscript on sea cucumber model, 3 theses dissertations on sea cucumber model from UoE, draft crab manuscript on effectiveness of periodic crab closures, ISS paper = Number completed, vs number pending | 0 | 0 | 0 | 0 | 0 | 0
Source
Blue Ventures' publications log
| Octopus FIP model |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Mangrove crab model |  | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1
| Sea cucumber model |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| VCS model |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Plan Vivo model |  | 0 | 0 | 1 | #REF! | 1 | 1 | 1 | 1 | 1
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target 2023 (Year 7) | Assumptions
SUSTAINABLE COMMUNITY OWNED MANGROVE FORESTRY MANAGEMENT PLANS IN PLACE | Number of sites with community-led mangrove management plans | Planned | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 6 | 6 | Community benefit from carbon payments or other ecosystem services and uphold management plans which include protection of mangroves, reducing deforestation/degradation - If management plans are in place and followed communities will be clear on the activities that need to be undertaken to acheive improved management
|  | Achieved | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 1.2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target 2023 (Year 7)
| Number of sites with an estimated carbon baseline scenario | Planned | 1 | 1 | 1 | 3 | 3 | 4 | 4 | 5 | 5
|  | Achieved | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 1.3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | 2021 | 2022 | Milestone 2023 (Year 7) | Target 2037 (Year 20)
| Number of carbon credits produced (with a minimum of 50% revenue shared with community) | Planned | 0 | 0 | 0 | 0 | 0 | 63591 | 129371 | 197303.3333 | 13934695.6667
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
IMPACT WEIGHTING % | Site 1 - AAB |  | 0 | 0 | 0 | 0 | 0 | 31188.6667 | 64056.6667 | 98589.3333 | 668605.6667
30 | Site 2 - TH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 32402.3333 | 65314.3333 | 98714 | 543248
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9749890.3333
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2972951.6667
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target 2023 (Year 7) | Assumptions
MANGROVE FISHERIES IMPROVEMENT PROJECTS IN PLACE | Number of fisheries being monitored | Planned | 5 | 5 | 6 | 7 | 9 | 10 | 11 | 11 | 11 | - Fisheries Improvement Project accrues benefits to fishers (through increased catch rates, price or improved access to market) ensuring buy-in to managment/ improvement project. - FIP includes advisory on habitat management specific to mangroves. - FIP also reinforces local governance structures that may manage both mangroves and fisheries in one management plan.
|  | Achieved | 0 | 5; plus Fisheries Diagnostic started at Site 2 | 8; diagnostic to be completed once sites selected in 2018 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber) | 3 (Fish, Crab and Sea cucumber)
| Site 2 - TH |  | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish) | 2 (Octopus and Fish)
| Site 3 - Maha |  | 0 | Fisheries diagnostic started | 3 (Octopus, Crab and Shrimp) | 3 | 3 | 3 | 3 | 3 | 3
| Site 4 - Indo carbon |  | 0 | 0 | Fisheries diagnostics started | 1 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | Fisheries diagnostics started | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | Fisheries diagnostic started | 1 | 1 | 1
| Output Indicator 2.2 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target (2023 Y7)
| Number of sites trialling/pilot locally relevant fisheries management (eg. periodic closures, gear restrictions) | Planned | 1 | 1 | 2 | 2 | 3 | 5 | 5 | 6 | 6
|  | Achieved | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 2.3 |  | Baseline | 2017 | 2018 | Milestone 1 (2019, Y3) | 2020 | Milestone 2 (2021, Y5) | 2022 | 2023 | Target (2023 Y7)
IMPACT WEIGHTING % | Number of local fisheries management plans developed (eg. Agreed harvest rules concerning a fishery or wider management contracts) | Planned | 0 | 0 | 0 | 2 | 2 | 3 | 4 | 6 | 6
25 |  | Achieved | 0 | 2 in development | 1 developed in Site 1 validated by all 36 communities | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2017 | Milestone 1 (2018 Y2) | 2019 | 2020 | Milestone 2 (2021 Y5) | 2022 | 2023 | Target (2023 Y7) | Assumptions
Implementation of viable new livelihood mechanisms | Number of people engaged in alternative livelihoods | Planned | 336 | 336; Sea cucumber farming developed in Site 1 | 799 | 983 | 1763 | 2543 | 3889 | 5235 | 5235 | - New livelihoods provide income to communities - New livelihoods provide sufficient income to reduce reliance on fishing
|  | Achieved | 0 | 292 (8 beekeepers; 78 sea cucumber farmers; 212 seaweed farmers) | 506 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 8 | 8 | 70 | 64 | 160 | 256 | 512 | 768 | 768
| Site 2 - TH |  | 328 | 328 | 436 | 478 | 592 | 706 | 834 | 962 | 962
| Site 3 - Maha |  | 0 | 0 | 0 | 256.95 | 407.425 | 557.9 | 720.925 | 883.95 | 883.95
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 183.65 | 275.475 | 367.3 | 654 | 940.7 | 940.7
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 131.18 | 262.36 | 467.155 | 671.95 | 671.95
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 196.77 | 393.54 | 700.72 | 1007.9 | 1007.9
| Output Indicator 3.2 |  | Baseline | 2017 | 2018 | 2019 | 2020 | Milestone 2 (2021 Y5) | 2022 | 2023 | Target (date)
| Total income generated (Number of people doing the activity [output 3.1] * USD 35 [aim of monthly income generated by alternative livelihoods] * 12 months) * (% of people making agreed profit level from this activity [outcome 3]) | Planned | 0 | 13776 | 53631.9 | 122694.6 | 281429.4 | 530670 | 783774.6 | 1319094 | 1319094
|  | Achieved | 0 | $ 250 (beekeepers); $ 23,853 (seaweed). | 25782 | 0 | 0 | 0 | 0 | 0 | 0
Source
Aquaculture farmers have a logbook of records of sales. Data are collected at each point of sale and BV digitise it.
| Site 1 - AAB |  | 0 | 0 | 500 | 5376 | 26880 | 64512 | 129024 | 193536 | 193536
| Site 2 - TH |  | 0 | 13776 | 25282 | 80304 | 149184 | 177912 | 210168 | 242424 | 242424
| Site 3 - Maha |  | 0 | 0 | 0 | 21583.8 | 68447.4 | 140590.8 | 181673.1 | 222755.4 | 222755.4
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 15426.6 | 23139.9 | 92559.6 | 164808 | 237056.4 | 237056.4
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 5509.56 | 22038.24 | 39241.02 | 169331.4 | 169331.4
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 8264.34 | 33057.36 | 58860.48 | 253990.8 | 253990.8
| Output Indicator 3.3 |  | Baseline | 2017 | 2018 | Milestone 1 (Y3 2019) | 2020 | Milestone 2 (Y5 2021) | 2022 | 2023 | Target (2023 Y7)
IMPACT WEIGHTING % | Number of new alternative livelihoods developed by site | Planned | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 6 | 8 | 9 | 9 | 9 | 9
25 |  | Achieved | 0 | 1 in development at Site 1, 2 in progress at Site 2 | 1 in development at Site 1, 2 in progress at Site 2 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 1 in development (bee keeping) | 1 in development (bee keeping) | 1 in progress (Bees), 1 in development (SC) | 2 (Bees, SC) | 2 | 2 | 2 | 2 | 2
| Site 2 - TH |  | 2 (SC, SW) | 2 (SC, SW) | 2 in progress (SC, SW), 1 in development (Bees) | 3 (SC, SW, Bees) | 3 | 3 | 3 | 3 | 3
| Site 3 - Maha |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7) | Assumptions
Increased access to family planning services | Needs assessments completed at each site | Planned | 1 completed in total | 2 completed 1 started/underway | 3 completed in total | 4 completed in total | 5 completed in total | 6 completed in total | 6 completed in total | 6 completed in total | 6 completed in total | - By meeting the need for family planning women are more able to manage their own fertility and use additional time/energy etc to engage in projects, livelihoods, income generation etc - By providing alternative livelihoods in conjunction with access to FP women are able to engage in livelihood projects and not enter fishery
|  | Achieved | 0 | 3 completed by end 2017 | 3 completed in total, 1 underway | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
| Site 2 - TH |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
| Site 3 - Maha |  | 0 | Started | Completed | Completed | Completed | Completed | Completed | Completed | Completed
| Site 4 - Indo carbon |  | 0 | 0 | Started | Completed | Completed | Completed | Completed | Completed | Completed
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | Completed | Completed | Completed | Completed | Completed
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | Completed | Completed | Completed | Completed
| Output Indicator 4.2 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
| Number of villages served by community-based health services | Planned | 8 at Site 2 | 8 at Site 2; Service delivery designed for Site 1 | 19 | 19 | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia | 19 to 33 plus Indo and SE Asia
|  | Achieved | 0 | 8 at Site 2; Service delivery designed for Site 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | Scoping and partner mapping completed. Programme for delivery designed | 11 | 2 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019 | 2; this could jump to 14 if we were to take on Mahefa Miarka CHWs after their program ends in 2019
| Site 2 - TH |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Site 3 - Maha |  | 0 | 0 | Needs assessment completed | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker | 9; assuming that each village involved in scoping report would support a community health worker
| Site 4 - Indo carbon |  | 0 | 0 | Needs assessment started | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | Needs assessment completed | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment | Community health worker or health service delivery point supported and providing access to health services in target communities as defined by needs assessment
| Output Indicator 4.3 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
IMPACT WEIGHTING % | Number of outreach missions completed by reproductive health partner | Planned | 2 mobile outreach missions per year (based on Site 2 in 2016); future milestones will be impacted by number of partners and funding available to them. | 2 mobile outreach missions per year; Site 2 outreach missions designed with partners and dependent on partner resources | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations. | 4 mobile outreach missions per year across 2 sites plus new sites. All targets dependent on resources of partner organizations.
10 |  | Achieved | 0 | 2 mobile outreach missions per year; Site 2 outreach missions designed with partners and dependent on partner resources | 3 1 in site 1 and 2 in site 2 | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2
| Site 2 - TH |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Site 3 - Maha |  | 0 | 0 | Partner mapping completed | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
| Site 4 - Indo carbon |  | 0 | 0 | Partner mapping completed | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations | Outreach and programme plans coordinated as best as possible to maximize the number of mobile outreach missions that can be supported by partner reproductive health organizations
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7) | Assumptions
Organisational and financial structures in place to support 20 year project vision | Organisational capacity - number of relevant community structures (organisational/financial/administrative) in place to support local mangrove and fisheries management | Planned | 2 | 2 | 3 | 3 | 5 | 5 | 5 | 6 | 6 | By having clear community led organisational and financial strutures both mangrove and fisheries management plans are supported, and more likely to be sustained in the long term beyond the scope of this funding.
|  | Achieved | 0 | 2 Site 1 Madagascar - 1 Federation officialised to coordinate the mangrove and fisheries management activities of the 11 associations. Site 2 Madagascar - 1 management association in place to manage mangrove and marine conservation in the project area. | 2 Site 1 Madagascar - 1 Federation officialised to coordinate the mangrove and fisheries management activities of the 11 associations. Site 2 Madagascar - 1 management association in place to manage mangrove and marine conservation in the project area. | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 5.2 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
| Monitoring capacity - number of sites where community resource monitoring protocol is in place | Planned | 0 | 1 | 2 | 2 | 5 | 5 | 5 | 6 | 6
|  | Achieved | 0 | Site 2 Madagascar - Protocol and key indicators to be monitored have been defined. Recruitment ongoing and training starting by end of Q4 2017. | 2 CSE being trialled in TH, forest guards officalised in AAB | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 5.3 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
| Enforcement capacity - number of sites where a community-led coastal management law enforcement protocol is in place | Planned | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 6 | 6
|  | Achieved | 0 | Site 2 Madagascar - Enforcement committee and enforcement procedure in place. | 2 Site 2 Madagascar - Enforcement committee and enforcement procedure in place. Forest guards in place in Site 1 Madagascar | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Output Indicator 5.4 |  | Baseline | 2017 | Milestone 1 (Y2 2018) | 2019 | Milestone 2 (Y4 2020) | 2021 | 2022 | 2023 | Target (2023 Y7)
IMPACT WEIGHTING % | Conservation agreements - number of sites with functioning, transparent community conservation agreements | Planned | 0 | 0 | 2 | 2 | 5 | 5 | 5 | 6 | 6
10 |  | Achieved | 0 | No agreements in place yet, although a pilot, based around mangrove reforestation, is being designed at Site 1. | 2 1 signed on mangrove carbon project, a second in development for aquaculture leasing agreements | 0 | 0 | 0 | 0 | 0 | 0
Source
| Site 1 - AAB |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Site 2 - TH |  | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1
| Site 3 - Maha |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 4 - Indo carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 5 - Indo non carbon |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Site 6 - SE Asia carbon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1

## Output 1.3 calcs (hidden)
| Emission reductions due to avoided deforestation | [11 empty] | Emission removals due to reforestation
Year | Madagascar 1 (TH) | V? | Madagascar 2 (AAB) | V? | Madagascar 3 (BST) | V? | Indo 1 (carbon) | V? | Indo 2 (non-carbon) | V? | SE Asia Low income (carbon) | V? | Madagascar 1 (TH) | V? | Madagascar 2 (AAB) | V? | Madagascar 3 (BST) | V? | Indo 1 (carbon) | V? | Indo 2 (non-carbon) | V? | SE Asia Low income (carbon) | V?
Y1 | 0 | N | 6649 | N | 8248 | N | 0 | N | 0 | N | 0 | N | 0 | N | 0 | N | 0 | N | 0 | N | 0 | N | 0 | N | 14897
Y2 | 0 | Y | 6793 | N | 8394 | N | 0 | N | 0 | N | 0 | N | 0 | Y | 324 | N | 0 | N | 0 | N | 0 | N | 0 | N | 15511
Y3 | 0 | Y | 6935 | N | 8534 | N | 136167 | N | 34042 | N | 0 | N | 0 | Y | 647 | N | 12 | N | 0 | N | 0 | N | 0 | N | 186337
Y4 | 0 | Y | 7075 | N | 8670 | N | 134615 | N | 33654 | N | 0 | N | 0 | Y | 971 | N | 25 | N | 0 | N | 0 | N | 0 | N | 185010
Y5 | 0 | Y | 7211 | Y | 8800 | Y | 133081 | N | 33270 | N | 0 | N | 0 | Y | 1295 | Y | 37 | Y | 1628 | N | 326 | N | 0 | N | 185648
Y6 | 0 | Y | 7345 | Y | 8926 | Y | 263247 | N | 65812 | N | 73363 | N | 0 | Y | 1619 | Y | 50 | Y | 3255 | N | 651 | N | 0 | N | 424268
Y7 | 0 | Y | 7476 | Y | 9047 | Y | 261853 | N | 65463 | N | 71730 | N | 0 | Y | 1942 | Y | 62 | Y | 4883 | N | 977 | N | 0 | N | 423433
Y8 | 0 | Y | 7604 | Y | 9163 | Y | 260468 | N | 65117 | N | 70133 | N | 0 | Y | 2266 | Y | 75 | Y | 6510 | N | 1302 | N | 405 | N | 423043
Y9 | 0 | Y | 7729 | Y | 9275 | Y | 259091 | Y | 64773 | N | 139087 | N | 0 | Y | 2590 | Y | 87 | Y | 8138 | Y | 1628 | N | 809 | N | 493207
Y10 | 0 | Y | 7852 | Y | 9382 | Y | 257722 | Y | 64431 | N | 137132 | N | 0 | Y | 2914 | Y | 99 | Y | 9765 | Y | 1953 | N | 1214 | N | 492464
Y11 | 0 | Y | 7973 | Y | 9485 | Y | 256362 | Y | 64090 | N | 135213 | N | 0 | Y | 3237 | Y | 112 | Y | 11393 | Y | 2279 | N | 1619 | N | 491763
Y12 | 0 | Y | 7915 | Y | 9392 | Y | 240761 | Y | 60190 | N | 124133 | Y | 0 | Y | 3561 | Y | 124 | Y | 13020 | Y | 2604 | N | 2023 | Y | 463723
Y13 | 0 | Y | 7861 | Y | 9307 | Y | 225821 | Y | 56455 | N | 113580 | Y | 0 | Y | 3885 | Y | 137 | Y | 14648 | Y | 2930 | N | 2428 | Y | 437052
Y14 | 0 | Y | 7811 | Y | 9228 | Y | 211523 | Y | 52881 | N | 103536 | Y | 0 | Y | 4209 | Y | 149 | Y | 16275 | Y | 3255 | N | 2833 | Y | 411700
Y15 | 0 | Y | 7764 | Y | 9156 | Y | 197851 | Y | 49463 | N | 93985 | Y | 0 | Y | 4532 | Y | 162 | Y | 17903 | Y | 3581 | N | 3237 | Y | 387634
Y16 | 0 | Y | 7721 | Y | 9090 | Y | 184787 | Y | 46197 | N | 84910 | Y | 0 | Y | 4856 | Y | 174 | Y | 19530 | Y | 3906 | N | 3642 | Y | 364813
Y17 | 0 | Y | 7681 | Y | 9031 | Y | 172313 | Y | 43078 | N | 76296 | Y | 0 | Y | 5180 | Y | 186 | Y | 21158 | Y | 4232 | N | 4047 | Y | 343202
Y18 | 0 | Y | 7645 | Y | 8977 | Y | 160414 | Y | 40103 | N | 68128 | Y | 0 | Y | 5503 | Y | 199 | Y | 22785 | Y | 4557 | N | 4451 | Y | 322762
Y19 | 0 | Y | 7611 | Y | 8928 | Y | 149073 | Y | 37268 | N | 60390 | Y | 0 | Y | 5827 | Y | 211 | Y | 24413 | Y | 4883 | N | 4856 | Y | 303460
Y20 | 0 | Y | 7581 | Y | 8886 | Y | 138275 | Y | 34569 | N | 53069 | Y | 0 | Y | 6151 | Y | 224 | Y | 26040 | Y | 5208 | N | 5261 | Y | 285264
| Emission reductions due to avoided deforestation | [11 empty] | Emission removals due to reforestation
| TH |  | AAB |  | MHJ |  | Indo 1 |  | Indo 2 |  | 3rd country |  | TH |  | AAB |  | MHJ |  | Indo 1 |  | Indo 2 |  | 3rd country
Y1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y5 | 0 |  | 7211 |  | 8800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1295 |  | 37 |  | 0 |  | 0 |  | 0
Y6 | 0 |  | 7345 |  | 8926 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1619 |  | 50 |  | 0 |  | 0 |  | 0
Y7 | 0 |  | 7476 |  | 9047 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1942 |  | 62 |  | 0 |  | 0 |  | 0
Y8 | 0 |  | 7604 |  | 9163 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2266 |  | 75 |  | 0 |  | 0 |  | 0
Y9 | 0 |  | 7729 |  | 9275 |  | 259091 |  | 0 |  | 0 |  | 0 |  | 2590 |  | 87 |  | 8138 |  | 0 |  | 0
Y10 | 0 |  | 7852 |  | 9382 |  | 257722 |  | 0 |  | 0 |  | 0 |  | 2914 |  | 99 |  | 9765 |  | 0 |  | 0
Y11 | 0 |  | 7973 |  | 9485 |  | 256362 |  | 0 |  | 0 |  | 0 |  | 3237 |  | 112 |  | 11393 |  | 0 |  | 0
Y12 | 0 |  | 7915 |  | 9392 |  | 240761 |  | 0 |  | 124133 |  | 0 |  | 3561 |  | 124 |  | 13020 |  | 0 |  | 2023
Y13 | 0 |  | 7861 |  | 9307 |  | 225821 |  | 0 |  | 113580 |  | 0 |  | 3885 |  | 137 |  | 14648 |  | 0 |  | 2428
Y14 | 0 |  | 7811 |  | 9228 |  | 211523 |  | 0 |  | 103536 |  | 0 |  | 4209 |  | 149 |  | 16275 |  | 0 |  | 2833
Y15 | 0 |  | 7764 |  | 9156 |  | 197851 |  | 0 |  | 93985 |  | 0 |  | 4532 |  | 162 |  | 17903 |  | 0 |  | 3237
Y16 | 0 |  | 7721 |  | 9090 |  | 184787 |  | 0 |  | 84910 |  | 0 |  | 4856 |  | 174 |  | 19530 |  | 0 |  | 3642
Y17 | 0 |  | 7681 |  | 9031 |  | 172313 |  | 0 |  | 76296 |  | 0 |  | 5180 |  | 186 |  | 21158 |  | 0 |  | 4047
Y18 | 0 |  | 7645 |  | 8977 |  | 160414 |  | 0 |  | 68128 |  | 0 |  | 5503 |  | 199 |  | 22785 |  | 0 |  | 4451
Y19 | 0 |  | 7611 |  | 8928 |  | 149073 |  | 0 |  | 60390 |  | 0 |  | 5827 |  | 211 |  | 24413 |  | 0 |  | 4856
Y20 | 0 |  | 7581 |  | 8886 |  | 138275 |  | 0 |  | 53069 |  | 0 |  | 6151 |  | 224 |  | 26040 |  | 0 |  | 5261
TOTAL C PER YEAR
| TH |  | AAB |  | MHJ |  | Indo 1 |  | Indo 2 |  | 3rd country
Y1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y5 | 0 |  | 8506 |  | 8837 |  | 0 |  | 0 |  | 0
Y6 | 0 |  | 8964 |  | 8976 |  | 0 |  | 0 |  | 0
Y7 | 0 |  | 9418 |  | 9109 |  | 0 |  | 0 |  | 0
Y8 | 0 |  | 9870 |  | 9238 |  | 0 |  | 0 |  | 0
Y9 | 0 |  | 10319 |  | 9362 |  | 267229 |  | 0 |  | 0
Y10 | 0 |  | 10766 |  | 9481 |  | 267487 |  | 0 |  | 0
Y11 | 0 |  | 11210 |  | 9597 |  | 267755 |  | 0 |  | 0
Y12 | 0 |  | 11476 |  | 9516 |  | 253781 |  | 0 |  | 126156
Y13 | 0 |  | 11746 |  | 9444 |  | 240469 |  | 0 |  | 116008
Y14 | 0 |  | 12020 |  | 9377 |  | 227798 |  | 0 |  | 106369
Y15 | 0 |  | 12296 |  | 9318 |  | 215754 |  | 0 |  | 97222
Y16 | 0 |  | 12577 |  | 9264 |  | 204317 |  | 0 |  | 88552
Y17 | 0 |  | 12861 |  | 9217 |  | 193471 |  | 0 |  | 80343
Y18 | 0 |  | 13148 |  | 9176 |  | 183199 |  | 0 |  | 72579
Y19 | 0 |  | 13438 |  | 9139 |  | 173486 |  | 0 |  | 65246
Y20 | 0 |  | 13732 |  | 9110 |  | 164315 |  | 0 |  | 58330
TOTAL CO2 or CREDITS PER YEAR
| TH |  | AAB |  | MHJ |  | Indo 1 |  | Indo 2 |  | 3rd country |  | Total (check)
Y1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y5 | 0 |  | 31188.6667 |  | 32402.3333 |  | 0 |  | 0 |  | 0 |  | 63591
Y6 | 0 |  | 32868 |  | 32912 |  | 0 |  | 0 |  | 0 |  | 65780
Y7 | 0 |  | 34532.6667 |  | 33399.6667 |  | 0 |  | 0 |  | 0 |  | 67932.3333
Y8 | 0 |  | 36190 |  | 33872.6667 |  | 0 |  | 0 |  | 0 |  | 70062.6667
Y9 | 0 |  | 37836.3333 |  | 34327.3333 |  | 979839.6667 |  | 0 |  | 0 |  | 1052003.3333
Y10 | 0 |  | 39475.3333 |  | 34763.6667 |  | 980785.6667 |  | 0 |  | 0 |  | 1055024.6667
Y11 | 0 |  | 41103.3333 |  | 35189 |  | 981768.3333 |  | 0 |  | 0 |  | 1058060.6667
Y12 | 0 |  | 42078.6667 |  | 34892 |  | 930530.3333 |  | 0 |  | 462572 |  | 1470073
Y13 | 0 |  | 43068.6667 |  | 34628 |  | 881719.6667 |  | 0 |  | 425362.6667 |  | 1384779
Y14 | 0 |  | 44073.3333 |  | 34382.3333 |  | 835259.3333 |  | 0 |  | 390019.6667 |  | 1303734.6667
Y15 | 0 |  | 45085.3333 |  | 34166 |  | 791098 |  | 0 |  | 356480.6667 |  | 1226830
Y16 | 0 |  | 46115.6667 |  | 33968 |  | 749162.3333 |  | 0 |  | 324690.6667 |  | 1153936.6667
Y17 | 0 |  | 47157 |  | 33795.6667 |  | 709393.6667 |  | 0 |  | 294591 |  | 1084937.3333
Y18 | 0 |  | 48209.3333 |  | 33645.3333 |  | 671729.6667 |  | 0 |  | 266123 |  | 1019707.3333
Y19 | 0 |  | 49272.6667 |  | 33509.6667 |  | 636115.3333 |  | 0 |  | 239235.3333 |  | 958133
Y20 | 0 |  | 50350.6667 |  | 33403.3333 |  | 602488.3333 |  | 0 |  | 213876.6667 |  | 900119
|  |  | 668605.6667 | 0 | 543257 | 0 | 9749890.3333 | 0 | 0 | 0 | 2972951.6667

## Impact Ind 2 calcs (hidden)
Forest ES | If we were to recreate your calcs, using the same studies, but for this actual project - what inputs do we need?
Inputs required
Ha of mangroves protected | is total ha of mangrove protected? Or just those avoided deforestation?
Aquaculture?
Income (Impact Indicator 2) | Tahiry Honko | AAB | Belo sur Tsiribihina | Indo (carbon) | Indo (non-carbon) | SE Asia (carbon)
Estimate population effected: | 4300 | 24000 | 5000 | 17500 | 12500 | 18750
Check indicators in outputs and add together
Plus another meaurement based around ha of forest saved - this can be done through exisitng data, assumptions and or our own census |  | Talk to Jen & Leah
Population estimtes/beneficiaries | Baseline | 2019 | 2021 | 2023 | Milestone 20 (2037)
Site 1 - AAB | 24000 | 25351 | 26779 | 28287 | 41508
Site 2 - TH | 4300 | 4542 | 4798 | 5068 | 7437
Site 3 - Maha | 5000 | 5282 | 5579 | 5893 | 8647
Site 4 - Indo carbon | 17500 | 17927 | 18365 | 18814 | 22277
Site 5 - Indo non carbon | 12500 | 12805 | 13118 | 13439 | 15912
Site 6 - SE Asia carbon | 18750 | 19208 | 19677 | 20158 | 23868
Site | Tahiry Honko | AAB | Belo sur Tsiribihina | Indo (carbon) | Indo (non-carbon) | SE Asia (carbon) | Total # | Units | Assumptions | Source
VIllages affected | 10 | 26 | 10 | 14 | 10 | 15 | 85 | villages | - PV: 10 - AA: 26 - BST: 11 | - BV relations with partner communities
Population affected | 4300 | 24000 | 5000 | 17500 | 12500 | 18750 | 82050 | people | - PV: 4,300 - AA: 24,000 - BST: 5,000 | - BV census; - Commune level population data (Ministry of Health) - BV scoping missions in southeast Asia - Kabupaten Berau, 2015. Rencana Pengelolaan, Taman Pesisir Kepulauan Derawan, Kabupaten Berau. Dinas Kelautan dan Perikanan Kabupaten Berau, 2015
Population growth rate | 2.777 | 2.777 | 2.777 | 1.214 | 1.214 | 1.214 |  | NA | - Assumed rural population growth rate mirrors national average (highly conservative) | - Population rates derived from total population data, population source United Nations Population Division, World Population Prospects
2018 | 4419 | 24666 | 5139 | 17712 | 12652 | 18978 | 83567
2019 | 4542 | 25351 | 5282 | 17927 | 12805 | 19208 | 85116
2020 | 4668 | 26055 | 5428 | 18145 | 12961 | 19441 | 86699
2021 | 4798 | 26779 | 5579 | 18365 | 13118 | 19677 | 88317
2022 | 4931 | 27523 | 5734 | 18588 | 13277 | 19916 | 89970
2023 | 5068 | 28287 | 5893 | 18814 | 13439 | 20158 | 91659
2024 | 5209 | 29073 | 6057 | 19042 | 13602 | 20403 | 93385 | people | - Assumed non change in 2015 rate of population growth in 7 year term of project
2025 | 5353 | 29880 | 6225 | 19274 | 13767 | 20650 | 95149
2026 | 5502 | 30710 | 6398 | 19508 | 13934 | 20901 | 96952
2027 | 5655 | 31562 | 6576 | 19744 | 14103 | 21155 | 98795
2028 | 5812 | 32439 | 6758 | 19984 | 14274 | 21412 | 100679
2029 | 5973 | 33340 | 6946 | 20227 | 14448 | 21671 | 102605
2030 | 6139 | 34266 | 7139 | 20472 | 14623 | 21935 | 104573
2031 | 6310 | 35217 | 7337 | 20721 | 14801 | 22201 | 106586
2032 | 6485 | 36195 | 7541 | 20972 | 14980 | 22470 | 108644
2033 | 6665 | 37200 | 7750 | 21227 | 15162 | 22743 | 110748
2034 | 6850 | 38233 | 7965 | 21485 | 15346 | 23019 | 112899
2035 | 7040 | 39295 | 8186 | 21745 | 15532 | 23299 | 115099
2036 | 7236 | 40386 | 8414 | 22009 | 15721 | 23582 | 117348
2037 | 7437 | 41508 | 8647 | 22277 | 15912 | 23868 | 119648 | people | - Assumed non change in 2015 rate of population growth in 20 year term of project
Note on A1: +garth@blueventures.org Please could you help us think about what are the inputs we would need to do the Forest ES for our own project. Keeping it simple and assuming we use the same assumptions for eg. storm protection in your sheet. _Assigned to Garth Cripps_ -Frances Humber Just reminding you about this -Frances Humber
Note on B19: +leah@blueventures.org +garth@blueventures.org Having briefly chatted to both of you, I'm not sure if we have any population numbers as an idea within sites 4-6 when doing the business case. If not, then I think we need to make some assumptions, so we work out targets for some of our output indicators (eg. number of people trained in alt livelihoods). -Frances Humber Hi +fran@blueventures.org and +garth@blueventures.org. I had a think about this and knew we'd calculated this somewhere for the business case. Found it: ICF_# people reached.xlsx on drive (sorry, can't seem to link it from my tablet). Have copied and adapted these numbers here. -Leah Glass

## Impact Ind 4 calcs (hidden)
with project' avoided deforestation (ha)
Year | Madagascar 1 (TH) | Madagascar 2 (AAB) | Madagascar 3 (BST) | Indo 1 (carbon) | Indo 2 (non-carbon) | WIO East Africa (carbon) | SE Asia Lower middle-income (non-carbon) | SE Asia Low income (carbon) | Total
Y1 | 0 | 42.6 | 150 | 0 | 0 | 0 | 0 | 0 | 192.6
Y2 | 0 | 41.87 | 145.88 | 0 | 0 | 0 | 0 | 0 | 187.75
Y3 | 0 | 41.15 | 141.84 | 235.68 | 58.92 | 0 | 0 | 0 | 477.59
Y4 | 0 | 40.44 | 137.9 | 229.01 | 57.25 | 0 | 0 | 0 | 464.6
Y5 | 0 | 39.74 | 134.04 | 222.48 | 55.62 | 0 | 0 | 0 | 451.89
Y6 | 0 | 39.06 | 130.27 | 444.02 | 111 | 0 | 0 | 145.54 | 869.88
Y7 | 0 | 38.37 | 126.58 | 434.1 | 108.52 | 0 | 0 | 140.55 | 848.12
UPDATED VERIFIED: | Using column AE of the business case (Verified total) and the formulas in this column to separate out by site
Year | Madagascar 1 (TH) | Madagascar 2 (AAB) | Madagascar 3 (BST) | Indo 1 (carbon) | Indo 2 (non-carbon) | WIO East Africa (carbon) | SE Asia Lower middle-income (non-carbon) | SE Asia Low income (carbon) | Total | Cumulative:
| Year 2 onwards | Year 5 onwards | Year 5 onwards | Year 9 onwards | Never | Never | Never | Year 12 onwards
Y1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Y2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Y3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Y4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Y5 | 0 | 39.74 | 134.04 | 0 | 0 | 0 | 0 | 0 | 173.78 | 173.78
Y6 | 0 | 39.06 | 130.27 | 0 | 0 | 0 | 0 | 0 | 169.33 | 343.11
Y7 | 0 | 38.37 | 126.58 | 0 | 0 | 0 | 0 | 0 | 164.95 | 508.06
UPDATED UNVERIFIED: | Using columns V-AC of the business case
Year | Madagascar 1 (TH) | Madagascar 2 (AAB) | Madagascar 3 (BST) | Indo 1 (carbon) | Indo 2 (non-carbon) | WIO East Africa (carbon) | SE Asia Lower middle-income (non-carbon) | SE Asia Low income (carbon) | Total | Cumulative: | Correct cumulative
| Year 2 onwards | Year 5 onwards | Year 5 onwards | Year 9 onwards | Never | Never | Never | Year 12 onwards
Y1 | 0 | 42.6 | 150 | 0 | 0 | 0 | 0 | 0 | 192.6 | 192.6 | 192.6
Y2 | 0 | 41.87 | 145.88 | 0 | 0 | 0 | 0 | 0 | 187.75 | 888.41 | 380.35
Y3 | 0 | 41.15 | 141.84 | 235.68 | 58.92 | 0 | 0 | 0 | 477.59 | 1366 | 857.94
Y4 | 0 | 40.44 | 137.9 | 229.01 | 57.25 | 0 | 0 | 0 | 464.6 | 1830.6 | 1322.54
Y5 | 0 | 39.74 | 134.04 | 222.48 | 55.62 | 0 | 0 | 0 | 451.88 | 2282.48 | 1774.42
Y6 | 0 | 39.06 | 130.27 | 444.02 | 111 | 0 | 0 | 145.54 | 869.89 | 3152.37 | 2644.31
Y7 | 0 | 38.37 | 126.58 | 434.1 | 108.52 | 0 | 0 | 140.55 | 848.12 | 4000.49 | 3492.43 | Makes little difference to end cumulative impact.
| SUM: | 283.23 | 966.51 | 1565.29 | 391.31 | 0 | 0 | 286.09 | 3492.43
192.6
187.75
477.59
464.6
451.89
869.88
848.12
Note on K29: Error in equation due to copy and paste. Adds 508 ha to all subsequent totals. -Leah Glass

## Impact Ind 5 calcs (hidden)
With project forest ES annual income excluding aquaculture support
Year | Madagascar 1 (TH) | Madagascar 2 (AAB) | Madagascar 3 (BST) | Indo 1 (carbon) | Indo 2 (non-carbon) | WIO East Africa (carbon) | SE Asia Lower middle-income (non-carbon) | SE Asia Low income (carbon)
Y1 | 31044 | 2025323 | 4040468 | 5059848 | 1264962 | 0 | 0 | 6714568
Y2 | 31013 | 2033289 | 4010164 | 4972818 | 1243205 | 0 | 0 | 6572219
Y3 | 30982 | 2041307 | 3981784 | 4917620 | 1229405 | 0 | 0 | 6432888
Y4 | 30951 | 2049374 | 3953630 | 4863034 | 1215759 | 0 | 0 | 6296511
Y5 | 30920 | 2057492 | 3925699 | 4830506 | 1206554 | 0 | 0 | 6163025
Y6 | 30889 | 2065660 | 3897991 | 4827913 | 1204833 | 0 | 0 | 6082289
Y7 | 30858 | 2073877 | 3870503 | 4825439 | 1203142 | 0 | 0 | 6002611
With project aquaculture support income
Year | Madagascar 1 (TH) | Madagascar 2 (AAB) | Madagascar 3 (BST) | Indo 1 (carbon) | Indo 2 (non-carbon) | WIO East Africa (carbon) | SE Asia Lower middle-income (non-carbon) | SE Asia Low income (carbon)
Y1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Y2 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0
Y3 | 0 | 470 | 704 | 0 | 0 | 0 | 0 | 0
Y4 | 0 | 939 | 1409 | 0 | 0 | 0 | 0 | 0
Y5 | 0 | 1879 | 2113 | 23483 | 4697 | 0 | 0 | 0
Y6 | 0 | 3757 | 2818 | 46966 | 9393 | 0 | 0 | 0
Y7 | 0 | 5636 | 3522 | 70449 | 14090 | 0 | 0 | 0
| TOTAL | would need to use figures below in "Forest ES BAU vs. WP"
Year | Madagascar 1 (TH) | Madagascar 2 (AAB) | Madagascar 3 (BST) | Indo 1 (carbon) | Indo 2 (non-carbon) | WIO East Africa (carbon) | SE Asia Lower middle-income (non-carbon) | SE Asia Low income (carbon)
Y1 | 31044 | 2025323 | 4040468 | 5059848 | 1264962 | 0 | 0 | 6714568
Y2 | 31013 | 2033524 | 4010164 | 4972818 | 1243205 | 0 | 0 | 6572219
Y3 | 30982 | 2041777 | 3982488 | 4917620 | 1229405 | 0 | 0 | 6432888
Y4 | 30951 | 2050313 | 3955039 | 4863034 | 1215759 | 0 | 0 | 6296511
Y5 | 30920 | 2059371 | 3927812 | 4853989 | 1211251 | 0 | 0 | 6163025
Y6 | 30889 | 2069417 | 3900809 | 4874879 | 1214226 | 0 | 0 | 6082289
Y7 | 30858 | 2079513 | 3874025 | 4895888 | 1217232 | 0 | 0 | 6002611
Forest ES BAU vs. WP
| Madagascar 1 (TH) | Madagascar 2 (AAB) | Madagascar 3 (BST) | Indo 1 (carbon) | Indo 2 (non-carbon) | WIO East Africa (carbon) | SE Asia Lower middle-income (non-carbon) | SE Asia Low income (carbon)
Y1 | 0 | 14452 | 50888 | 0 | 0 | 0 | 0 | 0
Y2 | 0 | 46985 | 100376 | 0 | 0 | 0 | 0 | 0
Y3 | 0 | 79274 | 150896 | 30334 | 7584 | 0 | 0 | 0
Y4 | 0 | 111558 | 200078 | 59810 | 14952 | 0 | 0 | 0
Y5 | 0 | 144074 | 247951 | 133380 | 31098 | 0 | 0 | 0
Y6 | 0 | 177296 | 294544 | 235464 | 54373 | 0 | 0 | 49921
Y7 | 0 | 210286 | 339886 | 336272 | 77328 | 0 | 0 | 98129
Notes from Garth chat | What assumptions has he made and which does he think can be updated through simple study? Which ones does he think need to be updated/completed?
Is there anything that wasn't included (eg. non monetary ecosystem services)?
| Just pulled storm and erosion from studies |  | TEEB report
Could be more studies that came out but could do more in depth lit searches
| Could do something more focussed but not best use of time. If extra research focus on fisheries & aqua |  | eg. storm protection is cost of rebuilding homes
Could derive ha of mangrove benefit on fisheries & aquaculture more likely

## Aqua calcs(old) (hidden)
|  | Baseline | Milestone 1 (2018 Y2) | Milestone 2 (2021 Y5) | Target (2023 Y7)
Number of people engaged in alternative livelihoods | Planned
Achieved
Source
Site 1 - AAB |  | 8 bee keepers; 0 SC | 64 SC (1 Module) | 256 SC (4 modules) | 768 SC (12 modules) | 6
|  | 8 | 64 | 256 | 768
Site 2 - TH |  | TH: SW 264: SC 64 | TH: 350 SW; 128 SC | TH: 450 SW; 256SC | TH: 450 SW; 512 SC | Separate SW and SC
|  | 328 | 478 | 706 | 962 | Total # of producers
Site 3 - Maha |  | 0 | 256.95 | 557.9 | 883.95
Site 4 - Indo carbon |  | 0 | 0 | 918.25 | 1881.4
Site 5 - Indo non carbon |  | 0 | 0 | 655.9 | 1343.9
Site 6 - SE Asia carbon |  | 0 | 0 | 983.85 | 2015.8
Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Total income generated | Planned
Achieved
Site 1 - AAB |  | 0 | 6912 | 27648 |  | total number of farmers * 35 usd(average income (SC 40usd/m and SW 30usd) *12 months in a year * 60% as the estimated number who will be making a profit
Site 2 - TH
Site 3 - Maha
Site 4 - Indo carbon
Site 5 - Indo non carbon
Site 6 - SE Asia carbon
Output Indicator 3.3 |  | Baseline | Milestone 1 (Y3 2019) | Milestone 2 (Y5 2021) | Target (2023 Y7)
% of people making agreed model profit from alternative activity | Planned | X% in Site 2 | 43.3333 | 61.6667 | 80
Achieved
Source
Site 1 - AAB |  | 0 | 90 | 90 | 90
Site 2 - TH |  |  | 90 | 90 | 90
Site 3 - Maha |  | 0 | 60 | 90 | 90
Site 4 - Indo carbon |  | 0 | 20 | 60 | 90
Site 5 - Indo non carbon |  | 0 | 0 | 20 | 60
Site 6 - SE Asia carbon |  | 0 | 0 | 20 | 60