## 2023 LogFrame
Please refer to the Smart Guide for advice on completing the various fields in the logframe
Smart Guide
PROJECT TITLE | LAND DEGRADATION NEUTRALITY FUND
IMPACT | Impact Indicator 1 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
Land Degradation Neutrality is achieved in line with the SDGs, while the flow of private finance towards SLM projects and practices increases substantially. This drives transformational change in a number of industries in countries across the developing world. | ICF KPI 15: transformational change (Extent to which ICF intervention is likely to lead to transformational change | Planned |  |  |  |  | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | ICF KPI 15: Transformational change, methodology is ongoing. It will use sub-indicators embedded in this Logical Framework
|  | Achieved | 0 | 2020: 1; 2021: 1; 2022: 1; 2023: 2
Source
All sources Mirova unless specified
| Impact Indicator 2 |  | Baseline | [14 empty] | Methodology and Assumptions
| Contribution to climate change, adaptation and relevant SDGs | Planned | [15 empty] | Qualitative indicator for evaluation of LDN progress towards stated Fund objectives. Quantitative values for be used for certain parts of this indicator - eg. carbon storage, area under SLM (as proxy for adaptation). However, the overall indicator would be a narrative one.
|  | Achieved |  | 2020: N/A; 2021: N/A; 2022: N/A
Source
| Impact Indicator 3 |  | Baseline | [14 empty] | Methodology and Assumptions
| Wider progress towards Land Degradation Neutrality | Planned | [15 empty] | Ha, difference between land degradation levels from Year 0 of project. Assumes that LDN Fund contributes towards achievement of land degradation neutrality.
|  | Achieved |  | 2020: N/A; 2021: N/A; 2022: N/A
Source
UNCCD
Finance | Impact Indicator 4 |  | Baseline | [14 empty] | Methodology and Assumptions
| Level of market-level private investment in Sustainable Land Management | Planned | [15 empty] | £, cumulative. Assumption that the LDN Fund is successful in proving the concept of healthy financial returns from SLM investments. Assumption that this success incentivises increased investment in the sector. Likely to be trend data as opposed to exact monetary figures.
|  | Achieved |  | 2020: N/A; 2021: N/A; 2022: N/A
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
The LDN Fund contributes to achieving Land Degradation Neutrality by increasing private investment in sustainable land management, proofing the concept of positive financial returns from sustainability projects, mainstreaming SLM practices in a number of industries and geographies, and sharing best practice with public and private partners across the developing world. | Area of reforestation | Planned |  |  |  | 62500 | 75000 | 90000 | 105000 | 117500 | 132500 | 145000 | 160000 | 175000 | 175000 | 175000 | 175000 | Ha, cumulative. Assumption that a) deforestation and forest degradation prevented by the project is not fully displaced into nearby areas; LDN-funded projects successfully prevent deforestation through SLM
|  | Achieved | 28795 | 2020: 32506.75; 2021: 45509; 2022: 47085.73; 2023: 65792
Source
| Outcome Indicator 2 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Tonnes of CO2e emissions avoided [KPI 6] | Planned |  |  |  | 1000000 | 2000000 | 3000000 | 4500000 | 6000000 | 8500000 | 11500000 | 14000000 | 16000000 | 18500000 | 21000000 | 25000000 | Tonnes, cumulative.
|  | Achieved | 0 | 2020: 144000; 2021: 514000; 2022: 1075000; 2023: 1687122
|  |  | Source | [15 empty] | But what about France, etc.?
| Outcome Indicator 3 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Private finance leveraged by the LDN Fund [KPI 11] | Planned (Fund) |  |  |  | 128079834 | 128079834 | 128079834 | 128079834 | 128079834 | 128079834 | 128079834 | 128079834 | 128079834 | 128079834 | 128079834 | 128079834 | USD, cumulative. Past figures and targets have been converted to USD Assumes that the private finance leveraged into projects funded by LDN is additional.
|  | Achieved (fund) | 48277434 | 2020: 102087434; 2021: 128079834; 2022: 128079834
|  | Planned (co-investment) |  |  |  | 100000000 | 130000000 | 135000000 | 140000000 | 145000000 | 150000000 | 155000000 | 160000000 | 165000000 | 170000000 | 175000000 | 180000000
|  | Achieved (co-investment) | 5000000 | 2020: 67500000; 2021: 87828283; 2022: 91828283; 2023: 178139258
Planned (leveraged at project)
|  | Achived (leveraged at project) |  | 2020: N/A; 2021: N/A
Source
| Outcome Indicator 4 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Public finance leveraged by the LDN Fund. [KPI 12] | Planned |  |  |  | 85572988 | 85572988 | 85572988 | 85572988 | 85572988 | 85572988 | 85572988 | 85572988 | 85572988 | 85572988 | 85572988 | 85572988 | USD, cumulative. Assumes that the public finance leveraged into projects funded by LDN is additional. Not considered for assessment of fund progress - this is not a specific target outcome of the Fund.
|  | Achieved | 28580327.5968 | 2020: 40866562.3968; 2021: 85572988; 2022: 85572988
Source
| Outcome Indicator 5 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Hectares of land contributing towards Land Degradation Neutrality | Planned |  |  |  | 125000 | 150000 | 180000 | 210000 | 235000 | 265000 | 290000 | 320000 | 350000 | 350000 | 350000 | 350000 | Ha, cumulative. Assumes that land is degradation neutral.
|  | Achieved | 37406 | 2020: 40753; 2021: 98155; 2022: 133301; 2023: 138445
Source
OUTPUT 1 - Financing and TA | Output Indicator 1.1 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
The LDN Fund provides finance and technical assistance to support successful SLM projects which provide financial returns for investors, sustained benefits for local communities and non-financial benefits on a local, national and global scale. Weighting: 40% | Level of TA funding provided | Planned |  |  |  | 2000000 | 2200000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | USD, cumulative. Assumes that TA funding provided by the LDN fund is successful in building capacity of recipients, and creates sustained impacts.
|  | Achieved | 0 | 2020: 996313.41; 2021: 1384435.16; 2022: 2058691.72; 2023: 2400000 |  | 2444254
Source
IDH
| Output Indicator 1.2 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Level of project investment provided | Planned |  |  |  | 160000000 | 180000000 | 180000000 | 180000000 | 180000000 | 180000000 | 180000000 | 180000000 | 180000000 | 180000000 | 180000000 | 180000000 | USD, cumulative. Assumes that project funding provided by the LDN fund is successful in building capacity of recipients in the long term, and creates sustained impacts.
|  | Achieved | 11116025 | 2020: 60616025; 2021: 74500000; 2022: 142411925; 2023: 165409869
Source
| Output Indicator 1.3 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Number of projects funded | Planned |  |  |  | 20 | 27 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | %, overall on LDN investment portfolio. Assumption that invested projects are likely to deliver on their expected outcomes.
|  | Achieved | 0 | 2020: 13; 2021: 17; 2022: 22; 2023: 30
Source
IDH
| Output Indicator 1.4 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Number of countries TA is provided | Planned |  |  |  | 16 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | Cumulative
|  | Achieved | 0 | 2020: 12; 2021: 14; 2022: 14; 2023: 15
Source
IDH
| Output Indicator 1.5 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | LDN, this includes knowledge sharing documents. Conducted by LDN TA. | Sure, but not really showing a change, if it's just LDN
| Number of Knowledge products | Planned |  | 2022: 9; 2023: 11; 2024: 17
|  | Achieved | 0 | 2020: 7; 2021: 10; 2022: 11; 2023: 14
Source
IDH
| Output Indicator 1.6 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Overall return rate on LDN investments | Planned |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 4.2% | 5% | 7.3% | 7.7% | 7.9% | 8.1% | %. Assumes that a healthy return rate will serve as proof of concept to catalyse further private investment in land degradation neutrality projects. Mirova suggestion for targets: LDNF target return quoted to private investors was 7-8%. And at least 5% was protected by junior investors. So I would propose something like "below 5%: underperformance, negative signal to market; 5%-8%: on-target, good signal; 8%+ over performance, very good signal". Something like this. Happy to adjust the numbers. This indicator won't really be useable for several years, but we can provide an estimate of fund performance until it starts to distribute to investors
|  | Achieved | 0 | 2020: N/A; 2021: N/A; 2022: N/A; 2023: N/A
Source
OUTPUT 2 - Environment | Output Indicator 2.1 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
Projects supported by the LDN Fund to deliver positive environmental outputs on a local, national and global scale. Weighting: 25% | Number of threatened species (IUCN Red List) in conservation areas | Planned | [15 empty] | Quantity, cumulative. Assumes that LDN project funding and funded projects have a positive impact on the targeted species
|  | Achieved | N/A | 2020: 39; 2021: 18; 2022: 157; 2023: 105
Source
| Output Indicator 2.2 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Number of sustainable certifications received by LDN-funded projects | Planned |  |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 14 | 14 | 14 | Quantity, cumulative. Assumes that sustainable certifications are a suitable proxy for SLM practices.
|  | Achieved | 3 | 4 | 5 | 2022 6: 7; 2023 7: 8
Source
| Output Indicator 2.3 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Area of land under sustainable management [KPI 17] | Planned |  |  |  | 125000 | 150000 | 180000 | 210000 | 235000 | 265000 | 290000 | 320000 | 350000 | 350000 | 350000 | 350000 | Ha, cumulative. Assumes that sustainable management of land will deliver positive environmental and non-financial benefits
|  | Achieved | 37406 | 2020: 40753; 2021: 98155; 2022: 133301; 2023: 138445
Source
OUTPUT 3 - Social | Output Indicator 3.1 (remove) |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
. Weighting: 25% | Gender ratio of people employed by or with main livelihood supported by LDN Fund projects | Planned |  |  |  | 45% | 46% | 47% | 48% | 49% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Ratio. Assumes that increased ratio of women will provide empowerment to women in affected communities.
|  | Achieved | 45.33% | 2020: 45.46%; 2021: 44.78%; 2022: 42.7%; 2023: 53%
Source
| Output Indicator 3.2 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Number of community engagement events (and attendance in brackets) | Planned | [15 empty] | Qualitative indicator - assumes biennial measurement through surveys.
|  | Achieved |  | 2020: 749; 2021: 654; 2022: 2189; 2023: 3696
Source
| Output Indicator 3.3 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Jobs created/supported by LDN Fund | Planned |  |  |  | 70000 | 75000 | 80000 | 85000 | 90000 | 95000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
|  | Achieved | 25140 | 2020: 35801; 2021: 31995; 2022: 73421; 2023: 106299
Source
OUTPUT 4 - Learning and Knowledge Sharing | Output Indicator 4.1 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
The LDN Fund shares best practice with public and private actors focused on a) expanding SLM practices in developing countries, or b) utilising the impact investment fund approach to contribute to meeting SDG, climate change or environmental targets. Weighting: 10% | Reports on LDN Fund results shared in public domain | Planned |  |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | Number, cumulative. Annual reporting. Assumes that reports will be utilised by interested parties once they are disseminated.
|  | Achieved | 0 | 3 | 5 | 2022 6: 6; 2023 7: 7
Source
| Output Indicator 4.2 |  | Baseline | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Methodology and Assumptions
| Number of external events hosted by LDN Fund, LDN Facility and project partners. | Planned |  |  |  | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | Number, cumulative. Annual reporting. Assumes that events will lead to increased uptake of best-practice approach used by LDN fund. Assumes that LDN Fund is using best practice in its approach to funding large-scale SLM projects.
|  | Achieved | 0 | 4 | 6 | 2022 8: 8; 2023 10: 10
Source