## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE: Building and Enhancing the Evidence Base for Nature Based Solutions to Climate Change: Soy Traceability Phase 2 | The International Climate Finance Evidence Project - Kew Soy
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Enabling non-timber forest risk commodities, especially soybean, from specific ODA countries, to be demonstrably legally harvested and supplied, raising income in ODA countries from soybean (and other non-timber) exports and enhancing livelihoods throughout the value chain, whilst supporting sustainable soy production and sustainability of forests in stakeholder ODA countries | ICF KPI 15: Extent to which ICF intervention/WFID Soy at Kew is likely to lead to Transformational Change | Planned (longer term) Adoption of WFID outputs and methods by soy trade | Status quo: sector and policy need for international cooperation on soy traceability, but currently no UK partnerships with means to determine provenance | Evidence of start of effective collaboration with leading soy producing countries by March 2022 based on WFID technologies | Negotiation of start of soybean reference collection development with Brazil/EMBRAPA (or equivalent LATAM country)
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Annual number of DAC list countries represented in WFID at Kew reference collection and number of samples supplied for lab analyses by at least University of Sheffield and Agroisolab, and results reported to enforcement or corporate bodies | Planned (short term) 1-3 DAC list countries (e.g. Brazil and other LATAM soy producers) & >250 samples supplied | Indicator measuring novel data | DAC list countries = 1-3 & samples supplied = 250 by end 2021/22
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Begin establishment of an accessible and useable reference collection for soybean seeds and their stable isotope signals using SIRA | Progress with implementing measures to reduce trade in illegal soybean globally via generation of authentication data | Planned: progress | Status quo: current support level for trade traceability lacks georeferenced data support from SIRA or other techniques | Beginning of reference database for effective scope and scale based on prototype scalable reference collection at Kew and analysis at Kew, Sheffield, and Agroisolab by March 2022 |  |  | Sample collection may not be possible in all countries approached. Some soybean in supply chains from a given country likely to originate from another. International interest in WFID is generated. DAC-list countries will also have the interest, equipment, and knowledge to use data generated.
Achieved
Source
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Prototype scalable soybean reference collection built to required standards, coverage and size to enable expansion and innovation of authentication technologies and reference database construction | Collection and subsample size | Planned 250 samples | Indicator measuring new samples acquired | 250 samples and associated subsamples by March 2022 |  |  | 1) Mean rate of specimen acquisition remains steady or grows despite CV-19; 2) Rate of specimen acquisiiton is uneven by month; 3) subsample output is determined by sample input and may be impacted by BREXIT changes (e.g. importation and consumables/parts issues).
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Achieved
Source
IMPACT WEIGHTING (%) |  |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
60% |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
INPUTS (£) 156,000 | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Scientific data acquired using the WFID at Kew collection to drive scientific progress and innovation in authentication, with reduction of sampling costs. | Begin development of machine learning approaches to enhance the power of sampling protocols for future supply chain sample analyses to determine soybean traceability. | Planned | Predictive provenancing approaches in early stages of development for other FRCs, namely timber by WFID/Kew. | Model development for soybean | Article draft for publication
Achieved
Source
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Development of a targeted and optimized sampling strategy for SIRA based on the identification, through machine learning modelling of specific focus areas to effectively reduce sampling cost per unit area. | Planned | Predictive provenancing for soybean does not currently exist in the literature | New publication for soybean traceability methodologies
|  | Achieved |  |  | Subject to revision | Subject to revision
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
40% |  | Achieved
|  | Source |  |  |  |  | RISK RATING
INPUTS (£) 104,000 | FCDO/Defra (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.