## Sheet1
PROJECT NAME | GEF - 6th Replenishment
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
Detrimental impact of climate change and environmental degradation on poor reduced and sustainable development supported | Global temperature rise above pre-industrial levels | Planned | TBC | <2 degree celcius | <2 degree celcius | <2 degree celcius | <2 degree celcius
Achieved
Source
UNFCCC
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Proportion of population in developing regions living below $1.25 purchasing power parity (PPP) per day | Planned | 22.0 (2010) [Statistical Annex: Millennium Development Goals, Targets and Indicators, 2013 ] | Not set | Not set | Not set | Not set
Achieved
Source
World Bank
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
GEF programmes contribute toward Millennium Development Goal 7 – ‘ensure environmental sustainability’ | Proportion of global land area covered by forest (%) in GEF countries | Planned | TBC | TBC | TBC | TBC | TBC | Due to the length of the GEF project cycle, GEF contributions to outcomes will largely be derived from previous replenishments Progress against outcome indicators is dependent upon previously approved projects producing the expected results, which take into account broader adoption Inputs will be supplemented by co-financing. The GEF Annual Monitoring Report 2012 stated that, to date, the ratio of GEF5 grant amount to planned co-finance is approximately 1 to 6
|  | Achieved |  |  |  |  | The rate of change in Brazil and Nepal seems to be slowing, while Democratic Republic of Congo (DRC) has seen a large constant rate of net deforestation. Ghana has seen growth of forests and wooded land, and Indonesia has unfortunately seen an increase in rate of deforestation after reductions from 1990-2000 levels. In GEF6 $227.5 million was spent on the Sustainable Forest Management (SFM) Programme against an original target allocation of $230 million.
Source
FAO
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Global CO2 emissions per $1 GDP (PPP) in GEF countries | Planned | TBC | TBC | TBC | TBC | TBC
|  | Achieved |  |  |  |  | In 2015, at a global level and average of 339 kg of CO2 was emitted per $1000 of GDP, compared with 483 kg in 1990. During GEF-6, projects have been approved that aim to mitigate 1,419 million metric tonnes CO2e (against a GEF6 target of 750 million metric tonnes). Investment in climate change has totalled $737.8 million against an original GEF6 target allocation of $1,130 million.
Source
UNFCC, CDIAC
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Terrestrial and marine areas protected to total territorial area (%) in GEF regions | Planned | TBC | TBC | TBC | TBC | TBC
|  | Achieved |  |  |  |  | During GEF-6, GEF projects have been approved that aim to improve the management of landscapes and seascapes for biodiversity conservation of 360 million hectares (against a GEF6 target of 300 million hectares). This equates to a total area of larger than India. The investment in biodiversity has totalled $823.4 million of GEF resources against an original GEF6 target allocation of $1,101 million.
Source
UNFCC, UNSD
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
$4.35bn
INPUTS (HR) | DFID (FTEs)
FTE A1x 0.15, A2x 0.4, B1x 0.15
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumption
GEF interventions approved to deliver GEF6 corporate-level results framework across 6 focal areas: climate change; biodiversity; land degradation; international waters; chemicals and waste; and corporate programmes | Climate Change: Tons of CO2-equivalent emissions to be mitigated through approved projects [from GEF6 Programming Directions, 24 February 2014] | Planned | Projects approved = to 0 million tons mitigated (July 2014) | Projects approved = to 150 million tons mitigated (June 2015) (20% of target) | Projects approved = to 375 million tons mitigated (June 2016) (50% of target) | Projects approved = to 562.5 million tons mitigated (June 2017; 75% of target for replenishment) | Projects approved = to 750 million tons mitigated (June 2018) | Expected results for approved projects are based on extrapolations from previous replenishments and include lifetime direct; lifetime direct post-project, and; lifetime indirect impacts, which requires broader adoption. More information on broader adoption can be found on p. 52 of GEF OPS5 Inputs will be supplemented by co-financing. The GEF Annual Monitoring Report 2012 stated that, to date, the ratio of GEF5 grant amount to planned co-finance is approximately 1 to 6 Meeting milestones will depend on the rate at which projects are approved remaining relatively steady throughout the GEF6 replenishment period
|  | Achieved |  | 460.6 million tons expected from projects approved (June 2015) (61% to target) | 1227 million tons expected from projects approved (June 2016) (164% to target) | Projects approved = to 1,243 million tons mitigated (April 30, 2017) (166% of target for replenishment) | 1,419 million tonnes mitigated (189% of target for replenishment) Exceeded
Source
GEF Secretariat
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Biodiversity: Hectares of landscapes and seascapes to have improved management in place through approved projects [from GEF6 Programming Directions, 24 February 2014] | Planned | Projects approved = to 0 hectares of with improved management (July 2014) | Projects approved = to 60 million hectares with improved management (June 2015) (20% of target) | Projects approved = to 150 million hectares with improved management (June 2016) (50% of target) | Projects approved = to 225 million hectares with improved management (June 2017; 75% of target for replenishment) | Projects approved = to 300 million hectares with improved management (June 2018)
|  | Achieved |  | 69.5 million hectares expected from projects approved (June 2015) (23% to target) | 256 million hectares expected from projects approved (June 2016) (85% to target) | Projects approved = to 395 million hectares with improved management (April 30, 2017) (132% of target for replenishment) | 360 million hectares with improved management (120% of target for replenishment) Exceeded
Source
GEF Secretariat
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Land Degradation: Hectares of agriculture, rangelands and forest landscapes to be sustainably managed through approved projects [from GEF6 Programming Directions, 24 February 2014] | Planned | Projects approved = to 0 hectares (July 2014) | Projects approved = to 24 million hectares (June 2015) (20% of target) | Projects approved = to 60 million hectares (June 2016) (50% of target) | Projects approved = to 90 million hectares (June 2017; 75% of target for replenishment) | Projects approved = to 120 million hectares (June 2018)
|  | Achieved |  | 43.2 million hectares expected from projects approved (June 2015) (36% to target) | 64 million hectares expected from projects approved (June 2016) (53% to target) | Projects approved = to 74 million hectares (April 30, 2017) (62% of target for replenishment) | 103 million hectares (86% of target for replenishment)Not achieved
Source
GEF Secretariat
| Output Indicator 1.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| International Waters: Number of freshwater basins to have Water-Food-Energy-Ecosystems security and conjunctive management of surface and groundwater through approved projects [from GEF6 Programming Directions, 24 February 2014] | Planned | Projects approved = to 0 water basins (July 2014) | Projects approved = to 2 water basins (June 2015) (20% of target) | Projects approved = to 5 water basins (June 2016) (50% of target) | Projects approved = to 7.5 water basins (June 2017; 75% of target for replenishment) | Projects approved = to 10 water basins (June 2018)
|  | Achieved |  | 6 water basins covered by projects approved (June 2015) (56% to target) | 7 water basins covered by projects approved (June 2016) (70% to target) | Projects approved = to 12 water basins (April 30, 2017) (120% of target for replenishment) | 29 water basins (290% of target for replenishment) Exceeded
Source
GEF Secretariat
| Output Indicator 1.5 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Chemicals & Waste: Tons of POPs (PCB obsolete pesticides) to be disposed of through approved projects [from GEF6 Programming Directions, 24 February 2014] | Planned | Projects approved = to 0 tons of POPs (July 2014) | Projects approved = to 16,000 tons of POPs (June 2015) (20% of target) | Projects approved = to 40,000 tons of POPs (June 2016) (50% of target) | Projects approved = to 60,000 tons of POPs (June 2017; 75% of target for replenishment) | Projects approved = to 80,000 tons of POPs (June 2018)
|  | Achieved |  | 2,700 tonnes covered by projects approved (June 2015) (3% to target) | 117,480 tons covered by projects approved (June 2016) (147% to target) | Projects approved = to 60,374 tons of POPs (April 30, 2017) (75% of target for replenishment) | 76,251 tonnes of POPs (95% of target for replenishment) Achieved
Source
GEF Secretariat
| Output Indicator 1.6 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Chemicals & Waste: Tons of mercury to be reduced through approved projects [from GEF6 Programming Directions, 24 February 2014] | Planned | Projects approved = to 0 tons of mercury (July 2014) | Projects approved = to 200 tons of mercury (June 2015) (20% of target) | Projects approved = to 500 tons of mercury (June 2016) (50% of target) | Projects approved = to 750 tons of mercury (June 2017; 75% of target for replenishment) | Projects approved = to 1000 tons of mercury (June 2018)
|  | Achieved |  | 360 tonnes covered by projects approved (June 2015) (36% to target) | 374 tons covered by projects approved (June 2016) (37% to target) | Projects approved = to 623 tons of mercury (April 30, 2017) (62% of target) | Projects approved = to 638 tonnes of mercury (64% of target) Not achieved
Source
GEF Secretariat
| Output Indicator 1.7 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Chemicals & Waste: Tons of ODP (HCFC) to be phased out through approved projects[from GEF6 Programming Directions, 24 February 2014] | Planned | Projects approved = to 0 tons of ODP (July 2014) | Projects approved = to 60 tons of ODP (June 2015) (20% of target) | Projects approved = to 150 tons of ODP (June 2016) (50% of target) | Projects approved = to 225 tons of ODP (June 2017; 75% of target for replenishment) | Projects approved = to 300 tons of ODP (June 2018)
|  | Achieved |  | 0 tonnes covered by projects approved (June 2015) (0% to target) | 0 tons covered by projects approved (June 2015) (0% to target) | Projects approved = to 135 tons of ODP (April 30, 2017) (45% of target) | 26 tonnes of (9% of target) Not achieved
Source
GEF Secretariat
| Output Indicator 1.8 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Corporate Programmes: Number of countries to be supported in the creation of development and sectoral planning frameworks, that integrate measurable targets drawn from the MEAs, through approved projects [from GEF6 Programming Directions, 24 February 2014] | Planned | Projects approved = to 0 (July 2014) | Projects approved = to 2 countries (June 2015) (20% of target) | Projects approved = to 5 countries (June 2016) (50% of target) | Projects approved = to 7.5 countries (June 2017; 75% of target for replenishment) | Projects approved = to 10 countries (June 2018)
|  | Achieved |  | 5 countries covered by projects approved (June 2015) (50% to target) | 8 countries covered by projects approved (June 2016) (80% to target) | Projects approved = to 14 countries (April 30, 2017) (140% of target) | 19 countries (190% of target) Exceeded
Source
GEF Secretariat
| Output Indicator 1.9 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Corporate Programmes: Number of countriesto be have functional enivronmental information systems, to support decision making, provided through approved projects [from GEF6 Programming Directions, 24 February 2014] | Planned | Projects approved = to 0 (July 2014) | Projects approved = to 2 countries (June 2015) (20% of target) | Projects approved = to 5 countries (June 2016) (50% of target) | Projects approved = to 7.5 countries (June 2017; 75% of target for replenishment) | Projects approved = to 10 countries (June 2018)
|  | Achieved |  | 5 countries covered by projects approved (June 2015) (50% to target) | 10 countries covered by projects approved (June 2016) (100% to target) | Projects approved = to 18 countries (April 30, 2017) (180% of target) | 19 countries (190% of target) Exceeded
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING minor
70% |  | GEF Secretariat
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
GEF policy priorities identified during GEF6 replenishment process, and as set out in GEF6 Business Case, implemented | % share of private sector co-financing in GEF6 projects [Policy Priority I in GEF6 Business Case; indicator drawn from GEF6 Programming Directions, 24 February 2014] | Planned | 20% [GEF5 figure from GEF6 Programming Directions, February 2014] | 21% | 23% | 25% | 25% [June 2018] (indicative)
|  | Achieved |  | 21% | 32.37% | 20% | 13% Below target
Source
GEF
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| % of GEF funds allocated to multi-focal area (MFA) focal area [Policy Priority II in GEF6 Business Case; indicator created by David Grocott 30.04.14] | Planned | 42% [GEF Annual Monitoring Review, October 2012] | 44% | 47% | 50% | 50% [June 2018] (indicative)
|  | Achieved |  | 44% | 50% of funding allocated so far during GEF6 | 55 | 53% Exceeded
Source
GEF Annual Monitoring Review
| Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| % of GEF funds allocated to special programmes [Policy Priority III in GEF6 Business Case; indicator created by David Grocott 30.04.14] | Planned | 8.8% [GEF Secretariat] | 9.2% | 9.6% | 10% | 10% [June 2018] (indicative)
|  | Achieved |  | 9% | 9% | 14% ($373 million out of the total $2.65 billion utilisation) | 12% Exceeded
Source
GEF Secretariat
| Output Indicator 2.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| % of GEF6 projects that incorporate gender equality and women empowerment issues in project document / project monitoring and evaluation reports [Policy Priority IV in GEF6 Business Case; indicator from GEF6 Programming Directions, 24 February 2014] | Planned | 57 % / 41% [GEF5 figure from GEF6 Programming Directions, February 2014] | 58% / 47% | 59% / 53% | 60 | 60% / 60% (indicative)
|  | Achieved |  | 100% / TBC | Percentage of projects that have conducted a gender analysis: 86% Percentage of projects that have incorporated elements of a gender responsive results framework: 79% Percentage of monitoring and evaluation reports that incorporate gender: 54% | 67 | 78% Exceeded
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING-Minor
15% |  | GEF Secretariat
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
Effectiveness, efficiency and economy of the GEF improved through operational reforms as set out in the GEF6 Business Case | % of GEF funds committed to projects in less developed countries (LDCs) [Operational Reform I in GEF6 Business Case; indicator created by David Grocott 30.04.14] | Planned | 15% [from QAU report, April 2014] | 17% | 18% | 19% | 19%
|  | Achieved |  | 10% | 17.95% | 18% | 17%
Source
GEF Secretariat
| Output Indicator 3.2 |  |  | Baseline | Milestone 2 | Milestone 3 | Target (date)
| Median length of time elapsed between PIF approval by the Council and CEO endorsement [Operational Reform II in GEF6 Business Case; indicator created by Emma Dougan 23.10.15.] | Planned |  | 20 months | 18 months | 18 MONTHS | 18 months
|  | Achieved |  |  | 26 months for full-sized projects submitted in fiscal year 16 for (July15-June16) | 19 months | 18 months
Source
GEF Secretariat
| Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| % of GEF6 projects that involve civil society organisations or indigenous people as key partners [Operational Reform III in GEF6 Business Case; indicator from GEF6 Programming Directions, 24 February 2014] | Planned | CSOs: 59% (of cumulative projects as presented in AMR, Part II, FY13) [GEF5 figure from GEF6 Programming Directions, February 2014] | 62% | 66% | 70% | 70% [June 2018] (indicative)
|  | Achieved |  | GEF-6 figures for CEO endorsed projects (but n=7) Indigenous peoples: 43% CSOs: 100% GEF-5 figures are: Indigenous peoples: 18% CSOs: 65% | For full-sized GEF6 CEO endorsed projects (there are 29): CSO: 62% Indigenous peoples: 28% Involving either as partners: 76% (Please see Annual Review 2016 for further details) | 92% | 95%
Source
GEF Secretariat
| Output Indicator 3.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| % of projects from all replenishments in which some or most broader adoption initiatives have been successfully adopted or implemented [Operational Reform IV in GEF6 Business Case; indicator from 'VfM measures' table in GEF6 Business Case] | Planned | 60% [as stated on p.55 of OPS5, November 2013] | 63% | 66% | 66% | 70% (June 2018) (indicative)
|  | Achieved |  | n/a | n/a |  | In FY17, 87% of 746 projects under implementation were rated 'moderately satisfactory' or higher. Slightly below target.
Source
GEF Independent Evaluation Office
| Output Indicator 3.5 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| % of GEF portfolio under implementation that receive moderately satisfactory or higher rating on progress towards development objectives in a given financial year [VfM measure in 'VfM measures' table in GEF6 Business Case; indicator from GEF6 Programming Directions, 24 February 2014] | Planned | 82% FY12 [GEF Annual Monitoring Review, October 2012]] | 84% | 87% | 90% | 90% (June 2018)
|  | Achieved |  | 91% | 91.5% | 87% | In FY17, 87% of 746 projects under implementation were rated 'moderately satisfactory' or higher. Slightly below target
Source
GEF Annual Monitoring Review
| Output Indicator 3.6 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| GEF agency fees [VfM measure in 'VfM measures' table in GEF6 Business Case; indicator from 'VfM measures' table in GEF6 Business Case] | Planned | 9.5% for grants up to $10 million and 9% for grants above $10 million [as stated in MAR Update 2013] | 9.5% for grants up to $10 million and 9% for grants above $10 million [June 2015] | 9.5% for grants up to $10 million and 9% for grants above $10 million [June 2016] | 9.5% for grants up to $10 million and 9% for grants above $10 million | 9.5% for grants up to $10 million and 9% for grants above $10 million [June 2018]
|  | Achieved |  | Project proposals for 2015 comply with the caps – some of the CEO endorsed projects have higher agency fees | Project proposals compliant | 9.5% for grants up to $10 million and 9% for grants above $10 m | Cumulative share of Agency fees is 7%. Exceeded.
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING minor
15% |  | GEF Secretariat
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
This logframe does not reproduce all the indicators in the GEF6 Programming Directions and reference should be made to that document and consideration given to other indicators when reviewing the link between outputs, outcome and impact.
This logframe is based on a $4.25 billion replenishment scenario, which represents “status quo” compared with the GEF-5 programming level