## Logframe
PROGRAMME NAME: BIOFIN
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Global need for biodiversity finance reduced due to establishement of methods of finance flowing towards biodiversity, with future biodiversity expenditures avoided. | KPI 11 and 12: 3-301 Volume of private and/or public finance leveraged for biodiversity purposes | Planned | 0 | Finance results likely not emerged in one year period. It is also not possible to define specific milestones in one year period. | Finance results likely not emerged in one year period. It is also not possible to define specific milestones in one year period. | 2023-03-31 | Achievement of this impact will ultimately require much longer than the 1 year timeframe of this project and depend on contributions from a wide range of other international and national-level actors.
Achieved
Data, sources and methods
Published government budgets, government regulations/legislations
RISK RATING
Medium
Outcome | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Governments, ministries or other public body awareness and engagement in biodiversity finance increased. | 1-102A Number of people directly supported by BIOFIN through networking and training to finance biodiversity. | Planned | 0 | 500 | 1000 | 2023-03-31 | Constraints accurately identified; Capacity and will exist to absorb and adopt fiannce redesigns and related policies, practices and institutional changes; No further barriers exist to prevent ongoing effective implementation of complementary mix of redesigns; redesigns lead to improved effectiveness, efficiency and synergies and to measureable increases in finance for biodiversity; Intention to invest in biodiversity translates to actual pro-biodiversity spending; incentives and oversight in place ensure ongoing biodiversity investment integrity; Political, administrative, economic and environmental conditions are favourable.
Achieved
Data, sources and methods
BIOFIN event records.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| 1-401 Number of finance solutions identified | Planned | 150 | 175 (also includes other donors, not Defra specific) | 200 | 2023-03-31
Achieved
|  |  | Data, sources and methods |  |  |  | RISK RATING
|  |  | Country progress reports. |  |  |  | Low
INPUTS (£) | Defra (£) |  | Govt (£) | Other (£) | Total (£) | Defra SHARE (%)
| £2M |  | £2M |  | £2M | 100%
INPUTS (HR) | Defra (FTEs)
OUTPUT 1: Regional Nodes Platform | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Establishment of the Regional Nodes platform providing information and knowledge on the BIOFIN methodology and biodiversity finance sources, providing the data and evidence needed to drive policy and practice to all CBD parties, and allowing an open ‘library’ of resources for all countries, | Number of existing entries in the Biodiversity Finance Sources database, which are now web-based, data quality-checked and improved | Planned | 0 | 160 | 320 | 2023-03-31 | BIOFIN resources, design and operations able to effectively engage key stakeholders and deliver
Achieved
Data, sources and methods
Biodiversity Finance Sources database
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Number of new entries in the Biodiversity Finance Sources database | Planned | 0 | 90 | 180 | 2023-03-31
Achieved
Data, sources and methods
Biodiversity Finance Sources database
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
25% | Number of unique visitors to the database on the BIOFIN website | Planned | 0 | 1000 | 2000 | 2023-03-31
Achieved
|  | Data, sources and methods |  |  |  |  | RISK RATING
|  | Google analytics |  |  |  |  | Medium
INPUTS (£) | Defra (£) |  | Govt (£) | Other (£) | Total (£) | Defra SHARE (%)
| 222600 |  | 222600 | - | 222600 | 100%
INPUTS (HR) | Defra (FTEs)
OUTPUT 2: Global campaign for governments working to repurpose subsidies harmful to nature | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Further awareness of the impact of subsidies harmful to nature and how they can be realigned or redirected to benefit nature raised for governments. | Number of country teams who have been briefed on the dissemination plan | Planned | 0 | 19 | 38 | 2023-03-31 | BIOFIN resources, design and operations able to effectively engage key stakeholders and deliver
Achieved
Data, sources and methods
participant list of briefing meetings
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| 1-102B Percentage of BIOFIN event participants who rate the event as having been a significant learning experience. | Planned | 0 | 75% | 80% | 2023-03-31
Achieved
Data, sources and methods
BIOFIN event records, specifically the post- event evaluation survey.
IMPACT WEIGHTING (%)
25%
RISK RATING
Medium
INPUTS (£) | Defra (£) |  | Govt (£) | Other (£) | Total (£) | Defra SHARE (%)
| 204050 |  | 204050 | - | 204050 | 100%
INPUTS (HR) | Defra (FTEs)
OUTPUT 3: Biodiversity Expenditure Taxonomy | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
The establishment of a Biodiversity Expenditure Taxonomy to classify expenditure data. | Completion of draft taxonomy and shared with partners by March 2023 | Planned | (no such taxonomy is exist) | 1st draft | Final draft | 2023-03-31 | BIOFIN resources, design and operations able to effectively engage key stakeholders and deliver
Achieved
Data, sources and methods
Copy of Taxonomy
IMPACT WEIGHTING (%)
25%
RISK RATING
Medium
INPUTS (£) | Defra (£) |  | Govt (£) | Other (£) | Total (£) | Defra SHARE (%)
|  |  | 92750 |  | 92750 | 100%
INPUTS (HR) | Defra (FTEs)
OUTPUT 4: Finance sector innovation grants | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
The development and piloting of innovative approaches in finance through finance sector grants. | Number of nature-related disclosure readiness studies validated by the national partners | Planned | 0 | 3 | 6 | 2023-03-31 | BIOFIN resources, design and operations able to effectively engage key stakeholders and deliver
Achieved
Data, sources and methods
Validation meeting records.
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Number of county-level feasibility studies on nature performance related debt-based financal instruments completed. | Planned | 0 | - | 1 | 2023-03-31
Achieved
Data, sources and methods
Copy of the feasibility study
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
25% | Number of screening studies completed. | Planned | 0 | - | 1 | N/A
Achieved
|  | Data, sources and methods |  |  |  |  | RISK RATING
|  | Screening study reports. |  |  |  |  | Medium
INPUTS (£) | Defra (£) |  | Govt (£) | Other (£) | Total (£) | Defra SHARE (%)
|  |  | 742000 |  | 742000 | 100%
INPUTS (HR) | Defra (FTEs)