## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE: Driving innovation in forest protection and enforcement monitoring. Tackling illegal logging: creating a timber reference library to support enforcement (World Forest ID or WFID at Kew).
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Enabling forest risk commodities, especially timber, from specific ODA countries, to be demonstrably legally harvested and supplied, raising income in ODA countries from timber exports and enhancing livelihoods throughout the value chain, whilst supporting sustainability of forests and forestry in stakeholder ODA countries | ICF KPI 15: Extent to which ICF intervention/WFID at Kew is likely to lead to Transformational Change | Planned: Adoption of WFID outputs and methods by timber trade | Up to 30% of forest product trade is illegal. Timber trade uses paper-based traceability approaches | Evidence of effective collaboration with BEIS-OPSS by December 2022 based on WFID technologies | Evidence of engagement: at least one major timber trade sector organisation involved in WFID structure and funding activity by December 2023 | Multiple major timber corporates using WFID authentication science to audit supply chains by October 2025
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Annual number of DAC list countries represented in WFID at Kew reference collection and number of subsamples supplied for lab analyses by at least WISC and Agroisolab, and results reported to enforcement or corporate bodies | Planned; 20 DAC list countries & 5000 subsamples supplied | Indicator measuring novel data | DAC list countries = 10 by end 2021/22 & Subsamples supplied = 2000 by September 2022/23 | DAC list countries = 16 by end 2023/24 & Subsamples supplied = 4000 by end 2023/24 | DAC list countries = 20 by March 2026 & Subsamples supplied = 5000 by October 2025
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Global collection of physical timber samples from ODA countries developed and samples used to confirm or disprove documentary claims about timber product identity and provenance using data from three scientific techniques; DART TOF MS, SIRA, wood anatomy . | Progress with implementing measures to reduce trade in illegal timber globally via generation of authentication data [Outcome #106 slightly modified] | Planned: progress | Status quo: current support level for trade traceability lacks georeferenced data support from anatomy, SIRA, DART combined | Reference database of effective scope and scale based on reference collection at Kew and analysis at Kew, WISC and Agroisolab by September 2023 | Use of database for enforcement action by March 24 | Yes/no as per milestones | 1) Compliance and enforcement drive transformational change 2) Reporting against EUTR and other legislation reflects the global picture of timber trade standards and compliance accurately 3) Enforcement effectiveness and investment remain consistent accross area covered by specific legislation
Achieved
Source
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Changes in business standards, compliance and behaviour of value chain stakeholders [investors] in relation to reducing deforestation as measured by levels of illegal logging and enforcement actions reported under EUTR/UKTR/Forest Risk Commodity legislation [Outcome # 112, modified] | Planned | 2020 EUTR: DAC list countries. 3 reporting increase in deforestation, illegal logging, or illegal trade. 19 reporting ongoing deforestation, illegal logging, or illegal trade. 6 reporting improvements or implementing measures against deforestation and illegal logging activity. EU Countries. 4 reporting increase in seizures or inadequate implementation. 2 reporting ongoing seizures or inadequate implementation . 6 reporting improvements or implementing measures against deforestation and illegal logging activity reporting ongoing seizures or inadequate implementation [Data from https://www.unep-wcmc.org/resources-and-data/briefing-notes-on-the-implementation-of-the-eu-timber-regulation] | Reduction of 5% in reports and enforcement actions against baseline by December 2023 |  | Reduction of 10% in reports and enforcement actions against baseline by October 2025
Achieved
Source
INPUTS (£) 2,639,433 | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Reference collection built to required standards, coverage and size to enable expansion and innovation of authentication technologies and reference database construction | Collection size | Planned: 6000 samples | Indicator measuring new samples acquired | 2400 samples by March 2022 | 4800 samples by end 2023/24 | 6000 samples acquired, accessioned, processed and curated to international standards by Y5 (1200/year) by October 2025 | 1) Mean rate of specimen acquisition rermains steady or grows despite CV-19 2) Rate of specimen acquisiiton is uneven by month 3) subsample output is determined by sample input and may be impacted by BREXIT changes 4) Field identification of specimens is accurate and checked
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Subsample supply | Planned: 5000 subsamples |  | 2000 by September 2022 | 4000 by March 2025 | 5000 subsamples supplied to WFID consortium laboratories by October 2025 (1000/year)
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
30 |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
3 x 2 = 6 Moderate
INPUTS (£) 1,055,773 | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Scientific data acquired using the WFID at Kew collection to drive scientific progress and innovation in authentication, with reduction of sampling costs | Technical advances in use of DART TOF MS, SIRA, wood anatomy as techniques for timber authentication by wider WFID consortium, supported by developments in AI and genomics as indicated by academic publications | Planned | All new publications | 2 publications by end 2021/22 | 4 publications by end 2023/24, . | 5 Academic publications by October 2025 | Scientific need for DART-TOFMS publications may be lower since the method has been proven. Opportunity remains for more applied papers (product types and so on). Technologies deliver at expected level.
Achieved
Source
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Development or enhancement of methods for timber species authentication, with a specific focus on the added strength of combination of multiple techniques and datatypes by wider WFID consortium (1 academic publication per year from 2021-22). | Planned | All new publications | 2 publications by end 2022/23 | 4 publications by end 2023/24 | 4 Academic publications by October 2025
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
30 | Development of a targeted and optimized sampling strategy for SIRA based on the identification, through machine learning modelling of specific focus areas to effectively reduce sampling cost per unit area. | Planned | New publication |  |  | 3 Academic publications by December 2024
Achieved
|  | Source |  |  |  |  | RISK RATING
2 x 3 = 6 Moderate
INPUTS (£) 790, 481 | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Generation of collaborations with BEIS-Office for Product Safety & Standards Environmental Enforcement & Compliance Team (BEIS-OPSS) resulting in targeted collections and authentication research enabling enhanced UKTR enforcement and international timber trade regulatory compliance | 2 country-based collaborations with BEIS-OPSS initiated or continued per year from 2021; 1 training session per year from 2021 held with BEIS-OPSS in enforcement-based scientific methods | Planned: 8 collaboration-years recorded & 4 training sessions | All novel activity | 2 collaboration years recorded by end 2021/22 | 6 collaboration years recorded by end 2021/22 | 8 collaboration-years recorded & 4 training sessions by October 2025 | Sample collection may not be possible in all countries. Some timber in supply chains from a given country likely to originate from another. International interest in WFID is generated. DAC-list countries will also have the interest, equipment and knowledge to use data generated.
Achieved
Source
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| 3 reports based on implementation of DART TOF-MS, SIRA, wood anatomy or other research methods delivered to BEIS-OPSS and international governmental stakeholders per year via WFID geared to their needs. At least one output similar in scope to Chinese plywood enforcement project report developed during project | Planned: 12 reports and 1 output | Novel reports and output |  |  | 12 reports and 1 output like Chinese plywood enforcement project report by October 2025
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20 | International use of WFID at Kew collection and open access databases arising from it by DAC list country governments to support timber trade legality verification | Planned: International governmental use | Novel uses will be recorded |  |  | Use by DAC list country governments by October 2025 (yes/no)
Achieved
|  | Source |  |  |  |  | RISK RATING
2 x 3 = 6 Moderate
INPUTS (£) 526, 487 | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Leveraging of matched funding via philanthropic and statutory finance during the Defra funded period of WFID at Kew and developing a roadmap towards being self-sustaining at the end of the five year Defra ICF-funded period via development of a business model based on private sector investment and/or fee for service provision | Statutory or philanthropic funding for WFID at Kew leveraged, at least one application per year | Planned: £3M | Novel funding | Target list of statutiry bodies and donors created and £1M to be raised by March 2023 | £2M to be raised by March 2024 | £3M to be raised by October 2025 | Sufficient philanthropic interest in this project to provide the estimated funding level. Statutory funders strategic priorities link to translational science like WFID. Both categories are able to continue funding at pre-CV-19 levels
Achieved
Source
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Development of WFID business model | Planned: WFID consortium financially self-sustaining | WFID a consortium of collaborating organisations | Not for profit organisation established in USA by December 2021 | Key private sector investment and (e.g.) fee for service clients identified by December 2024 | Wider WFID consortium financially self-sustaining by October 2025 (yes/no)
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20 |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
3 x 3 = 9 High
INPUTS (£) 263, 493 | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Note on E23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Potentiall change to other indicator. Reduction might be hard to quantify, @Victor Deklerck - think about. Reply: Potential change might be the increase in reporting in convictions (see new article DNA proof in the Pacific North West)
Note on E34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Track if exponential increase is indeed seen in sample supply.
Note on H47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Victor Deklerck -> potentially change risk rating to Minimal. NOTE: can go up again if a key country limits travel (covid 19) Reply: @Victor Deklerck , change to minimal once current reporting period ends (juli 2021)
Note on E74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Victor Deklerck -> check with Mark Martin when next meeting is with Deane Hughes. Reply: Have checked, Mark will provide update
Note on G79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do one on Solomon Islands (lessons learned, sampling) Reply: Ask in meeting with Phil/Emily/Marysol

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.