## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.

## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | 2023 | 2024 | Target (2025)
Increased, early uptake of integrated sustainable cooling and cold-chain solutions in developing countries to accelerate (and double) the climate benefits of the Kigali Amendment to the UN Montreal Protocol. | Greenhouse gas emissions reduced or avoided (ICF 6) | Planned | 0 | 0 | 0.07 MtCO2eq | 0.47 MtCO2eq
|  | Achieved |  | No data
Source
Needs to link to these methodologies: https://www.gov.uk/government/publications/uk-climate-finance-results
| Impact Indicator 2 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of people supported to better adapt to the effects of climate change (ICF 1) (disaggregated by gender and country) | Planned | 0 | 48 farmer coops | 288 farmer coops | 528 farmer coops
|  | Achieved |  | No data
Source
Needs to link to these methodologies: https://www.gov.uk/government/publications/uk-climate-finance-results
| Impact Indicator 2 |  | Baseline | 2023 | 2024 | Target (2025)
| Extent to which intervention is likely to lead to Transformational Change (ICF 15) | Planned | 0 | TBD
|  | Achieved |  | 4 out of 5 (Highly likely)
Source
Needs to link to these methodologies: https://www.gov.uk/government/publications/uk-climate-finance-results
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | 2023 | 2024 | Target (2025) | Assumptions
Strengthened capacity to facilitate uptake of sustainable cooling and cold-chain solutions | Number of knowledge bases created through needs and impact assessments, virtual models and other tools developed (disaggregated by countries) | Planned | 0 | 2 | 4 | 4
|  | Achieved |  | 7
Source
Monitoring and progress reports will track the number of these knowledge bases being created. Which countries will benefit from these will also be recorded in order to disaggrate
| Outcome Indicator 1.2 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of representatives from a farmer cooperative attending business model training courses to address sustainable cooling and cold-chain development and access (disaggregated by countries) | Planned | 0 | 48 | 288 | 528
|  | Achieved |  | 43 Trainers/Mobilisers (Rwanda: 38, Kenya: 5), 95+40 Faremrs (Rwanda 80, Kenya:15 + 40)
Source
Participant lists and reports will monitor the number of people attneding this courses. The country where the students have come from will also be recorded in order to dissagregate.
| Outcome Indicator 1.3 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of technicians/engineers trained to support development of a sustainable cooling and cold-chain system for food and health (disaggregated by countries and gender) | Planned | 0 | 15 | 60 | 120
|  | Achieved |  | 18 (Rwanda: 5, Kenya: 2, Uganda: 1, Telangana: 5, ACES: 4
Source
Participant lists and reports will monitor the number of people attneding this courses. The country where the students have come from will also be recorded in order to dissagregate.
| Outcome Indicator 1.4 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of health professionals trained to support development of a sustainable cooling and cold-chain system for health (disaggregated by countries and gender) | Planned | 0 | 15 | 60 | 120
|  | Achieved |  | 20
Source
The definintion of health professional here is expanded to include staff critical to the vaccine cold-chain system who may not have direct clinical care responsibilities, for example vaccine logitistics managers, data scientists and public health officials. We aim to capture the numbers of indivuduals through records of attendance at workshops/courses, co-authorts on grant submissions/academic outputs and students undetaking projects under supervsion of the ACES team.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | 2023 | 2024 | Target (2025) | Assumptions
Improved livelihoods for farmers and rural communities | Total value of food saved through access to cooling and cold-chain solutions and improved market connectivity | Planned | 0 | 0 | £21 million | £148 million | Current food loss is 36%.
|  | Achieved |  | 0 - First report due 2024
Methodology/Data/Source
Monitoring and progress reports will track the total value of food loss.
| Outcome Indicator 2.2 |  | Baseline | 2023 | 2024 | Target (2025)
| Percentage of farmers trained through ACES and SPOKEs reporting improved income (disaggregated by countries and gender) | Planned | 0
|  | Achieved |  | 0 - First report due 2024
Source
Participants lists and reports will track those attending the training (recording country where participants are from and gender), survey of beneficiaries after training to track reported improved income.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline | 2023 | 2024 | Target (2025) | Assumptions
Improved understanding of sustainable cooling and cold-chain solutions in specific markets which can lead to transformational change | Number of signed commitments with stakeholders to support ACES (Disaggregated by governments/industry/academic institutions) | Planned | 0 | Academic institutions: 2 Industry: 5 | Academic institutions: 6 Industry: 15 | Academic institutions: 6 Industry: 25
|  | Achieved |  | Academic institutions: 2 Industry: 9 Other orgs: 8
Source
Track number of partnership agreements reached.
| Outcome Indicator 3.2 |  | Baseline | 2023 | 2024 | Target (2025)
| Support leveraged by stakeholders (Disaggregated by capital incl. equipment and resource) | Planned | 0 | £0.5 million | £2.5 million | £5 million
|  | Achieved |  | ~£2.03 million (+ non monetary support)
Source
Track of support leveraged through financial means and also 'in-kind' support.
| Outcome Indicator 3.3 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of reports and academic papers published to further understand sustainable cooling and cold-chain solutions | Planned | 0 | 3 | 8 | 13
Achieved
Source
Monitoring and progress reports will track the number of these papers published.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2023 | 2024 | Target (2025) | Assumptions
Enhanced capacities to implement policies, programmes, and investment plans | Number of macro level tools developed and applied for gaps and needs analyses and impact assessment (disaggregated by countries) | Planned | 0 | 2 | 6 | 6 | Guidelines will be written and disseminated as planned. HFC Outlook Global Model will be completed and able to be used by partner organisations and countries on their technology. Defra financing will act as a catalyst with which to bring in futher support for deployment through the Multilateral Fund.
|  | Achieved |  | 4 (Kenya:3, Rwanda: 1)
Source
Monitoring and progress reports will track the number of these tools developed and applied. Which countries will benefit from these will also be recorded in order to disaggrate
| Output Indicator 1.2 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of SPOKEs / outreach programmes established (disaggregated by countries) | Planned | 0 | 1 | 4 | 7
|  | Achieved |  | 1 (Kenya, Konza)
Source
Monitoring and progress reports will track the number of these programmes established. Which countries will benefit from these will also be recorded in order to disaggrate
| Output Indicator 1.3 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of organisations and countries using the HFC Outlook Model | Planned | 0 | 10 | 15 | 30
|  | Achieved |  | No data
Source
Owner of model will track number of models issued or updated to an organisation or country.
| Output Indicator 1.4 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of regional harmonisation activities for cooling products (disaggregated by market and country) | Planned | 0 | 1 | 2 | 2
|  | Achieved |  | 2 (SADC + EAC)
Source
When finalised, the regional policies will be saved ont the respective regional website such as SADC for Southern Africa to be tracked: https://www.sadc.int/pillars/standards-quality-infrastructure
IMPACT WEIGHTING (%) | Output Indicator 1.5 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of governments receiving targeted support for implementation of MEPS or Energy Efficiency voluntary programmes for cooling products. (disaggregated by market/product) | Planned | 0 | 2 | 4 | 6
|  | Achieved |  | 3 - Malaysia (A/Cs), South Africa (Labelling development), The Gambia (A/Cs and residential refrigeration)
|  | Source |  |  |  |  | RISK RATING
Reports of stakeholder meetings/consulations. Tailored Training reports. Tracking of tools and materials shared, and technical consultations answered
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2023 | 2024 | Target (2025) | Assumptions
Improved skills and technical capacity within country to implement sustainable cooling and cold-chain solutions through capacity building | Number of farmer cooperatives trained in cold chain through ACES and SPOKEs reporting improved knowledge in new equipment and processes (disaggregated by countries and gender) | Planned | 0 | 38 | 230 | 422
|  | Achieved |  | No data
Source
Participants lists and reports will track those attending the training (recording country where participants are from and gender), survey of beneficiaries after training to track reported improved income.
| Output Indicator 2.2 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of students trained through ACES and SPOKEs reporting improved knowledge in analytical skills and models of vaccine systems (disaggregated by countries and gender) | Planned | 0 | 15 | 60 | 120
|  | Achieved |  | 20
Source
Participants lists and reports will track those attending the training (recording country where participants are from and gender), survey of beneficiaries after training to track reported improved income.
| Output Indicator 2.3 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of governments/organisations that have participated in training (webinar or in-person) on the Model Regulation Guidelines (disaggregated by market/product, gender and country) | Planned | 0 | 30 | 60 | 90
|  | Achieved |  | 14 from 14 countries, 40% female + number tbc on 20/07/23
Source
Training curricula, attendance lists, webinar recordings and workshop reports. All will be uploaded to: https://united4efficiency.org/resources/model-regulation-guidelines/ and https://united4efficiency.org/resources/videos-webinars/
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of procurement experts trained on the SPP toolkit (disaggregated by country and gender) | Planned | 0 | 30 | 30 | 30
|  | Achieved |  | Ghana – 22 (2 female) Morocco – 3 (1 female) Egypt - TBD, Q3 2023
|  | Source |  |  |  |  | RISK RATING
Training curricula, attendance lists, webinar recordings and workshop reports will all be used to track and uploaded onto here: https://united4efficiency.org/sustainable-public-procurement/
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2023 | 2024 | Target (2025) | Assumptions
Increased access to, energy efficient and climate friendly cooling and cold-chain solutions for food and vaccines. | Number of Community Needs Assessments conducted to support equipment deployment (disaggregated by countries) | Planned | 0 | 2 | 8 | 16
|  | Achieved |  | 6 (Kenya: 3, Rwanda: 2, Telangana: 1)
Source
Monitoring and progress reports will track the number of these assessments conducted. Which countries will benefit from these will also be recorded in order to disaggrate
| Output Indicator 3.2 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of demonstration activities completed with support from ACES (disaggregated by countries) | Planned | 0 | 2 | 12 | 24
|  | Achieved |  | 2, with 1 aditional ongoing (no disaggregation data)
Source
Monitoring and progress reports will track the number of these activities completed. Which countries will benefit from these will also be recorded in order to disaggrate
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of public health interventions contributing towards sustainable delivery of vaccines for future needs, and vaccine/cold-chain demand mitigation (disaggregated by countries) | Planned | 0 | 5 | 10 | 15
|  | Achieved |  | 1 (Rwanda)
|  | Source |  |  |  |  | RISK RATING
The principal output unit will be the publication of academic work (reports, reviews, models, basic sciences, impact/epidemiology and other original research) that widely disseminate our findings to the community of healthcare professionals and policy makers connected to vaccine cold-chain reliabilty, effeicency and sustainability.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | 2023 | 2024 | Target (2025) | Assumptions
Improved farmer knowledge and skill on best-practices through capacity building | Number of farmer cooperatives trained in post-harvest management reporting improved knowledge (disaggregated by gender and country) | Planned | 0 | 38 | 230 | 422 | 30 Farmers per attend each 8 week long programme. 80% of co-ops actually implement cold-chain strategy, mentoring and support to minimise fall-out rate.
|  | Achieved |  | No data
Source
Participants lists and reports will track those attending the training (recording country where participants are from and gender), survey of beneficiaries after training to track reported improved income.
| Output Indicator 4.2 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of farmer cooperatives received basic refrigeration training reporting improved knowledge (disaggregated by gender and country) | Planned | 0 | 38 | 230 | 422
|  | Achieved |  | No data
Source
Participants lists and reports will track those attending the training (recording country where participants are from and gender), survey of beneficiaries after training to track reported improved income.
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | 2023 | 2024 | Target (2025)
| Number of farmer cooperatives trained in market chain analysis, business planning and market linkage etc. reporting improved knowledge (disaggregated by gender and country) | Planned | 0 | 38 | 230 | 422
|  | Achieved |  | No data
|  | Source |  |  |  |  | RISK RATING
Participants lists and reports will track those attending the training (recording country where participants are from and gender), survey of beneficiaries after training to track reported improved income.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Note on E29: Woof-Dwight, Simon: Notes state 'We are commencing the Postharvest Training Programme in Kenya in August. We are commencing the Rwanda Postharvest Training programme in Rwanda in Q4, 2023' Which may put some figures outside of the reporting period. Kenya farmers 15+40 also unclear
Note on E34: Woof-Dwight, Simon: Response document says 18, but lists only 17, with 7/8 spaces for further recruitment
Note on C52: McFarlane, Isobel (DEFRA): We need more on this i.e.how will calculate value of food etc and how will attribute?
Note on E54: McFarlane, Isobel (DEFRA): Assume less than number training-need to baseline this. How many farmers trained through the cooperatives? Then can do a % based on this.
Note on C57: McFarlane, Issy: Would need to survey everyone to check income changed
Note on E71: Woof-Dwight, Simon: Data from both returns amalgamated and converted to GBP at today's exchange rate. Non-monetary support currently has no estimate
Note on E92: Woof-Dwight, Simon: Returned data is unclear: '1 – Kenya (Konza) Telangana and Haryana Senegal in MoU Lesotho and Nigeria subject to partners / matched funding' Implies Senegal, Lesotho and Nigeria are being developed, but unsure about Telangana and Haryana
Note on E102: Woof-Dwight, Simon: Previous data entry of 1 was inputted here
Note on E123: Woof-Dwight, Simon: '20+' from Logframe return, but the data is unclear in regards to the category itself. Actual attendance data is here, but feedback of those reporting increased understanding does not seem to be here, even if it can be inferred from attendance numbers
Note on E133: Woof-Dwight, Simon: Egypt may fall outside of reporting period
Note on E144: Woof-Dwight, Simon: Data unclear as to whether Rwanda and Telangana assessments are complete within reporting period
Note on E154: Woof-Dwight, Simon: Data indicates 4, however 3 of these are projects receiving funding or approval, and are due to begin after the reporting period. Rwanda project is ongoing, but the first stage is complete.