## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | The International Climate Finance Evidence Project
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Wider understanding of and research into nature-based solutions from public spend (in particular ODA ICF funds), to effectively and efficiently contribute to biodiversity, climate and poverty reduction policies in ODA-elidgible countries. | Tracking citations or use in informing other work in future - Review every 6 months | Planned | 0 citations | 31-Nov-2021: 3 citations or reference in government documents (such as strategy, spending review, Ministerial briefings) | 31-May-2022: 8 citations or reference in government documents (such as strategy, spending review, Ministerial briefings) | 31-Nov-2022: 10 citations or reference in government documents (such as strategy, spending review, Ministerial briefings) | Assume citation tracking is possible within government departments. Limited to citation or reference from government work, not external groups. Assume future reference to NbS or focus on NbS interventions to advance policy priorities on biodiversity, climate, and poverty reduction is traceable to this work (understanding other work may also contribute to focus or messaging). Assume time, resource available to promote this body of work after official project close.
Achieved
Source
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increase in NbS related research projects and events funded or hosted relevant agencies (the stakeholder group, i.e., Defra, FCDO, BEIS etc) | Planned |  | 30-June-2021: 1 workshop/ stakeholder call organised to promote the digital launch and materials | - | 31-May-2022: Delivery of further webinars (number TBD) tailored to audience or released online (i.e., JNCC Youtube channel)
|  | Achieved |  | Delivered 20September
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 542228 |  | 542228 |  | 542228
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Work Package 1) Consider how the contribution to biodiversity conservation policies of NbS can be effectively and efficiently measured at both the project and programme scale. Specific Outputs will be: - Indicator tool & supporting How to User guide -National Biodiversity Metrics: Feasibility Assessment -Consolidation of work in workshops/events combining thought from WP1 and 2 to address the overarching question 'Can Nature-Based Solutions effectively and efficiently contribute to simultaneously achieving HMG’s biodiversity, climate, and poverty-alleviation policies?' | Written outputs of work package 1 include: Indicators and framework review (Tasks 1 and 2) 2 selected indicators and 'how to' guides Review of indicators in context (Task 3) and National biodiversity metrics feasibility assessment (Task 4) Final consolidation of findings which contextualises products with WP2 outputs | Planned | 0 | 05-Mar-2021: Delivery of interim reports on Tasks 1 and 2: indicators and framework reports | 30-Apr-2021: Interim/indicative outlines for Tasks 3 and 4 delivered. Selection of indicators to develop with how to guides | 31-May-2021: Delivery of Tasks 3 and 4 (context of indicators, feasibility assessment) along with how to guides for two selected indicators | Assumes that products from other tasks and interim outputs will be reframed into the final outputs in the indicator. Metric feasibility assessment is still to be fully scoped out. Assumes engagement with steering group through workshops and review/EQA offers chance for active participation, comment, and review to ensure deliver of a high quality product.
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Delivery of 2 engagement workshops for steering group to review, steer, and comment on progress of work. Critical to delivering high quality and targeted output | Planned | 0 | W/c 08-Feb-2021: First engagement meeting | W/c 22-Mar-2021: Second enagagement meeting | W/c 19-Apr-21: Cross WP consolidation engagement meeting
Achieved
Source
IMPACT WEIGHTING (%) |  |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
40% |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Work Package 2) Consider what underlying principles of an NBS ODA project that successfully (i.e. effectively and efficiently) simultaneously contributes to biodiversity, climate, and poverty-alleviation policies. Specific outputs will be: - Task 1: review of NbS databases and case studies and selection of 12 (estimate) exemplary case studies which represent well- implemented NbS - Task 2: Review of the cost-effectiveness of NbS - Task 3 and 4: Principles and implementation guidance for delivering effective and efficient NbS in ODA-eligible countries to ensure delivery for biodiversity, climate, and poverty reduction policies in practise - Task 5: Assessment of financial models on the implementation and delivery of NbS - Task 6: Gap analysis and conclusions or recommendations | Task 1, 3 and 4 completion, consolidation and delivery | Planned | 0 | W/c XXX: Steering Group engagement session | W/c 19-Apr-2021: Interim outputs for review and Steering Group engagement session | 31-May-2021: Consolidated outputs delivered | Assumes adequate resourcing in terms of staff time and planning. Assumes we can secure a communications contractor able to develop final content within budget and with a tight timeline. Assumes staff assigned to different tasks can coordinate activities, conclusions, and collaborate on final products, and that there are no 'knock on' effects of any delays to tasks dependent on prior work (i.e., tasks 3 and 4 depend upon task 1). Assumes engagement and review by Steering Group at engagement sessions and via circulated documents to wnsure a high quality prodcut whcih takes comments and revisions into consideration. Ongoing workshops to 'socialise' the work assumes additional interest from wider cross-government agencies and availaibitly of staff/resources to produce webinars or presentations.
Achieved
Source
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Tasks 2 and 5 developed and delivered | Planned | 0 | w/c 15-Mar-2021: Engagement workshop with Steering Group on interim findings and overall structure | w/c 26-Apr-2021: Draft of Tasks 2 and 5 for Steering Group review. Steering Group engagement w/c 19th April also to consider T2,5 progress | 31-May-2021: Finals of Task 2 and Task 5 incorporated into consolidated output
|  | Achieved |  |  | Subject to revision | Subject to revision
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
60% | Task 6 and overall consolidation with WP1 outputs and conclusions | Planned | 0 | W/c 19-Apr-2021: Engagement session to review consolidation | 31-May-2021: Final consolidated output delivered to Steering Group | 11-June-2021: Delivery of digitised report (*revised based on Communications contractor timeline and availability*)
|  | Achieved |  |  | Completed 10 August | Submitted 2 September
|  | Source |  |  |  |  | RISK RATING
INPUTS (£) | FCDO/Defra (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.